TECHNICAL PROPOSAL

POLICY REVIEW AND LEGAL SCAN

ON DROUGHT GOVERNANCE IN BANGLADESH

Sustainable Urban Water Cycles Project

| SUBMITTED TO | SNV Netherlands Development Organisation |
| --- | --- |
| SUBMITTED BY | ACNABIN, Chartered Accountants |
| SUBMISSION DATE | [INSERT SUBMISSION DATE] |
| SUBMISSION SUBJECT | Policy Review and Legal Scan on Drought Governance in Bangladesh |

ACNABIN, Chartered Accountants

BDBL Bhaban (Level 13 & 15), 12 Kawran Bazar Commercial Area, Dhaka-1215, Bangladesh

www.acnabin.com

# Letter of Transmittal

Date: [INSERT SUBMISSION DATE]

Water Sector Leader
SNV Bangladesh
Dhaka, Bangladesh

Subject: Policy Review and Legal Scan on Drought Governance in Bangladesh

Dear Sir/Madam,

We are pleased to submit ACNABIN's Technical Proposal for the assignment titled “Policy Review and Legal Scan on Drought Governance in Bangladesh.” The proposal has been prepared in accordance with the Terms of Reference and presents our understanding of the assignment, detailed methodology, work plan, team structure, quality assurance arrangements, deliverables, and relevant organizational capability.

We understand that the assignment requires a rigorous review of Bangladesh's legal, policy, and institutional framework for drought management, with particular attention to policy coherence, institutional mandates, coordination, local government and urban drought governance, climate adaptation, financing, accountability, and practical opportunities for the Sustainable Urban Water Cycles Project.

ACNABIN confirms its willingness to undertake the assignment within three months from contract signing, to comply with SNV's confidentiality and non-disclosure requirements, and to work under the direction of the Water Sector Leader, SNV Bangladesh. Our Financial Proposal is submitted separately.

Yours faithfully,

________________________________________

Authorized Signatory: [INSERT NAME AND DESIGNATION]

For and on behalf of: ACNABIN, Chartered Accountants

Date: [INSERT DATE]

Firm seal: [AFFIX SEAL]

# Proposal Completion Notice

Editable draft All yellow-highlighted fields must be completed or confirmed before signature and submission. The CVs must be accurate and signed by both the proposed expert and an authorized official of ACNABIN.

| Submission component | Status / action before submission |
| --- | --- |
| Signed Technical Proposal | [FINALIZE, SIGN AND CONVERT TO PDF] |
| Separate Financial Proposal | [INSERT FEES, SIGN AND SUBMIT SEPARATELY] |
| Detailed Work Plan | Included in Section 6; update only if final staffing changes |
| Signed CVs | [COMPLETE APPENDIX B FOR EACH EXPERT AND OBTAIN TWO SIGNATURES] |
| SNV Due Diligence Form | [COMPLETE, SIGN AND ATTACH WITH MANDATORY DOCUMENTS] |
| Firm supporting documents | [ATTACH REGISTRATION, VAT, TAX COMPLIANCE AND UBO/EQUIVALENT DOCUMENTS] |

# Table of Contents

Letter of Transmittal	2

Proposal Completion Notice	3

Table of Contents	4

Executive Summary	7

1. Understanding of the Assignment	8

1.1 Assignment Context	8

1.2 ACNABIN's Interpretation of the Core Governance Challenge	8

1.3 Analytical Questions	8

1.4 Our Value Proposition	9

2. Objective and Expected Results	10

2.1 Overall Objective	10

2.2 Specific Results	10

3. Scope of Work and ToR Alignment	11

3.1 Policy and Legal Universe	11

3.2 Cross-cutting Lenses	11

3.3 Scope Boundaries	11

4. Technical Approach and Methodology	12

4.1 Methodological Principles	12

4.2 Phase 1 - Inception and Analytical Design	12

4.3 Phase 2 - Policy Review and Legal Scan	12

4.4 Phase 3 - Institutional and Local Governance Analysis	13

4.5 Phase 4 - Stakeholder Consultation and Validation	13

4.6 Phase 5 - Policy Coherence and Inconsistency Analysis	14

4.7 Phase 6 - Recommendations and SUWC Opportunity Prioritization	14

4.8 Phase 7 - Reporting, Validation and Finalization	15

5. Analytical Frameworks and Tools	15

5.1 Policy and Legal Review Matrix	15

5.2 Institutional Mandate and Coordination Matrix	15

5.3 Evidence and Finding Protocol	15

6. Work Plan and Timeline	16

7. Deliverables and Acceptance Framework	17

7.1 Payment Linkage	17

8. Team Composition and Competency	18

8.1 Responsibility Matrix	18

8.2 Team Management and Availability	19

9. Relevant Work and Research Experience	20

10. Firm Profile and Organizational Capability	21

10.1 About ACNABIN	21

10.2 Why ACNABIN for This Assignment	21

10.3 Code of Ethics, Independence and Confidentiality	21

11. Quality Assurance and Risk Management	22

11.1 Quality Assurance Framework	22

11.2 Key Risks and Mitigation	22

12. Reporting, Communication and Client Support	23

12.1 Reporting Line	23

12.2 Communication Protocol	23

12.3 Information and Support Requested from SNV	23

13. Assumptions	24

14. Conclusion	25

Appendix A - ToR Compliance Matrix	26

Appendix B - Curriculum Vitae Format for Proposed Experts	27

B.1 Education	27

B.2 Professional Memberships and Certifications	27

B.3 Employment Record	27

B.4 Relevant Assignment Experience	28

B.5 Languages	28

B.6 Expert Declaration and Signatures	28

Appendix C - Detailed Relevant Assignment Form	29

Appendix D - Pre-submission Document Checklist	30

# Executive Summary

SNV is seeking a comprehensive policy review and legal scan to clarify how drought risk is addressed across Bangladesh's existing laws, policies, plans, strategies, institutional mandates, coordination arrangements, and implementation pathways. The assignment is intended to support future drought resilience interventions under the Sustainable Urban Water Cycles (SUWC) Project and to provide an evidence base for policy dialogue at national and city/local government levels.

ACNABIN proposes an integrated legal-policy-institutional methodology. The approach combines a structured document inventory, provision-level legal mapping, institutional mandate analysis, policy coherence and inconsistency testing, targeted stakeholder consultations, and prioritization of practical opportunities for the SUWC Project. The review will distinguish between binding legal requirements and policy or planning commitments, and it will trace each relevant provision to responsible institutions, coordination arrangements, financing responsibilities, implementation mechanisms, and accountability requirements.

The work will be completed through seven connected phases over twelve weeks: inception and analytical design; policy and legal inventory; institutional and local governance analysis; stakeholder consultation; policy coherence and inconsistency assessment; development and prioritization of recommendations; and drafting, validation, and finalization. The principal outputs will be an Inception Report, a Draft and Final Policy Review and Legal Scan Report, a 10-15 page Policy Brief, and a comprehensive Policy Matrix.

ACNABIN was formed in February 1985 and currently operates as a multidisciplinary professional services firm with eight partners and approximately 500 professionals. It is an independent member firm of Baker Tilly International. The final proposed experts and assignment references will be inserted after completion of the editable schedules in Sections 8 and 9 and the signed CV annexures.

Technical scoring focus The proposal has been organized to respond directly to SNV's technical evaluation areas: understanding of the assignment (30), relevant work/research experience (20), team composition and competency (15), and gender equity in team composition (5).

# 1. Understanding of the Assignment

## 1.1 Assignment Context

SNV's SUWC Project supports city-wide inclusive services across sanitation and hygiene, grey water, solid waste, drainage, and drought management. The project works across four city corporations - Gazipur, Cumilla, Sylhet, and Khulna - and eight municipalities - Shibganj, Chapainawabganj, Kushtia, Joypurhat, Lalmonirhat, Moulvibazar, Chhatak, and Bagerhat. The drought governance assignment therefore needs to connect national laws and institutions with practical mandates, planning systems, service-delivery duties, and accountability arrangements at city and municipal levels.

Bangladesh has multiple legal and policy instruments relevant to disaster management, water resources, groundwater, climate adaptation, agriculture, environment, local government, and urban development. However, the ToR identifies the absence of a consolidated legal or policy framework dedicated solely to drought risk management. Drought provisions and responsibilities are dispersed across instruments and institutions, creating potential uncertainty regarding definitions, mandates, coordination, planning, financing, implementation, and accountability.

## 1.2 ACNABIN's Interpretation of the Core Governance Challenge

The assignment is not limited to summarizing policy documents. Its central analytical task is to determine whether the combined legal, policy, institutional, and implementation architecture provides a coherent and operational system for prevention, mitigation, early warning, preparedness, response, recovery, water allocation, groundwater management, urban drought management, financing, and climate adaptation.

- What constitutes drought under different laws, policies, plans, technical systems, and operational practices, and whether definitions or thresholds are aligned.

- Which institutions have binding legal mandates, policy responsibilities, implementation functions, coordination duties, financing roles, and accountability obligations.

- How national responsibilities translate into city corporation and municipality planning, budgeting, service delivery, enforcement, monitoring, and reporting.

- Where mandates overlap, conflict, remain unassigned, or depend on coordination mechanisms that are unclear or insufficiently operationalized.

- Whether drought is adequately integrated into urban water management, groundwater governance, disaster risk management, climate adaptation, agriculture, environmental protection, and development planning.

- Which gaps or opportunities can be addressed through SUWC-supported evidence, convening, institutional strengthening, local planning tools, policy dialogue, or pilot interventions.

## 1.3 Analytical Questions

| Analytical dimension | Key question for the assignment |
| --- | --- |
| Legal coverage | Do existing laws and subordinate instruments create sufficient authority and duties across the drought risk management cycle? |
| Policy coherence | Are national and sectoral policies mutually consistent, vertically aligned, and capable of joint implementation? |
| Institutional mandates | Are roles, decision rights, coordination duties, and accountability mechanisms clearly assigned? |
| Urban/local governance | Can city corporations and municipalities lawfully plan, finance, implement, monitor, and coordinate drought resilience actions? |
| Implementation architecture | Are planning, financing, data, early warning, enforcement, and monitoring arrangements operational and connected? |
| SUWC opportunity | Which feasible interventions would add value without duplicating existing government or development-partner initiatives? |

## 1.4 Our Value Proposition

- Provision-level traceability: every conclusion will be linked to a specific legal or policy provision and responsible institution.

- Legal-policy distinction: binding legal obligations will be clearly distinguished from policy intentions, plans, guidelines, and institutional practice.

- National-to-local lens: the analysis will explicitly assess translation of national frameworks into city and municipal mandates and implementation pathways.

- Implementation orientation: gaps will be tested against coordination, financing, capacity, enforcement, monitoring, and accountability realities.

- Actionable SUWC recommendations: recommendations will be prioritized according to legality, feasibility, impact, urgency, stakeholder ownership, and SNV's comparative value-add.

# 2. Objective and Expected Results

## 2.1 Overall Objective

To conduct a comprehensive review of Bangladesh's legal, policy, and institutional framework related to drought management and identify practical opportunities for strengthening drought governance in relation to the Sustainable Urban Water Cycles Project.

## 2.2 Specific Results

- A complete, quality-controlled inventory of relevant laws, policies, rules, regulations, plans, strategies, guidelines, and related institutional arrangements.

- A provision-level classification across prevention, mitigation, early warning, preparedness, response, recovery, water allocation, groundwater management, urban drought management, institutional coordination, financing, climate adaptation, and any additional categories emerging from the review.

- An institutional map covering mandates, coordination, planning, implementation, financing, enforcement, monitoring, and accountability responsibilities.

- An evidence-based assessment of policy inconsistencies, overlaps, gaps, ambiguities, and implementation constraints.

- Prioritized recommendations for national and city/local government levels and clearly defined entry points for the SUWC Project.

- A comprehensive report, a decision-focused 10-15 page policy brief, and an editable policy matrix suitable for future policy dialogue and programme design.

# 3. Scope of Work and ToR Alignment

| ToR workstream | ACNABIN response | Primary output |
| --- | --- | --- |
| Policy review and legal scan | Comprehensive inventory, legal status verification, provision extraction, thematic coding, and cross-instrument analysis. | Legal and policy review database; Policy Matrix; report chapters |
| Institutional analysis | Mandate mapping, institutional relationships, coordination and accountability analysis, and national-to-local translation. | Institutional map; mandate/RACI matrix; institutional analysis chapter |
| Policy inconsistencies | Structured testing for conflict, overlap, gap, ambiguity, vertical misalignment, financing disconnect, and implementation barriers. | Policy coherence and inconsistency matrix; prioritized findings |
| Recommendations and reporting | Co-design and prioritization of legally sound, feasible, and SUWC-relevant recommendations for national and city/local levels. | Draft and final report; Policy Brief; recommendation roadmap |

## 3.1 Policy and Legal Universe

The review will cover the instruments identified in the ToR, including the Disaster Management Act, National Disaster Management Policy, National Plan for Disaster Management, Bangladesh Delta Plan 2100, Bangladesh Climate Change Strategy and Action Plan, National Water Policy, Bangladesh Water Act, National Water Management Plan, groundwater management regulations, National Adaptation Plan, National Agriculture Policy, Standing Orders on Disaster, Local Government Acts, urban development policies, environmental laws, and any other relevant legislation or implementation instruments identified during inception.

The final document universe will be agreed through the Inception Report and maintained as a controlled review register showing the instrument title, issuing authority, legal status, date/version, amendments, official source, relevance, review status, and analyst responsible.

## 3.2 Cross-cutting Lenses

- Urban and peri-urban drought risk and the urban water cycle.

- National-local vertical coordination and subsidiarity.

- Groundwater abstraction, allocation, monitoring, conservation, and enforcement.

- Climate adaptation and integration with development planning and budgeting.

- Gender equality, social inclusion, vulnerability, and equitable service access.

- Public-private engagement, institutional capacity, financing, data, early warning, and accountability.

- Consistency with ongoing government and development-partner drought reduction initiatives.

## 3.3 Scope Boundaries

Scope control This policy, legal, and institutional review excludes legal representation, legislative drafting, hydrological or engineering work, and city-level vulnerability assessment unless SNV agrees a written scope change.

# 4. Technical Approach and Methodology

## 4.1 Methodological Principles

- Authoritative sourcing: use official or legally reliable versions of laws, rules, policies, plans, and amendments.

- Traceability: maintain a clear audit trail from source provision to finding, conclusion, and recommendation.

- Triangulation: test documentary findings through institutional evidence, consultation, and implementation examples.

- Legal hierarchy: distinguish constitutional or statutory authority, subordinate instruments, policy commitments, plans, guidelines, and administrative practice.

- Participation: consult relevant institutions to validate mandates, coordination, operational constraints, and feasible reform pathways.

- Use orientation: design the Policy Matrix and Policy Brief as practical tools for SNV and government dialogue, not merely annexes to the report.

- Proportionality: prioritize areas that materially affect drought governance and SUWC programming within the three-month timeframe.

## 4.2 Phase 1 - Inception and Analytical Design

The assignment will begin with a kick-off meeting with the Water Sector Leader and relevant SUWC team members. ACNABIN will confirm the scope, expectations, deliverable review protocol, stakeholder access, document sources, consultation needs, and communication arrangements. The analytical framework and quality control procedures will be finalized during this phase.

- Confirm the assignment questions, scope boundaries, deliverable structure, and acceptance process.

- Develop the literature review framework, instrument inventory, coding structure, and review templates.

- Prepare the stakeholder map, consultation plan, interview guides, and evidence request list.

- Agree the report outline, Policy Brief architecture, Policy Matrix fields, and file management protocol.

- Submit the Inception Report with detailed methodology and twelve-week work plan.

## 4.3 Phase 2 - Policy Review and Legal Scan

Each instrument will be reviewed at provision level. The team will record the operative text or accurate summary, legal status, responsible institution, scope, decision or duty created, implementation mechanism, coordination requirement, financing implication, enforcement or accountability provision, and relevance to urban/local drought governance.

| Review field | Illustrative content |
| --- | --- |
| Instrument control | Official title, issuing authority, year/version, amendments, legal status, source, and review status |
| Provision coding | Section/article/paragraph; duty or power; responsible institution; beneficiary or regulated party |
| Drought category | Prevention, mitigation, early warning, preparedness, response, recovery, allocation, groundwater, urban, coordination, financing, adaptation |
| Implementation link | Plan, budget, procedure, information system, licence, enforcement, monitoring, reporting, or grievance/accountability mechanism |
| Coherence finding | Consistent, complementary, overlapping, conflicting, ambiguous, silent, obsolete, or operationally disconnected |
| SUWC relevance | National policy dialogue, city planning, capacity building, evidence, coordination platform, pilot tool, or implementation support |

## 4.4 Phase 3 - Institutional and Local Governance Analysis

The institutional analysis will convert the policy and legal findings into an operational map of who is authorized, responsible, accountable, consulted, and informed across the drought governance cycle. It will consider ministries, departments, technical agencies, local government institutions, coordinating bodies, and other actors identified through the review.

- Legal mandate and policy responsibility.

- Planning, budgeting, implementation, enforcement, monitoring, and reporting responsibility.

- Vertical relationships between national institutions and city corporations/municipalities.

- Horizontal coordination across disaster management, water, local government, agriculture, environment, and climate institutions.

- Information and early-warning flows, decision triggers, escalation pathways, and accountability mechanisms.

- Institutional capacity and implementation constraints identified through documentary evidence and consultations.

## 4.5 Phase 4 - Stakeholder Consultation and Validation

Consultations will be targeted and evidence-led. They will clarify how formal mandates operate in practice, identify coordination and implementation constraints, test preliminary interpretations, and build ownership of feasible recommendations. Consultations will primarily take place in Dhaka if required, consistent with the ToR. Remote consultations may be used where efficient and agreed with SNV.

| Indicative stakeholder group | Purpose | Method |
| --- | --- | --- |
| SNV Water Sector Leader and SUWC team | Confirm scope, project priorities, city context, existing studies, and intended use of findings. | Kick-off, progress reviews, validation |
| Disaster management institutions | Clarify drought risk governance, early warning, preparedness, response, and national-local coordination. | Key informant interviews |
| Water resources and groundwater institutions | Clarify allocation, abstraction, monitoring, conservation, data, and regulatory mandates. | Key informant interviews / technical consultation |
| Local government, DPHE, LGED and urban institutions | Test city/municipal mandates, planning, service delivery, financing, and implementation constraints. | Key informant interviews / focused group discussion |
| Climate, environment and agriculture institutions | Assess cross-sector policy integration, adaptation planning, environmental regulation, and drought-sensitive agriculture. | Key informant interviews |
| Academia, civil society and development partners | Identify evidence, implementation lessons, ongoing initiatives, and feasible policy options. | Expert consultation / document request |

Finalization at inception SNV and ACNABIN will confirm the stakeholder list, consultation methods, sequence, and number in the Inception Report, subject to availability and access.

## 4.6 Phase 5 - Policy Coherence and Inconsistency Analysis

The team will compare instruments and mandates using a structured inconsistency typology. A finding will not be classified as an inconsistency merely because two instruments address the same subject; the review will determine whether the provisions are complementary, duplicative, conflicting, ambiguous, incomplete, or operationally disconnected.

| Inconsistency type | Test applied |
| --- | --- |
| Legal conflict | Two binding provisions prescribe incompatible duties, powers, procedures, or outcomes. |
| Mandate overlap | Multiple institutions hold similar responsibilities without clear lead, sequencing, or coordination rules. |
| Mandate gap | A necessary function is not clearly assigned or lacks authority, procedure, resources, or accountability. |
| Vertical misalignment | National responsibilities do not translate clearly into city/municipal mandates, plans, budgets, or reporting. |
| Policy-plan disconnect | Policy commitments are absent from operational plans, financing arrangements, indicators, or implementation guidance. |
| Definition or threshold ambiguity | Key terms, drought triggers, risk classifications, or decision thresholds are inconsistent or undefined. |
| Implementation inconsistency | Formal provisions are coherent, but practice, capacity, coordination, data, enforcement, or financing prevents implementation. |

## 4.7 Phase 6 - Recommendations and SUWC Opportunity Prioritization

Recommendations will be written as specific actions with a clear rationale, responsible institution, required coordination, indicative sequence, implementation conditions, and potential role for SUWC. They will be grouped into immediate, medium-term, and longer-term opportunities and prioritized through an explicit assessment framework.

| Prioritization criterion | Assessment question |
| --- | --- |
| Legal and policy soundness | Is the action supported by existing authority, or does it require amendment, clarification, or a new instrument? |
| Impact | Would the action materially improve prevention, preparedness, coordination, local implementation, equity, or accountability? |
| Feasibility | Are institutional ownership, capacity, resources, information, and coordination conditions realistic? |
| Urgency and sequencing | Is the action time-sensitive or a prerequisite for other reforms? |
| SUWC value-add | Can SNV make a distinctive contribution through evidence, convening, technical support, capacity building, or piloting? |
| Sustainability and scale | Can the action be institutionalized, replicated, financed, and monitored beyond the project period? |

## 4.8 Phase 7 - Reporting, Validation and Finalization

- Prepare and submit the Draft Policy Review and Legal Scan Report, and present key findings in a structured validation session if requested by SNV.

- Maintain a consolidated comment-response matrix and incorporate agreed revisions after quality assurance.

- Submit the Final Report, 10-15 page Policy Brief, Policy Matrix, editable source files, and signed/approved versions in the format agreed with SNV.

# 5. Analytical Frameworks and Tools

## 5.1 Policy and Legal Review Matrix

The Policy Matrix will be the principal evidence and traceability tool. It will be maintained throughout the assignment and delivered in editable form. The final column set will be confirmed with SNV during inception.

| Field group | Proposed matrix fields |
| --- | --- |
| Instrument identity | Title; authority; year/version; legal status; amendment status; official source |
| Provision identity | Section/article/paragraph; accurate provision summary; applicable geography and institution |
| Thematic coding | Drought category; disaster cycle stage; water/groundwater/urban/climate/finance/accountability tags |
| Institutional mapping | Lead institution; supporting institution; local government role; coordination mechanism |
| Implementation | Planning, budgeting, procedure, enforcement, monitoring, data, early warning, and reporting mechanism |
| Assessment | Strength; gap; overlap; conflict; ambiguity; implementation issue; supporting evidence |
| Recommendation | Proposed action; responsible actor; priority; sequence; SUWC opportunity; dependency |

## 5.2 Institutional Mandate and Coordination Matrix

The institutional matrix will map each institution's legal mandate, policy responsibility, operational role, decision authority, coordination relationship, financing responsibility, accountability mechanism, and national-local interface. Where useful, a Responsible-Accountable-Consulted-Informed view will be applied to specific drought governance functions.

## 5.3 Evidence and Finding Protocol

- Each major finding will identify the source instrument or consultation evidence supporting it.

- Conflicting interpretations will be recorded and resolved through legal hierarchy, subsequent amendment, official clarification, or transparent qualification in the report.

- Consultation evidence will not override binding legal text; it will be used to explain implementation practice and constraints.

- Recommendations requiring legal amendment will be clearly distinguished from those achievable through rules, guidance, coordination, planning, capacity, budgeting, or administrative action.

# 6. Work Plan and Timeline

The assignment will be completed within three months from contract signing. The following twelve-week plan is indicative and will be refined in the Inception Report based on the contract date, stakeholder access, and SNV's review schedule.

| Activity | W1-2 | W3-4 | W5-6 | W7-8 | W9-10 | W11-12 |
| --- | --- | --- | --- | --- | --- | --- |
| Kick-off, inception design, document request | ● |  |  |  |  |  |
| Instrument inventory and literature review | ● | ● |  |  |  |  |
| Provision extraction and policy/legal coding | ● | ● | ● |  |  |  |
| Institutional mapping and mandate analysis |  | ● | ● | ● |  |  |
| Stakeholder consultations |  | ● | ● | ● |  |  |
| Policy coherence and inconsistency analysis |  |  | ● | ● | ● |  |
| Recommendations and SUWC opportunity design |  |  |  | ● | ● |  |
| Draft report and draft policy matrix |  |  |  |  | ● |  |
| SNV review / validation / revisions |  |  |  |  | ● | ● |
| Final report, policy brief and policy matrix |  |  |  |  |  | ● |

| Milestone | Indicative timing | Review/approval |
| --- | --- | --- |
| Inception Report | End of Week 2 | SNV review and approval |
| Draft Policy Review and Legal Scan Report | End of Week 10 | SNV review and consolidated comments |
| Final Report, Policy Brief and Policy Matrix | End of Week 12 | SNV approval |

# 7. Deliverables and Acceptance Framework

| Deliverable | Minimum content | Quality/acceptance focus |
| --- | --- | --- |
| Inception Report | Detailed methodology; work plan; literature review framework; instrument universe; stakeholder consultation plan; analytical tools; report outline; risk and quality plan. | Completeness, feasibility, alignment with ToR, and agreed scope/sequence. |
| Draft Policy Review and Legal Scan Report | Policy and legal scan; institutional analysis; policy inconsistencies; city/local and national findings; draft recommendations; draft SUWC opportunities; supporting annexures. | Evidence traceability, analytical depth, policy coherence, institutional clarity, and practical relevance. |
| Final Policy Review and Legal Scan Report | Revised and quality-assured final report incorporating agreed comments and a comment-response record. | Accuracy, completeness, clear conclusions, usable recommendations, and SNV approval. |
| Policy Brief (10-15 pages) | Concise problem statement; priority findings; institutional implications; recommended actions; SUWC entry points; decision-focused visuals/tables where useful. | Clarity, brevity, senior-policy audience suitability, and consistency with final report. |
| Policy Matrix | Editable provision-level matrix of instruments, drought-relevant provisions, responsible institutions, findings, and recommendations. | Completeness, usability, traceability, filtering, and consistency with report. |

## 7.1 Payment Linkage

| Payment milestone | Percentage |
| --- | --- |
| Upon submission of the Inception Report | 30% |
| Upon submission of the Draft Report | 30% |
| Upon approval of the Final Report, Policy Brief and Policy Matrix | 40% |

# 8. Team Composition and Competency

The core team structure follows the ToR. The final names, academic qualifications, gender, years of experience, and assignment references must be completed from signed and verified CVs before submission.

| Proposed role | Proposed expert | ToR minimum qualification | Assignment responsibility |
| --- | --- | --- | --- |
| Team Leader / Policy & Governance Specialist | [INSERT NAME, GENDER AND AVAILABILITY] | PhD/Master's in Public Policy, Governance, Public Administration, Environmental Policy, Law, or related field; 10 years; PhD preferable. | Overall leadership; methodology; policy and governance analysis; stakeholder engagement; integration of findings; report quality and delivery. |
| Legal & Regulatory Specialist | [INSERT NAME, GENDER AND AVAILABILITY] | LL.M. in Law, preferably Environmental Law, Public Law, Administrative Law, Water Law, or related field; 8 years. | Legal inventory; legal status and hierarchy; provision analysis; inconsistency testing; legal recommendations; quality assurance of legal findings. |
| Institutional & Local Governance Expert | [INSERT NAME, GENDER AND AVAILABILITY] | Master's in Public Administration, Governance, Development Studies, Disaster Management, Urban Planning, or related field; 5 years. | Institutional mapping; national-local mandate analysis; coordination, planning, implementation and accountability review; consultation support. |
| Research & Policy Analyst (support) | [INSERT NAME OR STATE INTERNAL SUPPORT ARRANGEMENT] | Relevant postgraduate qualification and demonstrated research capability. | Instrument register; literature review; evidence management; matrix maintenance; consultation notes; annexures and documentation. |
| Independent Quality Assurance Reviewer | [INSERT NAME / PARTNER] | Senior professional with relevant quality review capability. | Independent review of methodology, evidence trail, findings, recommendations, consistency, and deliverable completeness. |

Gender equity - mandatory scoring item [CONFIRM BEFORE SUBMISSION] Include meaningful female representation in the core team, preferably by appointing at least one woman to a substantive expert role. Ensure the team table and signed CVs clearly show gender and responsibilities.

## 8.1 Responsibility Matrix

| Activity | Team Leader | Legal Specialist | Institutional Expert | Research Support | QA Reviewer |
| --- | --- | --- | --- | --- | --- |
| Inception and methodology | A/R | C | C | S | C |
| Policy and legal scan | A | R | C | S | C |
| Institutional mapping | A | C | R | S | C |
| Stakeholder consultations | A/R | C | R | S |  |
| Inconsistency analysis | A | R | R | S | C |
| Recommendations and SUWC opportunities | A/R | R | R | S | C |
| Drafting and finalization | A/R | R | R | S | C |
| Independent quality review | C | C | C |  | R |

Legend: A = Accountable; R = Responsible; C = Consulted; S = Support.

## 8.2 Team Management and Availability

- The Team Leader will be the primary technical focal point and will coordinate all workstreams and submissions.

- Each expert will sign an availability and accuracy declaration through the CV format in Appendix B.

- Weekly internal coordination and evidence review sessions will be held during active analytical phases.

- Substitution of a named expert will be subject to SNV's prior approval and replacement with an expert of equal or higher qualification.

- The team will maintain a shared evidence register, issue tracker, consultation tracker, and comment-response matrix.

# 9. Relevant Work and Research Experience

SNV allocates 20 technical marks to relevant work/research experience. The table below should contain only assignments that can be supported by contracts, work orders, completion certificates, client references, or verifiable deliverables and that directly demonstrate policy analysis, legal/regulatory review, institutional or governance studies, disaster risk management, climate adaptation, water resources, environmental governance, local government, or government/development-partner engagement.

| No. | Assignment / client | Period / value | Scope and relevance | Evidence / reference |
| --- | --- | --- | --- | --- |
| 1 | [ASSIGNMENT TITLE AND CLIENT] | [PERIOD / CONTRACT VALUE] | [SCOPE, METHODOLOGY, DELIVERABLES AND DIRECT RELEVANCE TO THIS TOR] | [EVIDENCE / CLIENT CONTACT] |
| 2 | [ASSIGNMENT TITLE AND CLIENT] | [PERIOD / CONTRACT VALUE] | [SCOPE, METHODOLOGY, DELIVERABLES AND DIRECT RELEVANCE TO THIS TOR] | [EVIDENCE / CLIENT CONTACT] |
| 3 | [ASSIGNMENT TITLE AND CLIENT] | [PERIOD / CONTRACT VALUE] | [SCOPE, METHODOLOGY, DELIVERABLES AND DIRECT RELEVANCE TO THIS TOR] | [EVIDENCE / CLIENT CONTACT] |
| 4 | [ASSIGNMENT TITLE AND CLIENT] | [PERIOD / CONTRACT VALUE] | [SCOPE, METHODOLOGY, DELIVERABLES AND DIRECT RELEVANCE TO THIS TOR] | [EVIDENCE / CLIENT CONTACT] |
| 5 | [ASSIGNMENT TITLE AND CLIENT] | [PERIOD / CONTRACT VALUE] | [SCOPE, METHODOLOGY, DELIVERABLES AND DIRECT RELEVANCE TO THIS TOR] | [EVIDENCE / CLIENT CONTACT] |
| 6 | [ASSIGNMENT TITLE AND CLIENT] | [PERIOD / CONTRACT VALUE] | [SCOPE, METHODOLOGY, DELIVERABLES AND DIRECT RELEVANCE TO THIS TOR] | [EVIDENCE / CLIENT CONTACT] |

Evidence discipline Do not list a client name alone. For each assignment, state the specific scope performed, dates, deliverables, relevance, ACNABIN's role, and available evidence. Delete any row that cannot be substantiated.

# 10. Firm Profile and Organizational Capability

## 10.1 About ACNABIN

ACNABIN, Chartered Accountants, was formed in February 1985. The firm currently has eight partners and approximately 500 professionals of varied experience and expertise. It provides assurance, tax, business consulting, risk and advisory, sustainability advisory, corporate finance, business process outsourcing, and information systems audit and advisory services. ACNABIN is an independent member firm of Baker Tilly International, a global top-ten professional services network.

The firm serves private, public, NGO, development-partner, and UN-related engagements across multiple sectors. For this assignment, ACNABIN will combine policy and governance analysis, legal and regulatory review, institutional assessment, evidence management, stakeholder consultation, and independent quality review through a multidisciplinary team.

## 10.2 Why ACNABIN for This Assignment

- Multidisciplinary platform: access to policy, governance, legal/regulatory, institutional, sustainability, risk, assurance, taxation, and information-system expertise.

- Evidence and quality discipline: professional methods for documentation, review trails, quality control, confidentiality, and defensible reporting.

- Bangladesh institutional context: experience working across public, private, NGO, and development-partner environments in Bangladesh.

- Implementation orientation: ability to translate policy and institutional findings into practical governance, control, coordination, accountability, and implementation recommendations.

- Scalable project management: partner oversight, designated team leadership, structured review protocols, and capacity to mobilize additional research and documentation support.

## 10.3 Code of Ethics, Independence and Confidentiality

- Complete conflict-of-interest and independence checks before mobilization and update them if circumstances change.

- Treat all client information, consultation records, drafts, and working papers as confidential and restrict access to authorized team members.

- Comply with the Non-Disclosure Agreement required by SNV.

- Apply professional conduct, anti-fraud, safeguarding, and reporting expectations relevant to SNV's supplier requirements.

- Use information only for the purposes of the assignment and retain or dispose of records in accordance with contractual requirements.

# 11. Quality Assurance and Risk Management

## 11.1 Quality Assurance Framework

Quality assurance will operate at four levels: analyst self-review, workstream review by the relevant specialist, integrated review by the Team Leader, and independent technical review before each major submission. The team will maintain version control, source traceability, issue logs, cross-reference checks, and a consolidated comment-response matrix.

- Source verification and legal status check for every instrument included in the final matrix.

- Completeness check against the ToR instrument list and analytical categories.

- Cross-workstream consistency check between legal provisions, institutional mandates, findings, and recommendations.

- Factual validation of institutional descriptions through documentary evidence and, where appropriate, consultation.

- Editorial review for accuracy, clarity, neutrality, accessibility, and consistency across the report, brief, and matrix.

- Final compliance check against deliverable requirements before submission.

## 11.2 Key Risks and Mitigation

| Risk | Potential effect | Mitigation |
| --- | --- | --- |
| Incomplete or outdated instrument set | Omission or inaccurate legal/policy conclusions | Establish a controlled document register; verify official versions and amendments; record unresolved status transparently. |
| Delayed stakeholder access | Reduced consultation coverage or timeline pressure | Agree priority stakeholders early; schedule in parallel; use remote consultation and documentary validation where approved. |
| Conflicting institutional interpretations | Ambiguous mandate or coordination conclusions | Triangulate with legal text, official documents, multiple perspectives, and clearly qualified findings. |
| Scope expansion | Delay and dilution of analytical depth | Confirm scope boundaries in inception; maintain an issue/change log; seek written approval for material additions. |
| Overly generic recommendations | Limited usefulness for SNV and government dialogue | Use an action template naming actor, legal basis, sequence, feasibility conditions, priority, and SUWC role. |
| Inconsistency across outputs | Report, brief, and matrix do not align | Use one master evidence database and complete cross-output reconciliation before finalization. |
| Confidentiality or data handling failure | Reputational and contractual risk | Restrict access, use secure storage, apply NDA requirements, and control circulation of drafts and consultation records. |

# 12. Reporting, Communication and Client Support

## 12.1 Reporting Line

The consultant team will report directly to the Water Sector Leader, SNV Bangladesh, as specified in the ToR.

## 12.2 Communication Protocol

- Kick-off meeting and confirmation of focal points at commencement.

- Weekly progress update by email or meeting during active review periods.

- Early escalation of access, scope, legal-source, or timeline issues requiring SNV direction.

- Submission of deliverables through agreed electronic channels with clear version and status labels.

- Consolidation of SNV comments through one comment-response matrix for controlled revision.

## 12.3 Information and Support Requested from SNV

- Relevant SUWC project documents, earlier studies, city-level information, and existing drought-related analyses.

- Introduction or facilitation support for priority government and stakeholder consultations, where required.

- Timely consolidated comments on inception, draft, and final deliverables.

- Confirmation of intended audiences, branding, formatting, and dissemination expectations for the Policy Brief and final report.

- Direction on confidentiality classification, document handling, and consultation-record requirements.

# 13. Assumptions

- The assignment will be completed within twelve weeks from contract signing, subject to timely access to documents, stakeholders, and consolidated feedback.

- The assignment will be primarily desk-based, with stakeholder consultations in Dhaka if required by SNV.

- SNV will provide available project documents and facilitate access to priority stakeholders where institutional protocol requires its support.

- Deliverables will be prepared in English unless otherwise agreed in writing.

- Material changes to scope, additional field locations, extensive primary data collection, legislative drafting, or technical modelling will be managed through written agreement.

- The final number and format of hard copies, if any, will be agreed during inception; the ToR requests electronic submission of the proposal and does not prescribe hard-copy deliverables for the consultancy.

# 14. Conclusion

ACNABIN appreciates the opportunity to submit this proposal to SNV Bangladesh. Our approach is designed to produce a defensible and usable analysis of Bangladesh's drought governance architecture while maintaining clear traceability from law and policy to institutions, implementation challenges, recommendations, and SUWC programming opportunities.

Subject to finalization of the proposed experts, relevant assignment evidence, and commercial schedules, ACNABIN is prepared to mobilize promptly and complete the assignment within the three-month period stated in the ToR.

# Appendix A - ToR Compliance Matrix

| ToR requirement | Proposal response / location | Status |
| --- | --- | --- |
| Overall understanding of assignment | Sections 1-3 and Executive Summary | Complied |
| Detailed methodology | Sections 4-5 | Complied |
| Work plan | Section 6 | Complied |
| Deliverables | Section 7 | Complied |
| Team composition and competency | Section 8 and Appendix B | [COMPLETE CVs] |
| Gender equity | Section 8 team table and gender note | [CONFIRM FINAL TEAM] |
| Relevant work/research experience | Section 9 and Appendix C | [INSERT VERIFIED ASSIGNMENTS] |
| Three-month timeline | Section 6 | Complied |
| Reporting to Water Sector Leader | Section 12 | Complied |
| Confidentiality/NDA | Section 10.3 | Complied |
| Separate financial proposal | Separate Financial Proposal document | [COMPLETE AND SIGN] |
| SNV Due Diligence supplier registration form | Submitted as separate attachment | [COMPLETE AND SIGN] |
| Accurate CVs signed by expert and authorized official | Appendix B certification blocks | [OBTAIN BOTH SIGNATURES] |

# Appendix B - Curriculum Vitae Format for Proposed Experts

Instruction Duplicate this CV format for each proposed expert. Complete every field, remove drafting instructions, and obtain signatures from both the expert and ACNABIN's authorized official.

| CV field | Details |
| --- | --- |
| Proposed position | [INSERT ROLE] |
| Name of expert | [INSERT FULL NAME] |
| Gender | [INSERT] |
| Nationality | [INSERT] |
| Current employer / position | [INSERT] |
| Years with current employer | [INSERT] |
| Total years of relevant experience | [INSERT] |
| Availability during assignment | [INSERT] |
| Contact information | [INSERT EMAIL AND TELEPHONE] |

## B.1 Education

| Degree / field | Institution / country | Year |
| --- | --- | --- |
| [DEGREE / FIELD] | [INSTITUTION / COUNTRY] | [YEAR] |
| [DEGREE / FIELD] | [INSTITUTION / COUNTRY] | [YEAR] |
| [DEGREE / FIELD] | [INSTITUTION / COUNTRY] | [YEAR] |

## B.2 Professional Memberships and Certifications

| Membership / certification | Issuing body | Year / status |
| --- | --- | --- |
| [MEMBERSHIP / CERTIFICATION] | [ISSUING BODY] | [YEAR / STATUS] |
| [MEMBERSHIP / CERTIFICATION] | [ISSUING BODY] | [YEAR / STATUS] |
| [MEMBERSHIP / CERTIFICATION] | [ISSUING BODY] | [YEAR / STATUS] |

## B.3 Employment Record

| Period | Employer / country | Position | Key responsibilities |
| --- | --- | --- | --- |
| [FROM-TO] | [EMPLOYER / COUNTRY] | [POSITION] | [KEY RESPONSIBILITIES] |
| [FROM-TO] | [EMPLOYER / COUNTRY] | [POSITION] | [KEY RESPONSIBILITIES] |
| [FROM-TO] | [EMPLOYER / COUNTRY] | [POSITION] | [KEY RESPONSIBILITIES] |
| [FROM-TO] | [EMPLOYER / COUNTRY] | [POSITION] | [KEY RESPONSIBILITIES] |
| [FROM-TO] | [EMPLOYER / COUNTRY] | [POSITION] | [KEY RESPONSIBILITIES] |

## B.4 Relevant Assignment Experience

| Period | Assignment / client / country | Role | Relevant tasks and outputs |
| --- | --- | --- | --- |
| [PERIOD] | [ASSIGNMENT / CLIENT / COUNTRY] | [ROLE] | [RELEVANT TASKS AND OUTPUTS] |
| [PERIOD] | [ASSIGNMENT / CLIENT / COUNTRY] | [ROLE] | [RELEVANT TASKS AND OUTPUTS] |
| [PERIOD] | [ASSIGNMENT / CLIENT / COUNTRY] | [ROLE] | [RELEVANT TASKS AND OUTPUTS] |
| [PERIOD] | [ASSIGNMENT / CLIENT / COUNTRY] | [ROLE] | [RELEVANT TASKS AND OUTPUTS] |
| [PERIOD] | [ASSIGNMENT / CLIENT / COUNTRY] | [ROLE] | [RELEVANT TASKS AND OUTPUTS] |

## B.5 Languages

| Language | Speaking | Reading | Writing |
| --- | --- | --- | --- |
| [INSERT] | [LEVEL] | [LEVEL] | [LEVEL] |
| [INSERT] | [LEVEL] | [LEVEL] | [LEVEL] |
| [INSERT] | [LEVEL] | [LEVEL] | [LEVEL] |

## B.6 Expert Declaration and Signatures

I certify that the information in this CV is accurate and complete and that I am available to undertake the assignment in the proposed position. I understand that any material misstatement may result in rejection or contractual action.

| Expert name | [INSERT] |
| --- | --- |
| Expert signature and date | [SIGN AND DATE] |
| Authorized ACNABIN official | [INSERT NAME AND DESIGNATION] |
| Authorized signature, date and seal | [SIGN, DATE AND AFFIX SEAL] |

# Appendix C - Detailed Relevant Assignment Form

Instruction Duplicate this form for each assignment included in Section 9. Attach or cross-reference verifiable evidence.

| Field | Assignment details |
| --- | --- |
| Assignment title | [INSERT] |
| Client and country | [INSERT] |
| Contract period and value | [INSERT] |
| ACNABIN's role | [PRIME / SUBCONSULTANT / OTHER] |
| Scope of services | [INSERT DETAILED SCOPE] |
| Methodology applied | [INSERT] |
| Key deliverables | [INSERT] |
| Relevance to SNV ToR | [POLICY / LEGAL / GOVERNANCE / DRM / CLIMATE / WATER / LOCAL GOVERNMENT] |
| Key experts involved | [INSERT] |
| Client reference | [NAME, TITLE, EMAIL, TELEPHONE] |
| Evidence attached | [CONTRACT / WORK ORDER / CERTIFICATE / REPORT COVER / OTHER] |

# Appendix D - Pre-submission Document Checklist

| No. | Check | Done |
| --- | --- | --- |
| 1 | Technical Proposal completed, reviewed, signed, and converted to PDF | [ ] |
| 2 | Financial Proposal completed and signed as a separate file | [ ] |
| 3 | Work plan consistent with team availability and contract period | [ ] |
| 4 | Each CV accurate and signed by expert and authorized official | [ ] |
| 5 | Gender equity clearly demonstrated in team composition | [ ] |
| 6 | Relevant assignment claims supported by evidence | [ ] |
| 7 | SNV Due Diligence Supplier Registration and Vetting Form completed and signed | [ ] |
| 8 | Certificate of registration / national equivalent attached | [ ] |
| 9 | VAT registration certificate attached | [ ] |
| 10 | Tax compliance certificate attached | [ ] |
| 11 | UBO extract or equivalent declaration / trade licence attached | [ ] |
| 12 | Bank details and supporting document checked | [ ] |
| 13 | Email recipient and exact subject line checked | [ ] |
| 14 | Submission scheduled before 5:00 p.m. Bangladesh time on 25 August 2026 | [ ] |