ACNABIN

in association with

CipherShield

TECHNICAL PROPOSAL

Selection of an AI Strategy & Governance Consulting Partner

Enterprise AI Strategy, Governance Framework and Implementation Roadmap

| Client | BRAC Bank PLC |
| --- | --- |
| Attention | Head of Enterprise AI / Procurement Committee, BRAC Bank PLC |
| Submitted By | ACNABIN Chartered Accountants (Baker Tilly International) in association with CipherShield |
| Reference | ToR — Enterprise AI Strategy (Annexure 1) |
| Date | 09 July 2026 |
| Classification | Confidential — Prepared exclusively for BRAC Bank PLC |

# Table of Contents

Table of Contents	2

1. Executive Summary	3

2. About the Proposing Consortium	4

2.1 ACNABIN Chartered Accountants	4

2.2 CipherShield	4

2.3 Why This Partnership	4

3. Understanding of the Assignment	6

4. Proposed Approach & Methodology	7

4.1 Guiding Principles	7

4.2 Delivery Structure	7

Workstream A — AI Readiness and Prioritised Use-Case Portfolio	7

Workstream B — Enterprise AI Governance and Control Framework	7

Workstream C — Enterprise AI Strategy, Roadmap and Business Case	8

4.3 Indicative Timeline	8

5. Deliverables Mapping	10

6. Team Composition & Capability	12

6.1 Engagement Sponsors	12

6.2 Workstream Leadership	12

6.3 Delivery Bench	12

6.4 Knowledge Transfer Approach	12

7. Experience & Credentials	13

7.1 ACNABIN	13

7.2 CipherShield	13

7.3 Relevant Comparable Engagement	13

8. Knowledge Transfer & Capacity Building	14

Staff Training Programme	14

Executive Awareness Sessions	14

9. Post-Engagement Support	15

10. Compliance with Respondent Requirements	16

11. Confidentiality & Conflict of Interest Declaration	17

12. Closing Statement	18

# 1. Executive Summary

BRAC Bank PLC (“the Bank”) is pursuing a disciplined, enterprise-wide approach to Artificial Intelligence (AI) — moving toward orchestrated, governed, and value-driven adoption of AI across its business and technology functions. ACNABIN Chartered Accountants, a member firm of Baker Tilly International, and CipherShield, an Australian cybersecurity and risk advisory firm with a Bangladesh presence, are pleased to submit this joint technical proposal in response to the Bank's Terms of Reference for the selection of an AI Strategy & Governance Consulting Partner.

This is an outcome-based engagement, and our proposed approach is built accordingly. Rather than prescribing a single fixed methodology, we combine two complementary bodies of expertise — ACNABIN's deep grounding in Bangladesh Bank regulation, financial-sector audit, internal control, and enterprise risk governance, and CipherShield's specialist capability in AI governance, model risk, cybersecurity, and technology architecture — into a single, accountable delivery team that can credibly own all three required outcomes:

- Outcome A: AI Readiness and a prioritised, evidence-based use-case portfolio.

- Outcome B: An enterprise AI governance and control framework that integrates with existing risk, audit, and technology governance rather than duplicating it.

- Outcome C: An enterprise AI strategy, target-state architecture, phased roadmap, and a quantified, fundable business case.

Our combined team is deliberately structured to avoid a “black-box” hand-off. Every framework, model, scoring methodology, and governance artefact we produce will be transparent, auditable, and fully transferable to the Bank's own teams — consistent with the standard both firms apply on regulatory transformation engagements in the banking sector, including our recent joint work on an IFRS 9 Expected Credit Loss transformation for a leading Bangladeshi commercial bank.

We anchor our approach on the Bank's existing technology, data, and private-cloud investments; we align recommendations with Bangladesh Bank's regulatory expectations as well as emerging international AI governance standards (e.g. ISO/IEC 42001, NIST AI RMF); and we place a sustained emphasis on capability uplift so that the Bank retains full ownership and control of its AI programme once our engagement concludes. Commercial terms and pricing are addressed separately, per Section 2.3 of the ToR, and are therefore excluded from this technical proposal.

# 2. About the Proposing Consortium

## 2.1 ACNABIN Chartered Accountants

Founded in February 1985, ACNABIN is one of the largest and most established chartered accountancy practices in Bangladesh, with more than 40 years of continuous public practice. ACNABIN is a member firm of Baker Tilly International and is licensed by the Institute of Chartered Accountants of Bangladesh (ICAB) and approved by Bangladesh Bank for audit and assurance services. The firm is led by eight partners and supported by over 700 personnel, giving it one of the deepest benches of any accountancy and advisory firm in the country.

ACNABIN has extensive, long-standing experience auditing and advising banking-sector entities in Bangladesh, and provides statutory, compliance, IT audit, internal audit, business process, and risk advisory services aligned with ISA and IFRS standards. Partners and senior staff have led engagements for banks and financial institutions including NCC Bank PLC, Prime Bank Limited, and Grameen Bank Limited, in addition to multinational and power-sector clients. As a Baker Tilly International member, ACNABIN also draws on a global network of practices, extending the reach of its banking and regulatory expertise beyond Bangladesh.

ACNABIN is a member of the Metropolitan Chamber of Commerce and Industries, the Dhaka Chamber of Commerce & Industries, and the American Chamber of Commerce in Bangladesh, and is registered with the Registrar of Joint Stock Companies and Firms.

## 2.2 CipherShield

CipherShield is an Australian cybersecurity and risk advisory firm delivering governance-led security, compliance, resilience, and technology risk solutions across Australia, APAC, and Bangladesh, with corporate offices in both Australia and Bangladesh. CipherShield's mission is to help organisations confidently embrace new technologies — including AI — while strengthening operational resilience and growing securely in an evolving digital environment.

CipherShield's capabilities span the full AI and technology risk lifecycle: strategic leadership and digital transformation advisory; governance, risk and compliance (GRC), including Bangladesh Bank regulatory compliance support, ISO 27001 and ISO/IEC 42001 (AI management systems) advisory, and third-party/vendor risk management; business resilience; and offensive and defensive cybersecurity services including 24x7 SOC, incident response, and managed detection and response. CipherShield is a PCI DSS Qualified Security Assessor (QSA) for the APAC region, holds CREST International Accreditation for penetration testing in Australasia, and is an approved supplier to the Government of Western Australia.

CipherShield's leadership and consulting team — including its Global Chief Information Security Officer, Global Chief Operating Officer, Chief Security Architect, Chief Information Officer, Chief Business Officer, and Cyber Security Manager — collectively brings decades of experience across banking technology, cybersecurity, governance, risk, compliance, and digital transformation, holding certifications including CISSP, CISM, CISA, CRISC, CERM, OSCP, ISO 27001/27701/42001 Lead Auditor/Implementer, and PCI QSA. CipherShield's client experience includes financial and corporate organisations such as NRB Bank, and its technology partnerships span Microsoft, Fortinet, Palo Alto Networks, CrowdStrike, Cisco, IBM, and CyberArk.

## 2.3 Why This Partnership

BRAC Bank's ToR asks for a single partner able to move credibly from boardroom strategy to technical control design — spanning use-case economics, model risk, cyber and data governance, target architecture, and a fundable business case. No single firm typically covers this full span with equal depth. This consortium is built specifically to close that gap:

- Local regulatory and banking credibility: ACNABIN's 40+ years of Bangladesh Bank-facing audit and governance work, and its standing with ICAB and the regulator, ground every recommendation in what is actually approvable and auditable in the Bank's operating environment.

- Specialist AI, data, and cyber depth: CipherShield contributes the technical core — AI governance frameworks, model risk lifecycle design, target-state architecture, MLOps and security patterns, and international standards alignment (ISO/IEC 42001, NIST AI RMF) — informed by delivery experience across Australia, APAC, and Bangladesh.

- Proven joint delivery: The two firms have already delivered a joint regulatory transformation engagement in the Bangladeshi banking sector (an IFRS 9 ECL model and governance uplift), giving the Bank confidence in our combined working model, escalation lines, and quality assurance before day one of this engagement.

- No parallel structures: Because both firms already work inside the Bank's broader ecosystem of auditors, regulators, and technology governance forums, we design AI governance as an extension of existing risk, audit, and technology structures — not a competing one.

# 3. Understanding of the Assignment

BRAC Bank operates one of the strongest franchises in Bangladeshi banking across Retail, SME, and Wholesale segments, within an established and actively evolving technology estate in which AI is now a strategic priority. The Bank is seeking an advisory partner — not a single deliverable, but a partner — to help it answer three connected questions: where does the Bank genuinely stand on AI readiness today; how should AI be governed responsibly and sustainably as it scales; and how should investment be sequenced to deliver measurable, defensible value.

We understand this to be deliberately an outcome-based ToR: the Bank has defined the outcomes and minimum deliverables it requires (Sections 3 and 4 of the ToR) but has intentionally left methodology, phasing, and delivery model to the Respondent. We have taken this as an invitation to propose a pragmatic, evidence-led approach shaped by what has actually worked in comparable banking environments, rather than a generic framework applied without adaptation to the Bank's context.

Three implications shape our approach throughout this proposal:

- Anchoring, not replacing: Recommendations on architecture, platforms, and governance must maximise reuse of the Bank's existing technology, data, and private-cloud investments, and must integrate with — not duplicate — existing risk, audit, and technology governance structures.

- Local and international regulatory alignment: The programme must reflect Bangladesh Bank's ICT, cloud, and emerging AI-related regulatory expectations alongside international model risk and AI governance standards, and must draw on proven implementations from comparable financial-services markets, including India.

- Early, evidenced value: The prioritised use-case portfolio and phased roadmap must surface initiatives capable of delivering early business value, not only long-horizon transformation, and every deliverable must articulate its business value contribution in terms a Board and Executive Committee can act on.

Pricing and commercial terms are addressed under the Bank's separate commercial process (ToR Section 2.3) and are accordingly excluded from this technical proposal.

# 4. Proposed Approach & Methodology

## 4.1 Guiding Principles

- Outcome-led, not template-led: every activity is traceable to Outcome A, B, or C and to a named deliverable in Section 5.

- Transparent and auditable: no proprietary black-box scoring or modelling — every framework, weighting, and assumption is documented and explainable to the Bank's risk, audit, and Board committees.

- Anchored on existing investments: architecture and platform recommendations maximise reuse of the Bank's current technology, data, and private-cloud estate.

- Single governance spine: Outcome B is designed as the connective layer that governs how Outcome A's use cases and Outcome C's roadmap actually get approved, funded, monitored, and escalated — avoiding parallel or duplicate structures.

- Continuous knowledge transfer: capability uplift is embedded throughout delivery, not held back for a final training phase.

## 4.2 Delivery Structure

We propose three integrated workstreams, aligned one-to-one with the Bank's required outcomes, run in a phased-but-overlapping sequence so that governance design (Outcome B) begins as soon as the first use cases and risk themes emerge from the diagnostic (Outcome A), rather than waiting for it to conclude. Outcome C's strategy and roadmap then consolidate the outputs of both into a single, fundable programme of work.

### Workstream A — AI Readiness and Prioritised Use-Case Portfolio

- Mobilisation and current-state diagnostic: structured stakeholder interviews and document review across business, technology, data, and risk functions; inventory of existing, planned, and federated AI initiatives already underway across the Bank.

- Maturity assessment: a scored readiness assessment across strategy and operating model, data, technology and infrastructure, talent and capability, governance and risk, and adoption and change — each dimension rated against a defined maturity scale with supporting evidence.

- External and peer benchmarking: benchmarking against banking peers regionally and in comparable markets (including India), and cross-industry leading practice, drawing on the consortium's combined delivery experience and Baker Tilly International's global network.

- Use-case scoring and prioritisation: a transparent, weighted scoring model — business value, expected outcome, feasibility, and strategic alignment — applied consistently to internal, planned, and externally sourced proven use cases, explicitly surfacing early-value candidates alongside longer-horizon initiatives.

- Readiness gap summary: capability gaps are explicitly linked forward to the Outcome C roadmap, with emphasis on maximising the Bank's existing technology, data, and infrastructure investments rather than recommending wholesale replacement.

### Workstream B — Enterprise AI Governance and Control Framework

- Current-state governance assessment: mapping of existing AI-related governance, policy coverage, and ownership of in-flight initiatives, including where they currently sit relative to existing risk, audit, and technology governance forums.

- Regulatory mapping: a structured mapping of applicable requirements — Bangladesh Bank ICT and cloud regulations, emerging AI-specific regulatory guidance, and international model risk and AI governance standards (e.g. ISO/IEC 42001, NIST AI RMF) — to concrete control obligations.

- Governance framework design: policies, standards, a model risk lifecycle (development, validation, deployment, monitoring, retirement), responsible-AI principles, and third-party/vendor AI control requirements, each mapped to an accountable owner.

- Operating model: committee structure, roles, decision rights, and escalation paths designed to extend the Bank's existing risk, audit, and technology governance rather than stand up a parallel structure, together with an executive reporting cadence.

- Controls catalogue and testing plan: controls mapped across the full AI lifecycle — discovery, design, development, deployment, monitoring — with defined testing cadence and ownership, suitable for internal and external audit reliance.

### Workstream C — Enterprise AI Strategy, Roadmap and Business Case

- Vision and strategic ambition: an executive workshop-led process to anchor the AI vision to the Bank's actual business priorities — digital channel expansion, cost-to-acquire/cost-to-serve, and customer experience — rather than a generic industry narrative.

- Target-state architecture and platform approach: a recommended architecture covering data, models, MLOps, and security, explicitly designed to maximise reuse of the Bank's existing infrastructure, including its private cloud investment.

- Capability-build plan: talent strategy (build/partner/buy), partnership and vendor strategy, training, and change management, sized to the Bank's realistic delivery capacity.

- Three-year phased roadmap: sequenced initiatives with dependencies, owners, and value-realisation milestones across short, medium, and long-term horizons, explicitly surfacing early-value initiatives and reflecting Bangladesh Bank and international regulatory considerations.

- Quantified business case: investment requirement, expected value across revenue, cost, risk, and customer experience, total cost of ownership, ROI profile, and value-realisation milestones, presented in a format suitable for Board and Executive Committee decision-making.

- Final executive readout: a single, integrated narrative across Outcomes A, B, and C, with clear articulation of how each initiative and the roadmap as a whole deliver measurable business value.

## 4.3 Indicative Timeline

Given the breadth of the three required outcomes and fourteen deliverables, we propose an indicative five-month delivery window, sequenced as set out below. This is a starting proposal for discussion — consistent with the ToR's outcome-based, non-prescriptive approach — and will be finalised jointly with the Bank at inception.

| Key Activity | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 |
| --- | --- | --- | --- | --- | --- |
| Inception, mobilisation & work plan | ● |  |  |  |  |
| Outcome A — Diagnostic, maturity assessment & use-case inventory | ● | ● |  |  |  |
| Outcome A — Benchmarking, scoring & prioritised portfolio |  | ● | ● |  |  |
| Outcome B — Governance assessment & regulatory mapping |  | ● | ● |  |  |
| Outcome B — Framework, operating model & controls catalogue |  |  | ● | ● |  |
| Outcome C — Vision, target architecture & capability plan |  |  | ● | ● |  |
| Outcome C — Roadmap, business case & executive readout |  |  |  | ● | ● |
| Capacity building & knowledge transfer |  | ● | ● | ● | ● |
| Final reports & project closeout |  |  |  |  | ● |

All deliverables will be presented to BRAC Bank's Senior Leadership and the relevant Enterprise AI oversight body for review and approval at defined stage gates throughout the engagement.

# 5. Deliverables Mapping

The table below maps our proposed approach directly to the fourteen deliverables set out in Section 4 of the ToR. Respondents were invited to propose additional or consolidated deliverables provided all required outcomes are fully met; we have retained the Bank's original structure and numbering for ease of evaluation.

| SL | Deliverable | Outcome | Our Approach |
| --- | --- | --- | --- |
| 1 | AI Readiness Diagnostic — current state, maturity scorecard, peer benchmark | A | Scored maturity assessment across six dimensions with regional and comparable-market benchmarking. |
| 2 | Portfolio and Prioritisation of Existing Use Cases | A | Consolidated inventory of existing, planned and potential use cases, scored and ranked with early-value flags. |
| 3 | Prioritisation of External, Proven Use Cases | A | Curated set of proven financial-services use cases assessed for BRAC Bank applicability and strategic fit. |
| 4 | Use Case Prioritisation Template | A | Reusable scoring, intake, and orchestration playbook, with training guide for ongoing Bank use. |
| 5 | Readiness Gap Summary | A | Capability gaps linked to Outcome C recommendations, emphasising reuse of existing assets. |
| 6 | AI Governance Framework | B | Policies, standards, model risk lifecycle, and responsible-AI principles document. |
| 7 | Control Tower Operating Model | B | Committee structure, roles, decision rights, and charters integrated with existing governance. |
| 8 | Controls Catalogue & Testing Plan | B | AI-lifecycle control matrix with testing cadence and ownership, audit-ready. |
| 9 | Executive Reporting Pack | B | Template KPIs, risk dashboard, and reporting cadence for ongoing oversight. |
| 10 | AI Strategy Document | C | Vision, strategic ambition, and guiding principles aligned to Bank priorities. |
| 11 | Target-State Architecture & Platform Blueprint | C | Data, model, MLOps and security blueprint anchored on existing private-cloud assets. |
| 12 | 3-Year Phased Roadmap | C | Sequenced initiatives with dependencies, owners, and short/mid/long-term value milestones. |
| 13 | Enterprise Business Case | C | Investment, value (revenue/cost/risk/CX), TCO, and ROI profile. |
| 14 | Final Executive Readout | C | Integrated narrative across A, B, C with recommendations and next steps. |

# 6. Team Composition & Capability

The engagement is jointly sponsored and delivered by named senior leadership from both firms, supported by workstream leads aligned to Outcomes A, B, and C, and a delivery bench of specialists. Detailed CVs for supporting team members will be provided upon shortlisting, together with confirmation of the proportion of senior management involvement, per ToR Section 5.2.

## 6.1 Engagement Sponsors

- Abdullah-Al-Mamun, FCA — Director, ACNABIN Chartered Accountants (engagement sponsor)

- ASM Nayeem, FCA, ACA, FCCA — Founding Partner, ACNABIN Chartered Accountants (quality and independence oversight)

- Ruman Sarawer — Global Chief Information Security Officer, CipherShield (engagement sponsor)

- Fouzan Shaikh — Global Chief Operating Officer, CipherShield (delivery oversight)

## 6.2 Workstream Leadership

- Outcome B — Governance, Risk & Model Risk Lead: Muhammad Aminul Hoque, FCA, IS Audit & Assurance Partner, ACNABIN, supported by Muhammad Asaduzzaman, Cyber Security Manager, CipherShield.

- Outcome C — Technology & Architecture Lead: Md. Aktaruzzaman Sarker, Chief Information Officer, CipherShield, supported by Robert Laurie, Chief Security Architect, CipherShield.

- Outcome A — Business & Strategy Lead: Md. Abu Taleb, Chief Business Officer, CipherShield, supported by senior ACNABIN audit and advisory managers with banking-sector experience.

## 6.3 Delivery Bench

The workstream leads are supported by a delivery bench drawn from both firms, covering: AI strategy and use-case economics; data architecture and MLOps; model risk and validation; cybersecurity and GRC; banking domain subject-matter expertise (Retail, SME, and Wholesale); and organisational change and capacity building. Team sizing and named CVs will be confirmed once the Bank's preferred delivery model and timeline are agreed.

## 6.4 Knowledge Transfer Approach

Consistent with our standard practice on regulatory and technology transformation engagements, we do not deliver a black-box solution. Frameworks, scoring logic, and governance artefacts are documented in a form the Bank's own teams can operate, challenge, and evolve independently. This includes structured working sessions with Bank staff throughout delivery (not only at a final training milestone), executive briefings for Senior Leadership, and full documentation handover with no vendor lock-in.

# 7. Experience & Credentials

## 7.1 ACNABIN

- 40+ years of continuous public practice in Bangladesh; member firm of Baker Tilly International.

- Licensed by ICAB and approved by Bangladesh Bank for audit and assurance services.

- Eight partners and 700+ personnel, with strong experience across multiple banking-sector audit and advisory engagements, including NCC Bank PLC, Prime Bank Limited, and Grameen Bank Limited.

- Member of the Metropolitan Chamber of Commerce and Industries, the Dhaka Chamber of Commerce & Industries, and the American Chamber of Commerce in Bangladesh.

- Access to Baker Tilly International's global network for cross-market benchmarking and comparable-market experience.

## 7.2 CipherShield

- PCI DSS Qualified Security Assessor (QSA) for the APAC region; CREST-accredited penetration testing organisation for Australasia; approved supplier to the Government of Western Australia.

- Team certifications include ISO 27001, ISO 27701, ISO/IEC 42001, ISO 22301 Lead Auditor/Implementer, PCI QSA, SWIFT CSPCA, CISSP, CISM, CISA, CERM, CRISC, OSCP, CSPA, and ISA 62443.

- Client experience across banking and finance, government, technology, transport, and healthcare, including financial institutions such as NRB Bank.

- Strategic technology partnerships with Microsoft, Fortinet, Palo Alto Networks, CrowdStrike, Cyble, Knowbe4, Cisco, IBM, and CyberArk.

- Corporate presence in both Australia and Bangladesh, combining international standards with local regulatory understanding.

## 7.3 Relevant Comparable Engagement

ACNABIN and CipherShield have already delivered a joint regulatory transformation engagement in the Bangladeshi banking sector — an IFRS 9 Expected Credit Loss (ECL) framework and risk governance uplift for a leading commercial bank — combining ACNABIN's regulatory and financial-reporting expertise with CipherShield's data governance, technology architecture, and audit-readiness capability. That engagement followed the same principles applied in this proposal: a phased, auditable methodology; elimination of black-box dependencies; and an explicit knowledge-transfer and train-the-trainer track ensuring the client retained full ownership of all models, frameworks, and documentation. References and further case detail are available on request.

# 8. Knowledge Transfer & Capacity Building

Sustainable internal capability is treated as a deliverable in its own right, not an afterthought at project close.

### Staff Training Programme

- Hands-on workshops for concerned BRAC Bank staff on use-case scoring and intake, AI governance operations, and controls testing.

- Technical sessions on model risk lifecycle management, data and MLOps fundamentals, and AI-specific control testing.

- Editable, Bank-owned documentation and playbooks for ongoing use after the engagement concludes.

### Executive Awareness Sessions

- Strategic briefings for Senior Leadership on the AI vision, roadmap, and governance operating model.

- Board- and committee-level briefings on AI-related risk, regulatory expectations, and value-realisation tracking.

Goal: build sustainable internal capacity so the Bank can independently operate, monitor, and evolve its AI governance and delivery programme after the engagement concludes.

# 9. Post-Engagement Support

We are committed to a defined support model beyond formal project closeout, structured around the following principles:

- Issue severity and turnaround: an agreed severity classification (Critical, High, Medium, Low) with defined turnaround times for post-implementation queries on governance framework interpretation or roadmap execution support.

- Flexible support channels: onsite, remote, and hybrid support options for governance operating model queries, controls testing, and regulatory interpretation.

- No vendor lock-in: BRAC Bank retains full ownership of all frameworks, scoring models, documentation, and roadmaps produced during the engagement.

Specific SLA terms and any post-engagement support scope will be agreed with the Bank as part of the separate commercial process referenced in ToR Section 2.3.

# 10. Compliance with Respondent Requirements

Below is our response to the Respondent Requirements set out in Section 5 of the ToR.

| Requirement (ToR Section 5) | Response | Comments |
| --- | --- | --- |
| Demonstrable enterprise AI strategy, governance, and roadmap experience in banking/financial services, including comparable markets (e.g. India) | Compliant | Delivered via combined ACNABIN banking-sector audit/governance experience and CipherShield's APAC delivery footprint and Baker Tilly International network. |
| Evidence of similar engagements, with references and anonymised case examples | Compliant | Joint IFRS 9 ECL regulatory transformation engagement referenced in Section 7.3; further references available on request. |
| Familiarity with relevant regulatory and risk frameworks applicable to AI in financial services, including Bangladesh | Compliant | ACNABIN's Bangladesh Bank-facing audit practice combined with CipherShield's ISO/IEC 42001, NIST AI RMF, and regional GRC expertise. |
| Named engagement team with relevant AI strategy, governance, risk, data, and architecture expertise, including senior management involvement | Compliant | Named sponsors and workstream leads set out in Section 6; full delivery-team CVs provided upon shortlisting. |
| Clear approach to knowledge transfer and uplift of Bank-side capability | Compliant | Continuous, embedded knowledge transfer approach detailed in Sections 6.4 and 8; no black-box deliverables. |
| Proposed approach and delivery plan achieving required outcomes, with indicative timeline and milestones | Compliant | Three-workstream approach and indicative five-month timeline set out in Section 4. |
| Clear articulation of how each deliverable and the roadmap deliver measurable business value | Compliant | Business value linkage embedded in the deliverables mapping (Section 5) and the Outcome C business case and executive readout. |
| Approach anchored on existing technology, data, and private-cloud investments; avoids parallel governance structures | Compliant | Explicit guiding principle (Section 4.1); Outcome B operating model is designed to extend, not duplicate, existing governance. |

# 11. Confidentiality & Conflict of Interest Declaration

ACNABIN and CipherShield declare that all information provided by BRAC Bank PLC in connection with this ToR and any subsequent engagement will be treated as strictly confidential and used solely for the purpose of this engagement. Both firms confirm that, to the best of their knowledge, there is no conflict of interest in undertaking this advisory role. A completed Supplier's Relationship Declaration Form (Annexure 2) will be submitted alongside this technical proposal, and any relationships identified will be disclosed in full and in advance of engagement commencement.

We have reviewed the Draft Agreement (Annexure 4) provided with the ToR and confirm our general acceptance of its structure; any specific comments will be raised through the Bank's designated negotiation process prior to contract execution. We acknowledge the submission process set out in Annexure 3 (Participation Manual) and will submit this technical proposal accordingly, excluding all pricing information as instructed in ToR Section 2.3.

# 12. Closing Statement

ACNABIN and CipherShield welcome the opportunity to partner with BRAC Bank PLC on this important programme. We believe our combined regulatory, banking, and AI/cyber technology expertise — already tested through joint delivery in the Bangladeshi banking sector — positions this consortium to deliver all three required outcomes to a standard the Bank can rely on for Board-level decision-making, while leaving the Bank fully equipped to own and evolve its AI programme independently.

We look forward to discussing this proposal further and to answering any questions the Bank's evaluation committee may have.