TECHNICAL PROPOSAL

For the Assignment of

AUDIT OF PARTNER ORGANIZATIONS OF PALLI KARMA-SAHAYAK FOUNDATION FOR FY 2026-2027

Submitted To

Palli Karma-Sahayak Foundation (PKSF)

Submitted By

ACNABIN, Chartered Accountants

An Independent Member Firm of Baker Tilly International

BDBL Bhaban (Level-13 & 15), 12 Kawran Bazar Commercial Area,

Dhaka-1215

| Primary Contact Abdullah-Al-Mamun, FCA Director, Audit & Consultancy ACNABIN, Chartered Accountants mamun.abdullah@acnabin-bd.com +8801915561888 |  | Secondary Contact Nusrat Maria, FCCA, ACA (ICAEW) Deputy Director, Audit & Consultancy ACNABIN, Chartered Accountants nusrat@acnabin-bd.com +8801791317795 |
| --- | --- | --- |

# Letter of Transmittal

The Deputy Managing Director

General Services Department (GSD)

Palli Karma-Sahayak Foundation (PKSF)

PKSF Bhaban-1, Plot E-4/B, Agargaon Administrative Area

Sher-e-Bangla Nagar, Dhaka-1207

16 September 2026

Technical Proposal for Appointment as External Auditor of PKSF Partner Organizations for FY 2026 - 2027

Dear Sir,

We submit our Technical Proposal for appointment as external auditor of PKSF’s Partner Organizations for FY 2026-2027 in response to PKSF’s invitation with a submission deadline of 17 September 2026. Our proposal addresses the invitation, Parts A-C of the Application Template and the Terms of Reference for Audit of Partner Organizations by PKSF-appointed External Auditors, effective from FY 2023-2024, including its prescribed reporting formats and annexures.

ACNABIN, Chartered Accountants is a Bangladesh-based chartered accountancy partnership and an independent member firm of Baker Tilly International. Our relevant audit experience, proposed personnel and supporting credentials are presented in the application schedules and supporting attachments listed in Section 17.

We confirm that our proposed engagement team possesses the professional qualifications, sector experience and field-audit capability necessary to perform the assignment across head office, branch and field levels, and to deliver all reports, statements and annexures prescribed in the ToR.

We further confirm our firm's commitment to:

- Independence and objectivity in accordance with the International Ethics Standards Board for Accountants (IESBA) Code of Ethics and applicable Bangladeshi professional regulations;

- Compliance with International Standards on Auditing (ISA) as adopted in Bangladesh, and with International Financial Reporting Standards (IFRS) as adopted in Bangladesh, in evaluating the POs' financial statements;

- Confidentiality of all information obtained during the course of the assignment, to be disclosed only as required by the ToR, applicable law, or with PKSF's authorization;

- Professional competence and due care through appropriate staffing, supervision and quality-control review at every stage of the engagement;

- Full compliance with the ToR, including its prescribed methodology, reporting cycle, reporting formats (Annexures A-L) and audit report submission requirements.

We acknowledge the remuneration stated in the invitation, inclusive of VAT: BDT 125,000 for each Large PO, BDT 86,000 for each Medium PO and BDT 57,500 for each Small PO. Our proposed work plan and team arrangements are set out in Sections 10 and 12. PO allocation, the financial period to be audited and assignment-specific reporting dates will be confirmed through PKSF’s appointment instructions.

We look forward to the opportunity to serve PKSF and its Partner Organizations and remain available for any clarification PKSF may require regarding this Technical Proposal.

Yours faithfully,

For and on behalf of ACNABIN, Chartered Accountants

Abdullah-Al-Mamun, FCA

Director, Audit & Consultancy

ACNABIN, Chartered Accountants

# Application for the Appointment of C.A. Firms for External Audit

PKSF's Partner Organizations POs
For the FY 2026-2027

PART-A (General Information)

| Sl. No. | Particulars | Details |
| --- | --- | --- |
| 1. | Name of the C.A. Firm: | ACNABIN, Chartered Accountants |
| 2. | Address of the C.A. Firm: | BDBL Bhaban (Level-13 & 15), 12 Kawran Bazar Commercial Area, Dhaka-1215, Bangladesh |
| 3. | E-mail Address of the C.A. Firm: | acnabin@bangla.net |
| 4. | Phone Number of the C.A. Firm: | (+88-02) 41020030 to 35 |
| 5. | a) Name of Contact Person: | Abdullah-Al-Mamun, FCA |
|  | b) Designation: | Director, Audit & Consultancy |
|  | c) Mobile Number: | +8801915-561888 |
|  | d) Email Address: | mamun.abdullah@acnabin-bd.com |

PART-B (Mandatory Information)

| Sl. No. | Name of Documents | Page no of attachment(s) |
| --- | --- | --- |
| a. | Trade License with expiry date | Annexure 1 - Legal Documents |
| b. | Certificate of Practice (CoP) of Firm and the Engagement Partner | Annexure 1 - Legal Documents |
| c. | Enlistment with the Financial Reporting Council (FRC) - for both Firm and Engagement Partner | Annexure 1 - Legal Documents |
| d. | Income Tax assessment Certificate | Annexure 1 - Legal Documents |
| e. | VAT Registration Certificate | Annexure 1 - Legal Documents |

PART-C (Technical Information for Evaluation)

| Sl. No. | Name of Documents | Page no of attachment(s) |
| --- | --- | --- |
| a. | Works experience of the C.A. firms | Pages 18-28 of Annexure 2 - Organizational Profile |
| b. | Number of Partners and their experience: | Technical Proposal’s Section 15.3.2 |
| c. | Specific experience of the Engagement Partner: | Annexure 3 - CV of Core Team Members |
| d. | Number of articled Students: | Pages 10-17 of Annexure 2 - Organizational Profile |
| e. | Number of Audit management staff/officers (other than partners and articled students): | Pages 06-10 of Annexure 2 - Organizational Profile |
| f. | Proposed work plan and Audit Methodology: | Technical Proposal’s Section 03, Section 04, and Section 09 |
| g. | Audit Team Composition: | Technical Proposal’s Section 10 |
| h. | Experience of conducting audit of development projects financed by development financial institutions, international development agencies, etc. for the last 3 years | Technical Proposal’s Section 14.1 |
| i. | Experience of conducting statutory audit of financial institutions and other corporate bodies for the last 3 years: | Technical Proposal’s Section 14.2 |
| j. | Experience of conducting statutory audit of NGOs/MFIs for the last 3 years: | Technical Proposal’s Section 14.3 |
| k. | Available logistic facilities of the CA firms including office spaces: | Pages 05-06 of Annexure 2 - Organizational Profile |
| l. | Up-to-date enlistment with Bangladesh Bank: | Annexure 4 - Proof of Enlistment (Serial: 03 of Enlistment Notice of Bangladesh Bank) |
| m. | Enlistment with NGO Affairs Bureau: | Annexure 4 - Proof of Enlistment (Serial: 12 of Enlistment Notice of NGO Affairs Bureau) |
| n. | Affiliation with a foreign CA firm or foreign association of CA firms | Annexure 5 - Foreign Affiliation Certificate |

Declaration:

We declare that the above-mentioned information is true to the best of our knowledge and belief. We also declare that if our firm is appointed as external auditor for the FY 2026-2027 for external audit of PKSF's Partner Organizations POs by PKSF, we shall carry out the audit work in accordance with the relevant ToR (https://pksf.org.bd/policy-documents) and other applicable Laws, Rules and Regulations.

For and on behalf of ACNABIN, Chartered Accountants

Abdullah-Al-Mamun, FCA

Director, Audit & Consultancy

ACNABIN, Chartered Accountants

# Table of Contents

Letter of Transmittal	2

Application for the Appointment of C.A. Firms for External Audit	3

Table of Contents	5

1. Executive Summary	7

1.1 Understanding of the Assignment	7

1.2 Key Objectives	7

1.3 Major Scope Areas	7

1.4 Proposed Audit Approach	7

1.5 Fieldwork Approach	7

1.6 Reporting Approach	7

1.7 Quality Assurance	8

1.8 Our Value Proposition	8

2. Understanding of the Assignment	9

2.1 Background and Context	9

2.2 Assignment Objectives	9

2.3 Scope of Work	9

2.4.1 Key Risks and Audit Considerations	10

2.4.2 Risk to procedure linkage	11

3. Detailed Technical Methodology	12

3.1 Engagement Initiation	12

3.2.1 Audit Planning and Risk Assessment	12

3.2.2 Sampling and coverage	12

3.3 Internal Control and Governance Review	13

3.4 Financial Statement Audit	14

3.5 Fund Flow and Fund Management Review	14

3.6 Loan Portfolio Audit	15

3.7 Savings and Member Fund Review	15

3.8.1 IT / Software / Automation System Review	16

3.8.2 IT control testing	16

3.9 Fixed Asset Review	16

3.10 Program and Project Review	16

3.11 Procurement Review (where applicable)	17

3.12 Tax, VAT and Legal Compliance	17

3.13 Operating and Financial Performance	17

3.14 Capital fund and other accounts	18

4. Field Audit Methodology	19

4.1 Head Office Procedures	19

4.2 Branch Procedures	19

4.3 Field-Level Procedures	19

5. Audit Evidence and Documentation	20

6. Reporting Methodology	20

7. Prescribed Reporting Format	21

8. Deliverables	22

8.2 Deliverable ownership and review	22

9. Proposed Audit Work Plan and Timeline	23

9.2 Proposed Audit Timeline	24

10. Team Structure and Personnel	25

11. Responsibility (RACI) Matrix	27

12. Engagement Risk Management	28

13 Quality Assurance	29

13.1 Professional Standards and Ethics	29

14. Relevant Firm Experience	30

14.1 Experience of Conducting Audit of Development Projects Financed by DFIs & International Agencies	30

14.2 Experience of Conducting Statutory Audit of Financial Institutions & Corporate Bodies	34

14.3 Experience of Conducting Statutory Audit of NGOs/MFIs	36

14.4 Experience in Information System (IS) / IT Audit & Software Reviews	37

14.5 Relevance to the PKSF Assignment	37

15. About ACNABIN	38

15.1 Firm Overview	38

15.2 Global Affiliation and Standing	38

15.3.1 Firm Strengths and Partner Profile	38

15.3.2 Work Experience of Partners	39

15.4 Service Portfolio	39

15.5 Development-Sector and Institutional Client Experience	39

15.6 External Quality Assurance	39

15.7 Why ACNABIN for the PKSF Assignment	40

15.8 Value Addition for PKSF and Partner Organizations	41

16. Conclusion	41

17. Annexures to This Technical Proposal	42

# 1. Executive Summary

PKSF implements its poverty-reduction programs and projects primarily through a network of Partner Organizations (POs). Under PKSF's internal control framework, each active PO is subject to internal audit by PKSF's own Internal Audit Department, and additionally to an external audit by a PKSF-appointed Chartered Accountancy firm once in every two financial years. This Technical Proposal sets out ACNABIN Chartered Accountants' understanding of that external audit assignment and our proposed approach to performing it.

## 1.1 Understanding of the Assignment

We understand the assignment to be a risk-based external audit of the overall loan program and PKSF-funded programs and projects implemented by each PO, covering internal control and governance, automation/software systems, fixed asset management, program and project management, financial management, and operating and financial performance, culminating in an opinion on whether the PO's financial statements present a true and fair view in accordance with IFRS as adopted in Bangladesh, and in prescribed reports and annexures submitted to PKSF.

## 1.2 Key Objectives

- Assess the effectiveness of each PO’s internal control and governance systems;

- Assess the reliability, security and disaster-recovery readiness of each PO’s automation (software) system;

- Assess compliance with the PKSF-PO agreement, PKSF policies/guidelines, MRA rules and applicable law;

- Form an opinion on whether the PO’s financial statements exhibit a true and fair view in accordance with IFRS as adopted in Bangladesh;

- Assess the quality and transparency of fixed asset and fund-flow management;

- Safeguard the interests of PKSF, the PO and its member/participant stakeholders.

- Assess whether the financial statements of the overall loan programs and PKSF-funded programs/projects have been prepared in accordance with IFRS as adopted in Bangladesh;

- Assess compliance with all applicable laws, acts, rules and regulations of Bangladesh in relevant cases;

- Assess whether funds received from PKSF as loans or grants have been properly utilized; and

- Assess whether savings and other funds collected from members/program participants have been properly managed and kept securely.

## 1.3 Major Scope Areas

Our proposed scope covers the six substantive audit areas in the ToR: (1) Internal Control and Governance; (2) Automation System; (3) Fixed Asset Management; (4) Programs and Projects; (5) Financial Management; and (6) Operating and Financial Performance. These are supported by the reporting and annexure requirements in ToR Section 7.0.

## 1.4 Proposed Audit Approach

We propose a risk-based, evidence-driven audit methodology that combines document review, systems and control evaluation, substantive testing, analytical procedures and field-level verification, executed in accordance with International Standards on Auditing (ISA) as adopted in Bangladesh. Our approach is designed to identify - and evidence - control weaknesses, compliance gaps and financial-reporting risks specific to microfinance operations, including fictitious disbursement, hidden overdue loans, window-dressing and fund diversion.

## 1.5 Fieldwork Approach

Fieldwork will be structured across three levels - head office, branch office and field/member level - to obtain sufficient and appropriate audit evidence on fund utilization, loan and savings integrity, and program implementation, consistent with the ToR's requirement that the auditor work at head office, branch offices and field level of the PO.

## 1.6 Reporting Approach

We will follow the ToR's prescribed reporting cycle - fieldwork, exit meeting, draft Audit Report and Audited Financial Statements, PKSF audit discussion, finalization, and submission of the final Audit Report and Management Report - and will deliver all prescribed statements and annexures (Annexures A through L) in the number of copies specified in the ToR.

## 1.7 Quality Assurance

Every stage of the engagement will be subject to multi-level review - engagement team, Engagement Director/team lead, and engagement partner - supported by standardized working papers, cross-referencing to source documents, and a final partner-level review before draft and final reports are issued.

## 1.8 Our Value Proposition

- Relevant sector credentials and engagement experience presented in the supporting schedules required by the Application Template;

- A risk-based methodology calibrated to the specific risks of loan disbursement, savings mobilization and program fund flow highlighted in the ToR;

- Head-office, branch and field-level audit procedures supported by the proposed team deployment plan;

- A disciplined reporting process fully aligned to the ToR's prescribed formats and submission cycle;

- A firm-wide quality-control framework consistent with our status as an independent member firm of Baker Tilly International.

# 2. Understanding of the Assignment

## 2.1 Background and Context

PKSF is an apex development organization established by the Government of Bangladesh in May 1990 for sustainable poverty reduction through employment generation, and is registered as a company not for profit under the Companies Act. PKSF implements its programs and projects at field level mainly through a network of Partner Organizations (POs), which are predominantly NGOs and other non-profit organizations.

PKSF's Internal Audit Department audits POs that receive PKSF funds (as loans for credit operations or as reimbursement of program/project expenditure) at least once in each financial year. In addition, each active PO is required to be audited by a PKSF-appointed external auditor once every two financial years, with PKSF's Internal Audit Department playing a coordinating and supportive role. We further note the ToR's explicit rationale for updating the audit approach: as PO operations are increasingly managed through automated software systems, the nature and areas of audit have changed, making a risk-based audit - rather than a purely transaction-by-transaction audit - the most effective approach.

## 2.2 Assignment Objectives

Based on the ToR, the assignment's objectives are to provide assurance, to PKSF and to the PO's own governance body, on the following:

- The effectiveness and efficiency of the PO's internal control and overall governance system;

- The reliability, functionality, efficiency, security, backup and Disaster Recovery Plan (DRP) of the PO's automation system;

- Compliance with the PKSF-PO agreement and with PKSF's policies and guidelines;

- Whether the PO's accounting records and financial statements present a true and fair view of its operating and financial performance;

- The quality and transparency of the PO's fixed asset and fund-flow management;

- Whether the PO's financial statements of overall loan programs and PKSF-funded programs/projects are prepared in accordance with IFRS as adopted in Bangladesh;

- Compliance with all applicable laws, acts, rules and regulations of Bangladesh;

- Proper utilization of funds received by the PO from PKSF as loans or grants;

- Proper and secure management of member (program-participant) savings and other collected funds;

- Protection of the interests of all stakeholders.

## 2.3 Scope of Work

Consistent with the ToR's structure, we present the scope in the following workstreams, addressed in Section 03 (Detailed Technical Methodology):

| Workstream | ToR Reference | Illustrative Coverage |
| --- | --- | --- |
| Internal Control & Governance | Section 1.0 | Constitution/registration, policies, staff management, committees, MRA & PKSF compliance, legal issues, budgetary control, internal audit |
| Automation System (Software) | Section 2.0 | System automation and web-basis, HO/branch report consolidation, configuration vs. MRA/PKSF directions, manipulation risk, system-vs-manual reconciliation |
| Fixed Asset Management | Section 3.0 | Physical verification, revaluation/IFRS compliance, fixed asset ratio, procurement-to-asset trail, depreciation |
| Programs & Projects | Section 4.0 | Books/registers per program, fund transfer discipline, PO's own contribution, utilization vs. agreement, field implementation and outcomes |
| Financial Management | Section 5.0 | Accounting systems, fund management (bank, investment, member savings, borrowing, welfare/risk fund, inter-entity transactions), financial transactions, capital fund, loan portfolio at field, other accounts |
| Operating & Financial Performance | Section 6.0 | Field monitoring system, portfolio quality analysis, budget variance analysis, ratio analysis against PKSF standards |
| Reporting | Section 7.0 | Independent Auditor's Report, audited financial statements, notes, receipts & payments account, performance analysis, portfolio report, fixed asset schedule, observations (Annexure K) and compliance issues (Annexure L) |

For the financial statement audit specifically, our work will distinguish between: (i) the overall loan/credit program of the PO; (ii) PKSF-funded programs and projects; and (iii) any other PO activities that interact with the credit program (e.g., general fund, private enterprise, resort/hospital/school operations), consistent with the ToR's requirement to examine transactions between the PO's micro-finance program and such other entities.

## 2.4.1 Key Risks and Audit Considerations

Drawing directly from the risk indicators embedded throughout the ToR, we have identified the following principal risk areas that will receive heightened audit attention:

| Risk Area | Indicators per the ToR |
| --- | --- |
| Misstatement / window-dressing | Fabrication or window dressing in loan classification to minimize LLP; excess of income over expenditure achieved by forwarding expenditure, capitalizing revenue expenditure, or showing fake cash-in-hand. |
| Fictitious / hidden loans | Fake or fictitious loan disbursement at field level; hidden overdue loans; syndication of loans at samity level. |
| Fund diversion | Use or draining of bank balances to the general fund or other projects; transfer of program/project funds beyond their intended purpose; unauthorized transfers from capital fund. |
| Weak internal controls | Signed blank cheques; absence of segregation of duties in cash/bank handling; weak committee oversight or governance non-compliance with MRA rules. |
| System manipulation | Software options enabling hiding/manipulation of overdue loans, automatic rescheduling of overdue loans, continuous-interest charging on overdue loans, or fake disbursement. |
| Inadequate provisioning | Loan Loss Provision (LLP) not computed in accordance with MRA guidelines; under-provision or over-provision relative to required rates by classification band. |
| Non-compliance | Non-compliance with MRA directions, PKSF guidelines, Income Tax and VAT law, Money Laundering Prevention Act, Trust Act, and Labour Law. |
| Unsupported transactions | Advances, welfare-fund adjustments or asset purchases lacking documentation, approval or field verification. |
| Weak field monitoring | Loan/savings collections not deposited by field staff in due course; inadequate monitoring and supervision of program/project implementation. |
| Program fund misuse | PKSF-funded program/project expenditure charged to, or recorded in, the credit program, or vice versa. |

## 2.4.2 Risk to procedure linkage

| Risk | Control to evaluate | Planned test and output |
| --- | --- | --- |
| Fictitious or concealed loans | Independent approval, locked aging and reconciliations | Verify borrowers; re-age loans from due dates; test overrides and receipts. Report financial effect in I and K/L. |
| Fund diversion or missing collections | Designated accounts, reconciliations and segregation | Trace PKSF-to-member flow and collections to deposits; inspect inter-fund transfers. Report in F/G and K/L. |
| System manipulation | Restricted access, change approval and audit logs | Test privileged activity, backdated changes and differing reports; reconcile independent records. Report in K(c). |
| Window-dressing or weak provisioning | Period-end review and reliable classifications | Test journals, deferred costs, cash and LLP calculations; evaluate misstatements and opinion. Report in A-F/I and K/L. |

# 3. Detailed Technical Methodology

This section explains how our team will perform the assignment - not merely what the ToR requires. For each major area, we set out the audit procedure, the evidence it is designed to produce, and the output it feeds into the ToR's prescribed reports.

## 3.1 Engagement Initiation

Conduct a kick-off meeting with PKSF's Internal Audit Department and the PO's management to confirm scope, logistics, data-access arrangements and audit timetable for the specific PO;

Obtain and review the PO's constitution, MoA/AoA, MRA and other registration certificates, prior statutory and PKSF-appointed external audit reports, PKSF Internal Audit reports, and management's action plans on prior observations;

Obtain the PO's approved policies (HR, savings-credit, risk mitigation fund, cost allocation, gender, procurement, staff loan/advance, investment/fund management, DAFA, integrity policy), PKSF-PO agreements, trial balance/general ledger, and loan/savings sub-ledgers;

Obtain program/project agreements, budgets and donor/PKSF reporting requirements for each PKSF-funded program or project implemented by the PO.

Before accepting each PO allocation, check existing audit and non-audit services, financial/business relationships, family relationships and prior involvement in preparing the records. Obtain individual independence and confidentiality declarations, document threats and safeguards, and refer any unresolved conflict to the Engagement Partner before accepting or deploying the team.

## 3.2.1 Audit Planning and Risk Assessment

Perform a preliminary risk assessment covering the PO's control environment, governance structure, automation system, and prior audit history;

- Determine materiality for the financial statements as a whole and, where relevant, for particular classes of transactions (e.g., loan portfolio, member savings);

- Identify significant risks, including those in Section 2.4, and design the audit strategy and sampling plan for each PO. The plan will record the population, selection method, sample size, coverage by number and value, and the rationale for control reliance. The Engagement Partner will approve the plan before fieldwork; Section 3.2.2 sets out the proposed selection framework.

- Prepare a fieldwork plan covering head office, branch offices and field/member-level procedures, and an audit timetable aligned to the reporting cycle in Section 7 and work plan in Section 10.

## 3.2.2 Sampling and coverage

Obtain complete branch, member, loan, savings, transaction, asset and project populations and reconcile their control totals to the financial records before selection. Select all material and specifically identified high-risk items for targeted testing, supplemented by representative random or systematic samples from the remaining population. Targeted selections will not be treated as statistically representative of the whole population.

| Population | Proposed selection and procedures |
| --- | --- |
| Branches | Rank by portfolio, overdue/PAR, growth, cash activity, prior findings and geography. Include material/high-risk branches and a representative selection of others; record number and portfolio coverage. |
| Loans and members | Cover all loan components, new and repeat borrowers, overdue bands, rescheduled and written-off accounts, large/ME loans and unusual period-end activity. Add random/systematic selection from the residual population. |
| Savings and risk funds | Cover compulsory, voluntary, term and dormant accounts; interest, withdrawals, refunds and death/damage claims. Confirm balances and transactions directly with members. |
| Cash and transactions | Cover head office and selected branches, different months, year-end cut-off, large/unusual journals and collection-to-deposit timing; include unannounced verification. |
| Assets and procurement | Test material acquisitions, disposals and revaluations and selected residual items; verify physical existence, ownership, permissions and procurement evidence. |
| Programs and payroll | Cover each PKSF-funded program/project and significant expenditure category; select beneficiaries, grants, procurement and payroll allocations, including unusual or duplicate payments. |

Record misstatements and control deviations, investigate their cause, consider projection where appropriate to the sampling method, and expand testing when exceptions or unreliable data undermine the planned assurance. Record branches and members visited and coverage achieved; explain residual limitations in the audit file and reports where relevant.

## 3.3 Internal Control and Governance Review

We will assess each of the ToR's Section 1.0 areas through a combination of document inspection, re-performance, and enquiry:

| Area | Procedure |
| --- | --- |
| Constitution & registration | Inspect approved constitution, MoA/AoA and current MRA/NGO Affairs Bureau/Social Welfare/RJSC certificates; confirm consistent use of the PO's registered name across official documents. |
| PO's own policies & practices | Confirm General Body approval of key policies; assess alignment with MRA rules and PKSF guidelines; test a sample of transactions/decisions against the approved policy to confirm actual practice. |
| Staff management | Test recruitment, promotion, increment and settlement decisions against approved HR policy; inspect personal files for ACR, academic certificates and nominee forms; recompute a sample of salary/allowance payments and statutory deductions; verify banking-channel payment; test PF/Gratuity trustee-meeting minutes and reconcile PF/Gratuity ledgers to trust deed terms; test staff loans/advances for approval, documentation, discriminatory patterns and repayment. adjustment. Also test ghost employees and duplicate salary charges across branches/programs; review training arrangements, benefit-fund recognition, separate books/financial statements and annual audits, fund-specific investment title, prohibited liens/diversions or gratuity loans, accrued returns and allocation to staff, gratuity adequacy, forfeited/unclaimed PF treatment and advances remaining after final settlement. |
| Committees & effectiveness | Assess committee composition, tenure and gender representation against MRA rules; inspect General Body/Executive Committee minutes for regularity and follow-through; confirm external auditor appointment at AGM and General Body approval of the statutory audit report. |
| MRA compliance | Test service charge, savings interest, loan classification, LLP/LLE, statutory investment, write-off and rebate practices against current MRA rules and circulars; recompute LLP and write-off recovery accounting. |
| PKSF compliance | Test loan policy (component-wise), FDR policy, mother-bank-account operation, grant/donation policy and asset-revaluation policy against PKSF guidelines; assess project-implementation practice against project guidelines. |
| Legal issues | Test compliance with the Income Tax Act 2023, VAT and Supplementary Duty Act/Rules, Companies Act 1994, Societies Registration Act/Amendment, Public Procurement Act/Rules (where applicable), and Money Laundering Prevention Act 2012; verify TDS/VAT deduction, deposit (challan) and return-filing; test for income/expenditure netting used to reduce tax liability. |
| Budgetary control | Confirm General Body approval of the annual budget; perform budget-vs-achievement variance analysis (see Section 3.13) and assess corrective action taken. |
| Internal audit system | Confirm existence, staffing and reporting line (to the ED) of the PO's internal audit function; inspect the PO's audit ToR, report/compliance formats and audit plan; test coverage of head office, branch and field levels; assess follow-through on prior internal-audit observations; confirm annual statutory audit by a PO-appointed CA firm. Check that significant internal-audit findings are presented to the Board and assess the effectiveness of the early warning system and management’s corrective action. |
| Other governance issues | Enquire and corroborate, through document review and field enquiry, whether there is evidence of gender harassment, child labour, environmental non-compliance, nepotism or terrorism-financing risk in the PO's practices. Review operational and financial risk policies and evidence of racial disparity, and assess whether stakeholder safeguards work in practice. |

## 3.4 Financial Statement Audit

We will audit the PO's Statement of Financial Position, Statement of Profit or Loss and Other Comprehensive Income, Statement of Cash Flows, Statement of Changes in Capital Fund, and Notes to the Financial Statements (Annexures A-F formats) in accordance with ISA as adopted in Bangladesh. Procedures include:

- Reconciling each financial statement line to the general ledger, trial balance and supporting sub-ledgers/registers;

- Vouching a risk-based sample of transactions to source documents (vouchers, bank statements, cash book, contracts) and confirming appropriate authorization;

- Testing bank reconciliations for the mother bank account and operating bank accounts, and confirming that transactions are executed only through assigned bank accounts;

- Evaluating the PO's accounting policies for consistency with IAS/IFRS as adopted in Bangladesh, including recognition of interest income, service charge income, interest expense and fixed-asset depreciation;

- Reviewing the carry-forward of cumulative surplus/deficit and any prior-year adjustments, and corroborating the reasons for such adjustments;

- Testing period-end cut-off, accruals (interest payable/receivable) and provisioning (LLP, gratuity) for completeness and accuracy;

- Performing analytical procedures (trend and ratio analysis - see Section 3.13) to corroborate the overall reasonableness of reported results.

- Evaluate opening balances and comparatives, management override through unusual/manual journals and period-end entries, related-party transactions, estimates, litigation/contingencies, subsequent events and going concern. Obtain written management representations and evaluate corrected and uncorrected misstatements before forming the opinion. Management remains responsible for preparing and approving the financial statements and maintaining internal control.

- Test the chart of accounts, approval of vouchers, accrual accounting, month/year-end carry-forwards and MIS-to-AIS consistency. Verify the PO’s retention of accounting records against the ToR requirement of at least ten years at head office and five years at branch offices, together with applicable updated requirements.

## 3.5 Fund Flow and Fund Management Review

We will explicitly trace the fund-flow chain from PKSF to the PO, and from the PO to the branch, program and member/participant level, verifying:

- Receipt of PKSF (and non-PKSF) loan/grant funds into the mother bank account, and timely transfer to operating or designated accounts as per the PKSF-PO agreement;

- That funds have been used for their intended purpose and have not been transferred to the general fund or diverted to other projects;

- Appropriate accounting for the PO's own contribution to programs/projects;

- Disbursement of loans to members and recovery, cross-checked among the disbursement register, bank account, cash book, general ledger, member passbook and collection sheet;

- Reimbursement claims to PKSF for program/project expenditure, cross-checked to supporting expenditure records;

- Repayment of PKSF fund installments as per the repayment schedule, and accrual of interest/service-charge expense on borrowed funds;

- Investment of statutory reserve and savings-fund balances in FDR at scheduled banks, within PKSF's single-bank concentration limits, and free of lien.

- Inspect cash and cheque-book security, vault and cheque registers, authorized signatories, signed blank cheques, daily cash limits and idle bank balances. Perform cash counts and cut-off testing, investigate cash shortages and teeming-and-lading indicators, and reconcile cheque records to bank statements and cash books.

- For each borrowing source, inspect agreements, Executive Committee approval, interest rates, tenor, fees, security/lien conditions, use and repayment. Confirm bank/loan/FDR balances directly under auditor control; test accrued investment income, fund-specific title to investments and restrictions. Examine inter-PO/inter-unit loans and transfers involving the general fund, enterprises, land-development activities, resorts, hospitals, schools and training centers.

## 3.6 Loan Portfolio Audit

- Reconcile the loan portfolio (disbursement, recovery, outstanding balance) between the software/MIS, general ledger and physical registers;

- Test a risk-based sample of loan files for complete documentation - proposal, agreement, non-judicial stamp, NID, photograph, A/C-payee cheque, guarantor acceptance, samity resolution, member passbook and, for enterprise loans, trade/drug licence;

- Test loan classification (Good/Watchful/Substandard/Doubtful/Bad) against the MRA overdue-day bands and recompute required LLP by classification;

- Test for indicators of fictitious disbursement, hidden overdue loans, undue rescheduling, and syndication of loans at samity level, using both document review and field/member verification (see Section 4);

- Test write-off transactions against MRA rules and the PO's write-off/write-off-recovery registers, and confirm recovered write-off amounts are properly accounted for;

- Assess the concentration of micro-enterprise (ME) loans against the MRA-prescribed limit on total outstanding loans;

- Corroborate selected disbursements, recoveries and balances through auditor-controlled borrower confirmations and physical field verification. Telephone follow-up will supplement fieldwork where appropriate. Record non-responses and exceptions, perform alternative procedures and escalate unresolved access or evidence limitations to the Engagement Partner and PKSF.

## 3.7 Savings and Member Fund Review

Confirm the PO has met MRA's eligibility conditions and, where applicable, MRA approval, for collecting voluntary and term savings;

- Test interest computation and posting to member passbooks, including on interim withdrawal, and reconcile the savings ledger to the general ledger and collection sheets;

- Test the ratio of voluntary and term deposits against the capital fund for compliance with MRA limits;

- Verify that no unauthorized transfer/merger of savings fund balances into other funds (capital fund, general fund, project fund) has occurred;

- Test dormant-account identification and treatment for inactive member savings;

- For the Member Welfare/Risk Fund, test risk-premium collection, adjustment of uncollectible principal against documented death/damage claims (approval application, samity resolution, death certificate, and, where feasible, client visit), and confirm no unauthorized use of the fund for fixed-asset purchase or overdue-loan adjustment.

## 3.8.1 IT / Software / Automation System Review

- Confirm the PO's software is fully automated and web-based, and that branch and head-office monthly reports can be generated/consolidated without manual adjustment or posting;

- Test system configuration for service charge, rebate, member-savings interest, grace period, loan-processing fee, insurance fee, loan classification, LLP, depreciation/amortization, reserve-fund/investment and write-off logic against MRA and PKSF directions;

- Test for the presence of, or transactions consistent with, continuous-interest charging on overdue loans, options for hiding/manipulating overdue status, automatic rescheduling, or fake disbursement;

- Reconcile system-generated reports against manual registers, books of account, collection sheets and passbooks for a sample of branches, and investigate any mismatch;

- Assess whether financial defalcation, fund drain or cash shortages identified through other procedures are appropriately reflected in system reports, or concealed from them;

- Inspect backup logs, off-site backup arrangements and evidence of restoration and DRP/BCP exercises. Observe a controlled restoration demonstration where practicable, assess recovery responsibilities and recovery objectives, and report deficiencies in recovery capability.

## 3.8.2 IT control testing

- Review the software policy, user manual, IT staffing and responsibilities at head office and branches. Inspect joiner/mover/leaver access, privileged and vendor accounts, password sharing and authentication, segregation of data entry/approval/correction, and periodic access reviews. Test a sample of access grants and removals to approval and employment records.

- Inspect audit logs, locked periods, backdated postings, deleted/reversed records, master-data changes and manual overrides. Trace selected changes to authorization and subsequent reporting; compare reports generated for different recipients for inconsistent underlying data. Review change requests, testing and release approval and assess whether entry-level staff can manipulate inputs or conceal overdue loans.

- Inspect data-centre and backup security, incident handling and relevant cyber/data-security compliance. Review the software vendor agreement, compliance with its terms, access to and ownership of data, export/recovery rights, support obligations and continuity safeguards in a vendor dispute. Examine whether the PO performs IT audits and follows up findings. Use read-only access and controlled tests that protect production data.

## 3.9 Fixed Asset Review

- Physically verify a sample of fixed assets for existence, location, identification/tagging and active use, cross-checked to the fixed asset register;

- Test acquisitions for competitive procurement, payment to the actual supplier through banking channels, and correct accounting classification and account head;

- Assess revaluation and financial-reporting depreciation against the applicable IAS/IFRS requirements. Separately test compliance with the depreciation/amortization directions referenced in the ToR and applicable MRA guidance, including its reference to the Third Schedule of the Income Tax Act 2023. Identify differences between regulatory/tax calculations and financial-reporting amounts and evaluate the necessary accounting, disclosures and audit-report implications.

- Test the fixed-asset-to-capital-fund ratio against the MRA-prescribed limit and evaluate whether assets were acquired for the PO's own use;

- Test disposals for authorization, and reconciliation of the fixed asset schedule (Annexure J format) opening balance, additions, disposals/write-offs and closing balance, cost and accumulated depreciation.

- Inspect Executive Committee approval for significant purchase, sale and revaluation, and the MRA permission and PKSF no-objection clearance required by the ToR for significant purchases/sales. Verify legal ownership in the PO’s name, register completeness, management’s physical-verification results and follow-up of differences. Trace selected assets from register to location and from location to register.

## 3.10 Program and Project Review

- Confirm separate books of accounts and registers are maintained for each PKSF-funded program/project and for the PO's own credit program;

- Test fund transfers from the mother bank account to program/project accounts and confirm no unauthorized inter-program transfer has occurred;

- Test recognition of the PO's own contribution to programs/projects in the books of account;

- Assess utilization of program/project funds against the PKSF-PO agreement and applicable project guidelines, and test a sample of program/project expenditure for supporting documentation;

- Assess the field implementation, monitoring and supervision of program/project activities, and compare achieved outcomes against stated program/project objectives;

- Confirm program/project income and expenditure has not been improperly transferred to, or charged against, the credit program, or vice versa.

## 3.11 Procurement Review (where applicable)

- Where public procurement legislation applies, test compliance with the Public Procurement Act and Rules effective for the relevant procurement, including applicable amendments and transitional provisions. Establish applicability from the PO’s legal status, funding agreement and procurement date before testing methods, approvals and documentation.

- For non-PPA procurement, test compliance with the PO's own approved procurement policy, including competitive quotation/tender, vendor selection, purchase order, goods/services receipt, and payment authorization;

- Evaluate for conflict-of-interest indicators in vendor selection and payment, and confirm supporting documentation (quotations, comparative statements, purchase orders, receiving reports, invoices) is complete.

## 3.12 Tax, VAT and Legal Compliance

- Test deduction and deposit of income tax (TDS) and VAT at source on procurement of goods/services/works at NBR-prescribed rates, and preservation of treasury challans;

- Confirm timely filing of the PO's income tax return, VAT return and withholding tax return, and test the advance income tax register against the amounts adjusted in the return;

- Assess compliance with the Money Laundering Prevention Act 2012 and related circulars, and with the Trust Act (for Provident Fund/Gratuity Fund trust deeds) and applicable Labour Law provisions;

- Where relevant, assess compliance with the Companies Act, the applicable societies-registration legislation and MRA rules and circulars, cross-referenced to Section 3.3. Record the applicable version and effective date of each legal requirement.

## 3.13 Operating and Financial Performance

The table below summarizes the benchmarks printed in ToR Section 6.04. We will also complete Annexure H using its prescribed formulas and conducive workings. Differences between the narrative benchmarks and annexure definitions will be documented and referred to PKSF for written clarification; we will not describe different calculation bases as identical.

| Category | Indicator | PKSF Standard |
| --- | --- | --- |
| Liquidity & Solvency Risk | Current Ratio | Minimum 2:1 |
| Liquidity & Solvency Risk | Liquidity to Savings Ratio (FDR + cash + bank) | Minimum 10% (at least 5% as cash and bank) |
| Financial Risk & Leverage | Debt to Capital Ratio | Maximum 9:1 |
| Financial Risk & Leverage | Capital Adequacy Ratio (CAR) | Minimum 10% |
| Financial Risk & Leverage | Debt Service Coverage Ratio (DSCR) | Minimum 1.25:1 |
| Financial Risk & Leverage | Liability Concentration | Maximum 50% |
| Profitability & Productivity Risk | Return on Total Assets (ROTA) | Minimum 3% |
| Profitability & Productivity Risk | Borrower Coverage Ratio | Minimum 70% |
| MRA/PKSF Policy Compliance | Voluntary Deposit (% of capital fund) | Maximum 40% |
| MRA/PKSF Policy Compliance | Term Deposit (% of capital fund) | Maximum 50% |
| MRA/PKSF Policy Compliance | Fixed Asset Ratio (% of capital fund) | Maximum 35% |
| MRA/PKSF Policy Compliance | Investment in FDR - single bank | Maximum 35% |

We will compute PAR, OTR, credit concentration and yield on average loan portfolio, with the ToR benchmarks of maximum 10%, minimum 92%, maximum 60% and minimum 20%, respectively. We will complete current-year and prior-year performance and portfolio comparisons and the latest five-year income and expenditure analysis in Annexure H. Budget variance analysis will cover the PO’s approved budget and actual achievement across assets, capital, lending, savings, borrowing, income and expenditure, with explanations and corrective action for significant variances.

The ToR narrative and Annexure H differ for liquidity-to-savings, voluntary/term deposit denominators and the fixed-asset ratio denominator. We will retain separate workings where the bases differ and obtain PKSF’s direction before finalizing compliance conclusions. The five-year table also labels an income-to-expenditure ratio while showing the reverse column formula; this requires clarification.

## 3.14 Capital fund and other accounts

- Reconcile annual surplus/deficit to capital fund and consecutive-year balances. Test all material capital-fund adjustments, reserve transfers and donations to approval, restrictions and supporting evidence. Examine improper inclusion of savings, welfare, general or project funds, revaluation reserve treatment, transfers to CSR/disaster/other reserves, and statutory-reserve creation and supporting investment.

- Test sundry/staff advances for purpose, approval, terms, interest, settlement and actual use. Investigate old balances, loans or embezzled cash/savings transferred to unsettled staff advances, and balances remaining after staff final settlement. Verify social-welfare expenditure limits, beneficiary eligibility and delivery, processing fees and donations against policies. Test income and expenditure for support, accruals, cut-off, improper capitalization and transfers between credit, project and general funds.

# 4. Field Audit Methodology

The ToR requires the auditor to work at head office, branch offices and field level to ensure effective and efficient use of funds. Our field methodology is structured across three levels:

## 4.1 Head Office Procedures

Review of governance, policy and Executive Committee/General Body records;

Review of consolidated financial records, general ledger, trial balance and financial statements;

Review of mother bank account operation, investment (FDR) records and head-office-level bank reconciliations;

Review of the automation system at the consolidation/reporting level (Section 3.8);

Review of tax, VAT and other statutory compliance records maintained centrally.

## 4.2 Branch Procedures

Review of branch-level cash book, loan and savings registers, and collection sheets;

Test of branch cash-in-hand and cash-in-transit against recorded balances;

Inspection of a sample of loan files for documentation completeness;

Reconciliation of branch software/MIS reports against branch manual records;

Assessment of branch-level internal controls, including segregation of collection, recording and cash-custody duties.

## 4.3 Field-Level Procedures

- Select members independently from reconciled loan and savings populations and verify their identity, disbursement, outstanding principal, repayments, savings and interest directly with the member. Compare responses and passbooks with collection sheets, loan files, MIS and the ledger. Samity representatives may corroborate group records but will not substitute for verification with the selected member.

- Loan utilization verification - assessment of whether disbursed loans have been utilized for their stated purpose;

- Fictitious-borrower and hidden-overdue testing - cross-checking a sample of borrower records against physical presence/ samity attendance and repayment behavior to identify indicators of fictitious disbursement or concealed overdue status;

- Collection verification - confirming that amounts collected by field staff have been deposited to the PO in a timely manner;

- Program/project implementation verification - site or beneficiary-level confirmation that PKSF-funded program/project activities have been implemented as per the project guideline;

- Physical existence checks - for fixed assets and, where applicable, program infrastructure, located at or near field offices.

- Observe selected samity meetings and review group discipline and supervision of income-generating activities. Confirm delivery of in-kind grants and services, validate risk-fund claims with the intended beneficiary and supporting facts, and investigate loan syndication, borrowing for third parties and re-lending through Mohajon/ Dadon/ village money-lending activities.

- Include an element of unpredictability, such as cash counts or collection verification without advance notice of the selected items, where access and safety permit. The auditor controls sample selection and confirmation responses. Non-availability of a member will not result in automatic substitution with a management-selected member; document follow-up, alternative evidence and any required expansion.

- Taken together, these three levels of work are designed to produce sufficient and appropriate audit evidence to support our audit opinion and the observations reported in Annexures K and L.

# 5. Audit Evidence and Documentation

Our engagement methodology is built around a consistent evidence chain applied to every finding:

- For each observation, record the criterion, condition, evidence and quantified exception where available, cause where supported, impact, recommendation, management response and agreed action owner/target date. Distinguish verified facts from allegations or matters awaiting evidence.

- Audit working papers will document the objective, procedure performed, sample selected, evidence obtained and conclusion for each audit area, cross-referenced to the relevant ToR section and Annexure;

- Documentary evidence (vouchers, registers, agreements, bank statements, system reports) will be retained and cross-referenced to working papers;

- Physical verification (fixed assets, cash, field/member checks) will be evidenced by verification checklists countersigned by the responsible PO official where practicable;

- External confirmations (e.g., bank balance confirmation) will be used where appropriate to corroborate account balances;

- Reconciliations (system-to-manual, sub-ledger-to-general-ledger, portfolio-to-financial-statements) will be performed and retained as primary evidence for control and completeness assertions;

- Analytical procedures (ratio and trend analysis per Section 3.13) will be used both at planning (risk identification) and at completion (overall reasonableness);

- All samples will be selected on a documented, risk-based or systematic basis, with the basis of selection recorded in the working papers;

- Every exception identified will be evaluated for its individual and cumulative financial, control and compliance impact before being escalated as a reportable observation;

- Working papers will be subject to review and supervision as described in Section 13 (Quality Assurance), and retained in accordance with the firm’s document-retention policy and applicable professional standards.

# 6. Reporting Methodology

We will follow the reporting cycle prescribed in ToR Section 7.0 without deviation:

| Stage | Milestone | Description |
| --- | --- | --- |
| Stage 1 | Fieldwork Completion | Completion of head-office, branch and field-level audit procedures for the PO. |
| Stage 2 | Exit Meeting | An exit meeting is held with the PO's management to discuss observations arising from the audit and obtain management's response. |
| Stage 3 | Draft Reports | Submission to PKSF of the draft Audit Report, draft Audited Financial Statements and supporting annexures (2 copies each, per the ToR). |
| Stage 4 | Draft Management Report | Submission of the draft Management Report setting out observations, impact and recommendations (2 copies, per the ToR). |
| Stage 5 | PKSF Audit Discussion | PKSF arranges a discussion involving the external auditor, PKSF management and, where required, PO representatives. |
| Stage 6 | Incorporation of Decisions | Evidence-supported corrections from the PKSF discussion are incorporated; unresolved disagreements are evaluated and reported by the auditor. |
| Stage 7 | Final Audit Report & Financial Statements | Submission of the final Independent Auditor's Report and Audited Financial Statements (5 copies each, per the ToR) within the stipulated time. |
| Stage 8 | Final Management Report | Submission of the final Management Report (5 copies, per the ToR). |

Auditors are reportable to the Chairman of the General Body of PKSF, as specified in the ToR, and the Independent Auditor's Report will be addressed accordingly. Maintain a findings and corrections log through the exit meeting and PKSF discussion. Incorporate corrections only where supported by audit evidence and the applicable reporting framework; unresolved disagreement, non-response or scope limitations will remain transparently documented and considered in the opinion. Discussion with management does not transfer responsibility for the auditor’s judgment.

# 7. Prescribed Reporting Format

Each Audit Report package submitted to PKSF will comply with the exact annexure structure prescribed in ToR Section 7.0:

| No. | Component | Format Reference |
| --- | --- | --- |
| 1 | Independent Auditor's Report | To the Chairman of the General Body of PKSF |
| 2 | Audited Financial Statements | Annexures A-D (Statement of Financial Position, Statement of Profit or Loss and Other Comprehensive Income, Statement of Cash Flows, Statement of Changes in Capital Fund), or as near thereto |
| 3 | Background & Significant Accounting Policies | Annexure E, or as near thereto |
| 4 | Notes to the Financial Statements | Annexure F, or as near thereto |
| 5 | Receipts and Payments Account | Annexure G, or as near thereto |
| 6 | Statement of Performance Analysis | Annexure H, or as near thereto |
| 7 | Portfolio Report | Annexure I, or as near thereto |
| 8 | Fixed Asset Schedule | Annexure J, or as near thereto |
| 9 | Auditor's Comments/Observations | Annexure K, or as near thereto - covering internal control & governance, internal audit function, automation systems, fund utilization, fixed asset management, procurement systems, program/project management, financial management, and operating & financial performance |
| 10 | Compliance Issues | Annexure L, or as near thereto - covering PKSF loan/grant agreement terms, PKSF policies/guidelines, MRA rules, Income Tax law, VAT law, Money Laundering Prevention Act, Trust Act, and Labour Law |

In parallel, we will prepare a separate Management Report for each PO, setting out the observations revealed from the audit together with their impact and our recommendations, as required by ToR Section 7.0(B).

# 8. Deliverables

| Deliverable | Format | Quantity | Recipient |
| --- | --- | --- | --- |
| Draft - Independent Auditor's Report & Audited Financial Statements (Annexures A-L) | Hard copy (as prescribed) | 2 copies per PO | PKSF |
| Final - Independent Auditor's Report & Audited Financial Statements (Annexures A-L) | Hard copy (as prescribed) | 5 copies per PO | PKSF |
| Draft - Management Report | Hard copy (as prescribed) | 2 copies per PO | PKSF |
| Final - Management Report | Hard copy (as prescribed) | 5 copies per PO | PKSF |

## 8.2 Deliverable ownership and review

| Output | Planned timing | Preparation and approval |
| --- | --- | --- |
| Draft audit package and separate management report | End of Week 3, after exit meeting | Manager coordinates; specialists reconcile schedules; Partner reviews before submission. |
| Final audit package and separate management report | Week 4, after PKSF discussion within agreed deadline | Manager closes evidence-supported corrections; Partner approves opinion and release; quality review where required. |

# 9. Proposed Audit Work Plan and Timeline

9. 1 Proposed Audit Work Plan

The Engagement Director will review progress daily during fieldwork and report weekly to the Engagement Partner. Significant suspected fraud, evidence restrictions or deadline risks will be escalated immediately. Concurrent PO audits will use separately identified field teams, shared specialist support and reserved partner-review slots; no individual will be scheduled for overlapping full-time assignments. The deployment schedule will state each PO, named staff, working dates and person-days.

| SL | Activity | Description |
| --- | --- | --- |
| 1 | Mobilization | Kick-off meeting; confirm scope, PO(s), and logistics with PKSF and PO management |
| 2 | Planning & Risk Assessment | Preliminary risk assessment, materiality, audit strategy and sampling approach |
| 3 | Document Review | Review of policies, agreements, prior audit reports, financial and MIS data |
| 4 | Head Office Fieldwork | Internal control, governance, financial management, automation-system review |
| 5 | Branch & Field Verification | Branch-level testing and field/member-level verification |
| 6 | Analysis | Portfolio quality, ratio and budget-variance analysis; consolidation of findings |
| 7 | Drafting | Preparation of draft Audit Report, Audited Financial Statements and Management Report |
| 8 | Exit Meeting | Discussion of observations with PO management and receipt of management response |
| 9 | Submission of Draft Reports | Submission of draft reports and annexures to PKSF (2 copies each) |
| 10 | PKSF Audit Discussion | Joint discussion with PKSF, the auditor and PO representatives (as required) |
| 11 | Finalization | Incorporation of evidence-supported corrections; resolution and documentation of outstanding matters. |
| 12 | Final Submission | Submission of final Audit Report, Financial Statements and Management Report (5 copies each) |

## 9.2 Proposed Audit Timeline

Small POs | 4 Working Weeks

| Activity | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 |
| --- | --- | --- | --- | --- | --- | --- |
| Mobilization, records review and risk assessment | X |  |  |  | - | - |
| Head office audit and IT systems review | X | X |  |  | - | - |
| Branch visits and member verification |  | X | X |  | - | - |
| Analysis, exit meeting and draft report submission |  |  | X |  | - | - |
| PKSF audit discussion and resolution of comments |  |  |  | X | - | - |
| Final partner review and final report submission |  |  |  | X | - | - |
| Supervision and quality review | X | X | X | X | - | - |

Medium POs | 5 Working Weeks

| Activity | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 |
| --- | --- | --- | --- | --- | --- | --- |
| Mobilization, records review and risk assessment | X |  |  |  |  | - |
| Head office audit and IT systems review | X | X |  |  |  | - |
| Branch visits and member verification |  | X | X | X |  | - |
| Analysis, exit meeting and draft report submission |  |  |  | X |  | - |
| PKSF audit discussion and resolution of comments |  |  |  |  | X | - |
| Final partner review and final report submission |  |  |  |  | X | - |
| Supervision and quality review | X | X | X | X | X | - |

Large POs | 6 working weeks

| Activity | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 |
| --- | --- | --- | --- | --- | --- | --- |
| Mobilization, records review and risk assessment | X |  |  |  |  |  |
| Head office audit and IT systems review | X | X | X |  |  |  |
| Branch visits and member verification |  | X | X | X |  |  |
| Analysis, exit meeting and draft report submission |  |  |  | X | X |  |
| PKSF audit discussion and resolution of comments |  |  |  |  |  | X |
| Final partner review and final report submission |  |  |  |  |  | X |
| Supervision and quality review | X | X | X | X | X | X |

X / green shading = planned activity. Grey cells with a dash fall outside the proposed duration.

Planning basis: These are indicative timelines proposed by ACNABIN, not durations prescribed by PKSF. Each working week comprises five working days from the agreed commencement date. Activities within the same week will follow the required sequence: exit meeting, draft submission, PKSF discussion, then final reporting. Final dates depend on timely records, field access, management responses and PKSF’s discussion schedule; staffing and coverage will be aligned with each PO’s size and risk.

# 10. Team Structure and Personnel

The roles below describe the proposed delivery structure. A qualified team member may cover more than one specialist function where competence and workload permit, while preserving independent review. The final named schedule will identify the Engagement Partner, field team leader, audit staff and specialist support, their qualifications, experience, and availability.

| Position | Key Responsibilities | Relevant Expertise |
| --- | --- | --- |
| Engagement Partner | Overall engagement responsibility, acceptance and independence assessment, final sign-off of the Independent Auditor's Report | Statutory and development-sector audit leadership |
| Engagement Director / Team Lead | Day-to-day engagement management, fieldwork planning and supervision, first-level review of working papers | Microfinance/NGO audit and field-audit coordination |
| Engagement Manager | Day-to-day engagement management, fieldwork planning and supervision | Financial reporting and IFRS as adopted in Bangladesh |
| Financial & Accounting Specialist(s) | Financial statement audit, accounting-policy evaluation, IFRS compliance assessment | MRA regulatory framework and microfinance operations |
| IT / System Control Specialist | Automation-system and application-control review, system-vs-manual reconciliation testing | MIS/software control assessment for financial institutions |
| Tax Specialist | MRA, PKSF, tax, VAT, and other legal-compliance testing | Bangladesh tax, VAT and regulatory compliance |
| Field Audit Team | Branch and field-level verification, member/borrower confirmation, physical asset verification | Field-audit execution across multiple branch locations |

10.2.1 Proposed Core Team Members

| Position | Name of Personnel | Designation | Qualification | Experience |
| --- | --- | --- | --- | --- |
| Engagement Partner | Muhammad Aminul Hoque, FCA | Partner | Fellow Chartered Accountant (FCA), ICAB, BBA & MBA | 21+ |
| Engagement Director / Team Lead | Abdullah-Al-Mamun, FCA | Director | Fellow Chartered Accountant (FCA), ICAB, BBA & MBA | 20+ |
| Tax Specialist | Mohammad Mutasim Hossain FCA | Director | Fellow Chartered Accountant (FCA), ICAB, BBA & MBA | 16+ |
| IT / System Control Specialist | Hasan-Al-Monsur | Associate Director | CISA, ISMS-LA, CEH, CPISI | 15+ |
| Engagement Manager | Nusrat Maria, FCCA, ACA (ICAEW) | Deputy Director | FCCA (ACCA, UK), ACA (ICAEW) | 10+ |
| Financial & Accounting Specialist(s) | Md. Shif All Mostakin | Assistant Director | Chartered Accountancy Final Level, BBA - AIUB | 15+ |

Please see annexure 3 for detailed CV.

10.2.2 Field Audit Team

| Position | No of Personnel |  |  | Qualification | Experience |
| --- | --- | --- | --- | --- | --- |
|  | Small PO | Medium PO | Large PO |  |  |
| Audit In-Charge | 1 | 1 | 1 | Professional Level and Course Complete Audit Associate | 3+ years of experience |
| Senior Student | 2 | 2 | 3 | Certificate Level and 2 Years Complete Audit Associate | 2+ years of experience |
| IT Specialist | 1 | 1 | 1 | BSC in Computer Science and Relevant IT Certification | 2+ years of experience in IT and Cybersecurity Audit |

# 11. Responsibility (RACI) Matrix

The matrix below distinguishes management’s responsibility for records and financial statements, PKSF’s coordination role and the auditor’s independent responsibility for audit procedures, conclusions and report issuance.

| Activity | Audit Team | PKSF | PO |
| --- | --- | --- | --- |
| Provision of PO records, policies and system access | C | I | R / A |
| Field access and coordination with branches/members | C | I | A / R |
| Performance of audit procedures (HO, branch, field) | R / A | I | C |
| Attendance at Exit Meeting; management response | R | I | R / A |
| Submission of draft reports to PKSF | R / A | I | I |
| PKSF audit discussion | R | R / A | C |
| Incorporation of agreed corrections | R / A | C | C |
| Submission of final reports to PKSF | R / A | I | I |

R = Responsible, A = Accountable, C = Consulted, I = Informed.

# 12. Engagement Risk Management

| Risk | Potential Impact | Proposed Mitigation |
| --- | --- | --- |
| Incomplete or delayed access to PO records/systems | Delay to audit timetable; scope limitation | Early document request list at kick-off; escalation to PKSF Internal Audit Department where access is not provided within agreed timelines |
| Restricted field access | Reduced field-level evidence | Coordinate field-visit schedule with PO management in advance; document any access limitation and its impact on the audit opinion |
| Indicators of fraud / fictitious loans / fund diversion | Financial misstatement; reputational and compliance risk to PKSF and the PO | Heightened-risk procedures per Section 3.6/3.8; escalation of significant findings to the Engagement Partner and PKSF as appropriate |
| System manipulation / data-integrity concerns | Unreliable MIS-based evidence | Independent reconciliation of system output to manual records; corroboration through physical/field evidence |
| Delayed management responses at Exit Meeting | Delay to draft/final reporting timetable | Fix Exit Meeting date at planning stage; document responses in real time |
| Non-compliance findings requiring specialist interpretation (tax/VAT/MRA) | Risk of inconsistent compliance assessment | Review by the Compliance/Tax Specialist and Engagement Partner before inclusion in Annexure L |
| Reporting-cycle delays (multi-party discussion process) | Delay to final submission | Early scheduling of the PKSF audit discussion; pre-circulation of draft reports |

# 13 Quality Assurance

Our engagement quality-control framework applies at every stage of the assignment:

- Engagement Partner oversight: overall responsibility for engagement acceptance, resourcing, audit strategy, and final sign-off of the Independent Auditor's Report.

- Engagement Director / Team Lead review: day-to-day supervision of fieldwork, review of working papers as they are completed, and resolution of matters arising during fieldwork.

- Working paper review: every working paper is reviewed by a person other than its preparer before conclusions are relied upon.

- Financial statement review: line-by-line agreement of the draft financial statements to the underlying general ledger, trial balance and supporting schedules.

- Compliance review: a dedicated check of MRA, PKSF, tax, VAT and other legal compliance findings against the applicable current rules and circulars.

- Annexure reconciliation and cross-referencing: the Financial Statements, Notes, Receipts & Payments Account, Performance Analysis, Portfolio Report and Fixed Asset Schedule are cross-cast and cross-referenced to one another before issuance.

- Evidence sufficiency review: confirmation that every reported observation in Annexures K and L is supported by documented evidence in the working papers.

- Final Engagement Partner review: approve the audit conclusions, opinion, financial statements, annexures and management report before draft and final issue. Where an engagement quality review is required under applicable standards or firm policy, an eligible reviewer independent of the engagement team will complete that review before the auditor’s report is dated.

- Documentation and Archiving: Document significant technical consultations and resolution of review points. Before release, check scope and period, opinion wording, supporting evidence, management approval and representations, unresolved matters, annexure consistency, signatures, and copy quantities. Protect working papers through restricted access and secure transfer; control changes after completion, and retain the file under the applicable standards and firm policy.

## 13.1 Professional Standards and Ethics

- International Standards on Auditing (ISA) as adopted in Bangladesh, applied throughout planning, execution and reporting;

- International Financial Reporting Standards (IFRS) as adopted in Bangladesh, applied in evaluating the PO's financial statements;

- MRA rules, regulations and circulars applicable to microfinance institutions;

- PKSF's policies, guidelines and directions as set out in the ToR and the PKSF-PO agreement;

- Applicable Bangladeshi laws, rules, orders and circulars effective for the relevant transactions, including company and societies-registration legislation, income tax, VAT and supplementary duty, public procurement where applicable, anti-money laundering, trusts, labour and cyber/data-security requirements;

- The principles of Integrity, Objectivity, Confidentiality and Competency specified in the ToR by reference to the IIA Code, together with the IESBA Code and applicable professional ethical requirements;

- Our firm's independence, confidentiality and professional-competence policies applicable to all engagement personnel.

# 14. Relevant Firm Experience

ACNABIN, Chartered Accountants possesses extensive professional experience in conducting audit, assurance, financial management, internal control evaluation, governance, and regulatory compliance engagements across development, microfinance, financial, and corporate sectors in Bangladesh. The firm's core practice encompasses the assessment of internal control environments, operational processes, risk management mechanisms, legal and regulatory compliance, and management reporting systems.

The selected assignments detailed below demonstrate relevant capabilities aligned with the Terms of Reference (ToR) for the external audit of PKSF Partner Organizations (POs). This experience spans microfinance and MRA regulatory compliance, DFI and international donor-funded development project audits, statutory audits of financial institutions and corporate groups, and information systems (IS) and automation controls reviews

## 14.1 Experience of Conducting Audit of Development Projects Financed by DFIs & International Agencies

| Sl. | Name of Project | Implementing Partner | Location | Period | Sponsoring / Funding Agency |
| --- | --- | --- | --- | --- | --- |
| 1 | Capacity Development of Young and Mid-level icddr,b Researchers and Enhancing the Institution's Capacity to Collaborate both Nationally and Internationally on Genomics Research (2016-2020) | Icddr,b | 68, Shaheed Tajuddin Ahmed Sarani Mohakhali, Dhaka 1212, Bangladesh | 2022-23 | SIDA |
| 2 | USAID’s Research for Decision Makers (RDM) Activity & Alliance for Combating TB (ACTB), Funded by USAID | Icddr,b | 68, Shaheed Tajuddin Ahmed Sarani Mohakhali, Dhaka 1212, Bangladesh | 2023 | USAID |
| 3 | Incorporating TB services into Integrated Management of Childhood Illness (IMCI) and expanding TB preventive treatment (TPT) along with introduction of digital technology for monitoring TPT adherence in a selected district of Bangladesh | Icddr,b | 68, Shaheed Tajuddin Ahmed Sarani Mohakhali, Dhaka 1212, Bangladesh | 2022-2025 | Stop TB/UNOPS |
| 4 | Support to the Rohingya Refugee Community to Improve Sanitary Conditions in Cox’s Bazar Camps | ACTED Bangladesh | White House (4th Floor), Bypass Road (In front of Police Line), Kolatoli, Cox's Bazar-4700, Bangladesh | 01 March 2023 to 31 August 2023 | ACTED Head Quarters Paris-France |
| 5 | Strengthening Protection, Health and Resilience of Refugees and Host Communities in Cox’s Bazar, Bangladesh | ACTED Bangladesh | White House (4th Floor), Bypass Road (In front of Police Line), Kolatoli, Cox's Bazar-4700, Bangladesh | 01 May 2023 to 30 April 2024 | ACTED Head Quarters Paris-France |
| 6 | United Nations office for Disaster Risk Reduction Stakeholder Engagement Mechanism (UNDRR-SEM) | ActionAid Bangladesh | House SE(C) 5/B (Old 8), Road 136, Gulshan 1, Dhaka 1212, Bangladesh | From 28 February to 31 December 2023 | ActionAid International |
| 7 | Poverty Alleviation through Sustainable Approach and its Administrative Cost Project | ActionAid Bangladesh | House SE(C) 5/B (Old 8), Road 136, Gulshan 1, Dhaka 1212, Bangladesh | 2023, 2024, 2025 | ActionAid International, AA Denmark, AA UK, AA Australia, AA Italy |
| 8 | Strategic Partnership Agreement (SPA) II | ActionAid Bangladesh | House SE(C) 5/B (Old 8), Road 136, Gulshan 1, Dhaka 1212, Bangladesh | 2024, 2025 | ActionAid Denmark |
| 9 | Strategic Partnership Agreement (SPA) II | ActionAid Myanmar | Pyapon, Myanmar (Burma) | 2025 | ActionAid Denmark |
| 10 | ActionAid International Bangladesh Society | ActionAid Bangladesh | House SE(C) 5/B (Old 8), Road 136, Gulshan 1, Dhaka 1212, Bangladesh | January to December'2023 | Mutual Trust Bank Limited, EDOTCO Bangladesh Co. Ltd and Local Individual |
| 11 | Clean Cooking Scale Up Bangladesh | International Development Enterprises -iDE | Plot # 1/B (Level 4), Road 90, Gulshan 2, Dhaka 1212, Bangladesh | 2023-24 | DANIDA |
| 12 | InSPIRE Project | Swisscontact Bangladesh | House-19/1, Road-6, Baridhara Diplomatic Zone, Dhaka-1212 | 2023-24 | Swiss Agency for Development and Cooperation (SDC) |
| 13 | Young Power in Social Action (YPSA) for Sarathi-Improving Financial Health project | Swisscontact Bangladesh | House-19/1, Road-6, Baridhara Diplomatic Zone, Dhaka-1212 | 2022-24 | Swisscontact Head Office |
| 14 | Uttoron | Swisscontact Bangladesh | House-19/1, Road-6, Baridhara Diplomatic Zone, Dhaka-1212 | 2022 | Swisscontact Head Office |
| 15 | Defending Environmental Rights and Promoting Justice (2nd phase) | Bangladesh Environmental Lawyers Association (BELA) | House-15/A (4th Floor), Road-3, Dhanmondi, Dhaka-1205 | 2024 | SIDA |
| 16 | PRACTICE | Plan International | House 14, Road 35, Gulshan 2, Dhaka 1212, Bangladesh | 2023-24 | Plan International |
| 17 | Resilience and Adaptation Fund (RAF) for Disability Specialized Services to Refugees and Vulnerable Host Communities in Cox’s Bazar | Handicap International | House 3/A, Road 36, Gulshan-2, Dhaka-1212, Bangladesh | 01 Oct 2025 to 31 Mar 2026 | Foreign, Commonwealth & Development Office (FCDO) |
| 18 | Ensuring Essential Rehabilitation and Psychosocial Support for the Most Vulnerable in Cox’s Bazar | Handicap International | House 3/A, Road 36, Gulshan-2, Dhaka-1212, Bangladesh | 01 Sept 2025 to 31 May 2026 | Bangladesh Humanitarian Fund (BHF) |
| 19 | Strengthening the Advocacy Capacity of Indigenous Peoples and Promoting Livelihoods in Bangladesh | Indigenous Peoples Development Service | House 62, Probal Housing, Ring Road, Mohammadpur, Dhaka-1207, Bangladesh | 01 July 2025 to 31 December 2025 | MISEREOR/KZE |
| 20 | Promoting Land Rights and Access to Natural Resources of the Marginalized Poor, Landless, Women, Ethnic Peoples and Minorities, continuation | Association for Land Reform and Development | House # 6/6, Block # F, Lalmatia, Mohammadpur, Dhaka # 1207 | 2024, 2025 | Bread for the World (BftW) |
| 21 | Promoting Land Rights and Access to Natural Resources of the Marginalized Poor, Landless, Women, Ethnic Peoples and Minorities, continuation | Association for Land Reform and Development | House # 6/6, Block # F, Lalmatia, Mohammadpur, Dhaka # 1207 | 01 January 2025 to 30 June 2025 | Bread for the World (BftW) |
| 22 | HUGO BOSS Women's Cafe | Phulki | House 264, Road 4/A, Block F, Bashundhara R/A, Dhaka-1229 | 01 June 2022 to 31 May 2023 | HUGO BOSS |
| 23 | Rights of Dalit's (RiD) Project | Dalit | Kadir Vila, Holding # 1/10, Aziz Moholla, Madrasa Road, Mohammadpur, Dhaka-1207 | 01 January 2025 to 31 July 2025 | Islamic Relief Sweden |
| 24 | Amader Kotha Helpline Project | Phulki | House 264, Road 4/A, Block F, Bashundhara R/A, Dhaka-1229 | 01 January 2023 to 31 December 2023 | The Cahn Group, LLC & ELEVATE Hong Kong Holdings Limited |
| 25 | Sustainable Organization for Land Rights & Agrarian Reform | Community Development Association | House#51, Block #1, Upa-Shahar, Dinajpur-5200 | 2023, 2024, 2025 | Bread for the World (BftW) |
| 26 | Community-based Dispute Resolution Mechanisms and Improving Gender-Just Access to Justice in Bangladesh | Nagorik Uddyog | House 8/14, Block-B, Dhaka-1207, Bangladesh | 2023, 2024, 2025 | Bread for the World (BftW) |
| 27 | Bandarban Agriculture and Nutrition Initiative (BANI) | Helen Keller International | House no: 10E, Kazi House, Road No. 82, Dhaka 1212 | 2023-24, 2024-25 | U.S. Agency for International Development |
| 28 | Transforming Lives Through Nutrition (TLTN) | Helen Keller International | House no: 10E, Kazi House, Road No. 82, Dhaka 1212 | 2024-25 | Helen Keller International, USA |
| 29 | CRUS 2023 Rapid Response Emergency Funding Opportunity | Helen Keller International | House no: 10E, Kazi House, Road No. 82, Dhaka 1212 | 2024 | Red Nose Day Fund at Comic Relief Inc. (RNDF) |
| 30 | For Supporting Second Chance Education of Underprivileged Children through Sponsoring School in Rajshahi | UCEP Bangladesh | Plot # 2 & 3, Mirpur-2, Dhaka- 1216 | 2023 | NKD Group GmbH,Germany |
| 31 | Expanded Education Opportunity for Underprivileged Children in Bangladesh (EDUCIB) | UCEP Bangladesh | Plot # 2 & 3, Mirpur-2, Dhaka- 1216 | 2023 | BESTSELLER Foundation, Denmark |
| 32 | Women Involvement in National Growth and Sustainability (WINGS) Project-2023 | UCEP Bangladesh | Plot # 2 & 3, Mirpur-2, Dhaka- 1216 | 2023 | Charities Aid Foundation of America (CAF America), Citi Foundation |
| 33 | For Supporting General Education of Underprivileged Children through Sponsoring Schools | UCEP Bangladesh | Plot # 2 & 3, Mirpur-2, Dhaka- 1216 | 2023 | KiK Textilien Und Non-Food GmbH (KIK) |
| 34 | Securing Rights of Women Domestic Workers in Bangladesh (SRDW) | UCEP Bangladesh | Plot # 2 & 3, Mirpur-2, Dhaka- 1216 | 01 October 2023 to 31 March 2024 | OXFAM GB |
| 35 | Skill Development Program Under the Schneider Electric Foundation | UCEP Bangladesh | Plot # 2 & 3, Mirpur-2, Dhaka- 1216 | 01 May 2023 to 30 April 2024 | Schneider Electric Foundation |
| 36 | Caterpillar 2023/2024 Grant: Quality Education and Skills for Transaction (QUEST) | UCEP Bangladesh | Plot # 2 & 3, Mirpur-2, Dhaka- 1216 | 01 September 2023 to 30 June 2024 | Caterpillar Foundation through CAF America |
| 37 | Skills for Economic Growth and Prosperity- Phase-2 | UCEP Bangladesh | Plot # 2 & 3, Mirpur-2, Dhaka- 1216 | 01 July 2023 to 30 June 2024 | Department of Foreign Affairs and Trade (DFAT) |
| 38 | For Supporting Second Chance Education of Underprivileged Children through Sponsoring School in Rajshahi | UCEP Bangladesh | Plot # 2 & 3, Mirpur-2, Dhaka- 1216 | 01 January 2024 to 31 December 2024 | NKD Group GmbH, Germany |
| 39 | For Supporting General Education of Underprivileged Children through Sponsoring Schools | UCEP Bangladesh | Plot # 2 & 3, Mirpur-2, Dhaka- 1216 | 01 January 2024 to 31 December 2024 | KiK Textilien Und Non-Food GmbH (KIK) |
| 40 | Skill Development Program Under the Schneider Electric Foundation | UCEP Bangladesh | Plot # 2 & 3, Mirpur-2, Dhaka- 1216 | 01 May 2024 to 31 December 2024 | Schneider Electric Foundation |
| 41 | For Supporting Vocational Education of Underprivileged Children through Sponsoring Schools | UCEP Bangladesh | Plot # 2 & 3, Mirpur-2, Dhaka- 1216 | 01 January 2024 to 31 December 2024 | KiK Textilien Und Non-Food GmbH |
| 42 | Securing Rights of Women Domestic Workers in Bangladesh (SRDW) | UCEP Bangladesh | Plot # 2 & 3, Mirpur-2, Dhaka- 1216 | 01 April 2024 to 31 March 2025 | OXFAM GB |
| 43 | Gender-Responsive and Inclusive Vocational Education and Training (GRIVET) | UCEP Bangladesh | Plot # 2 & 3, Mirpur-2, Dhaka- 1216 | 01 April 2024 to 31 March 2025 | Global Affairs Canada (GAC) |
| 44 | Skills for Economic Growth and Prosperity- Phase-2 | UCEP Bangladesh | Plot # 2 & 3, Mirpur-2, Dhaka- 1216 | 01 July 2024 to 30 June 2025 | Department of Foreign Affairs and Trade (DFAT) |
| 45 | MetLife Foundation-UCEP Caregiving Youth Project In Bangladesh | UCEP Bangladesh | Plot # 2 & 3, Mirpur-2, Dhaka- 1216 | 01 April 2024 to 31 March 2025 | Charities Aid Foundation of America |
| 46 | Nature Based Adaptation towards Prosperous and Adept Lives & Livelihoods in Bangladesh (NABAPALLAB) | International Development Enterprises | Plot # 1/B (Level 4), Road 90, Gulshan 2, Dhaka 1212, Bangladesh | 01 January 2025 to 31 December 2025 | International Development Enterprises (iDE USA) |
| 47 | The NutriGrow: Cultivating Prosperity and Nutrition for Sustainable Development and Climate Resilience Project | International Development Enterprises | Plot # 1/B (Level 4), Road 90, Gulshan 2, Dhaka 1212, Bangladesh | 2024-25, 2024-26 | International Development Enterprises (iDE USA) |

## 14.2 Experience of Conducting Statutory Audit of Financial Institutions & Corporate Bodies

| Sl. | Client’s Name | Registered / Head Office Address | Audit Year(s) | Entity Type |
| --- | --- | --- | --- | --- |
| 1 | Bangladesh Bank | Head Office, Motijheel C/A, Dhaka-1000 | 2023-24 | Central Bank of Bangladesh |
| 2 | Grameen Bank | Grameen Bank Bhaban, Mirpur-2, Dhaka-1216 | 2023, 2024, 2025 | Specialized Microfinance Bank / Statutory Audit |
| 3 | Islami Bank Bangladesh PLC | Islami Bank Tower, 40 Dilkusha C/A, Dhaka-1000 | 2023 | Scheduled Islamic Commercial Bank / Statutory Audit |
| 4 | Prime Bank PLC | Sena Kalyan Bhaban, 195 Motijheel C/A, Dhaka-1000 | 2023-24 | Scheduled Commercial Bank / Statutory Audit |
| 5 | United Commercial Bank PLC (UCB) | Plot CWS-A-1, Road 34, Gulshan Avenue, Dhaka-1212 | 2023-24 | Scheduled Commercial Bank / Statutory Audit |
| 6 | Dhaka Bank PLC | Plot CWS-C-10, Bir Uttam A.K. Khandakar Road, Gulshan-1, Dhaka-1212 | 2023-24 | Scheduled Commercial Bank / Statutory Audit |
| 7 | National Credit & Commerce Bank PLC (NCCB) | NCC Bank Bhaban, 13/1-2 Toyenbee Circular Road, Motijheel C/A, Dhaka-1000 | 2024-25 | Scheduled Commercial Bank / Statutory Audit |
| 8 | Shimanto Bank PLC | Shimanto Square, Peelkhana, Dhanmondi, Dhaka-1205 | 2024-25 | Scheduled Commercial Bank / Statutory Audit |
| 9 | State Bank of India (BD Operations) | Navana Pristine Pavilion (12th Floor), 128 Gulshan Avenue, Dhaka-1212 | 2024-25 | Foreign Commercial Bank / Statutory Audit |
| 10 | LankaBangla Investments Limited | Assurance Nazir Tower (Level 8), 65/B Kemal Ataturk Avenue, Banani, Dhaka-1213 | 2023-24 | Merchant Bank / Capital Market Entity |
| 11 | Sirajganj Economic Zone Limited (SEZL) | House 351 (5th Floor), Road 27, Mohakhali DOHS, Dhaka-1206 | 2024-25 | Special Economic Zone / Statutory Audit |
| 12 | Remark HB Ltd | Khandaker Tower (11th Floor), 94 Gulshan Avenue, Dhaka-1212 | 2024-25 | FMCG & Skincare Manufacturer / Statutory Audit |
| 13 | Orange Solutions Ltd | Neptune Heights (5th Floor), Plot 2, Road 11, Block C, Section 6, Mirpur, Dhaka-1216 | 2024-25 | Information Technology & Software / Statutory Audit |
| 14 | A.K. Khan Telecom Limited | Bay’s Galleria (2nd Floor), 57 Gulshan Avenue, Gulshan-1, Dhaka-1212 | 2024-25 | Telecommunications Distribution / Statutory Audit |
| 15 | Moulvi Tea Company (Pvt.) Ltd | Gulshan Centre Point, Plot 23-26, Road 90, Gulshan-2, Dhaka-1212 | 2024-25 | Agro-Based & Tea Producer / Statutory Audit |
| 16 | Titas Gas Transmission & Distribution PLC | Titas Bhaban, 105 Kazi Nazrul Islam Avenue, Kawran Bazar C/A, Dhaka-1215 | 2024-25 | Public Listed Gas Utility / Statutory Audit |
| 17 | Hohenstein Laboratories Bangladesh Limited | 122/1 Love Road (Level 3), Tejgaon Industrial Area, Dhaka-1208 | 2024-25 | Textile Testing & Certification / Statutory Audit |
| 18 | Summit Power Limited | Summit Centre, 18 Kawran Bazar C/A, Dhaka-1215 | 2024-25 | Power Generation & Infrastructure / Premier Conglomerate |
| 19 | United Mymensingh Power Limited | United House, Madani Avenue, Vatara, Dhaka-1212 | 2024-25 | Power Generation / Statutory Audit |
| 20 | Doreen Power Generations and Systems Ltd | Walsow Tower (16th Floor), 21 Kazi Nazrul Islam Avenue, Dhaka-1000 | 2022-23 | Public Listed Power Producer / Statutory Audit |
| 21 | Electricity Generation Company of Bangladesh Limited | Unique Heights (Level 15-16), 117 Kazi Nazrul Islam Avenue, Dhaka-1217 | 2022-23 | State-Owned Power Generation Enterprise / Statutory Audit |
| 22 | Energypac Power Generation Ltd | Energy Center, 25 Tejgaon I/A, Dhaka-1208 | 2022-23 | Public Listed Power & Engineering / Statutory Audit |
| 23 | Kushiara Power Company Limited | Baitul Hossain Building (6th Floor), 27 Dilkusha C/A, Motijheel, Dhaka-1000 | 2023, 2024, 2025 | Independent Power Producer / Statutory Audit |
| 24 | Grameenphone Ltd | GPHouse, Bashundhara, Baridhara, Dhaka-1229 | 2024-25 | Telecommunications / Listed Multinational Leader |
| 25 | Robi Axiata PLC | Robi Corporate Office, 53 Gulshan South Avenue, Gulshan-1, Dhaka-1212 | 2023, 2024 | Public Listed Telecommunications Provider / Statutory Audit |
| 26 | Labaid Cancer Hospital & Super Speciality Center Ltd | 26 Green Road, Dhanmondi, Dhaka-1205 | 2023-24 | Healthcare & Specialized Hospital / Statutory Audit |
| 27 | Presidency University | Plot 11/A, Road 92, Gulshan-2, Dhaka-1212 | 2023-24 | Private University / Statutory Audit |
| 28 | Xiaomi Technologies Bangladesh Private Limited | Concord Silvy Heights (10th Floor), Plot 11A, Block CWS(A), Bir Uttam Mir Shawkat Sarak, Gulshan South Avenue, Dhaka-1212 | 2023, 2024, 2025 | Technology & Consumer Electronics / Statutory Audit |
| 29 | Haier Bangladesh Ltd | Crystal Palace (8th Floor), SE (D) 22, Road 140, Gulshan South Avenue, Dhaka-1212 | 2023, 2024, 2025 | Consumer Electronics & Home Appliances / Statutory Audit |
| 30 | Arla Foods Bangladesh Limited | TIC Building (Level 15), 213/A Bir Uttam Mir Shawkat Sarak, Tejgaon, Dhaka-1208 | 2023, 2024, 2025 | Dairy & Food Manufacturer / Statutory Audit |
| 31 | Heidelberg Materials Bangladesh PLC (formerly HeidelbergCement) | Symphony (6th Floor), Plot SE (F) 9, Road 142, Gulshan South Avenue, Dhaka-1212 | 2023-24 | Cement & Concrete Materials / Listed Multinational |
| 32 | Oracle Bangladesh Limited | Simpletree Anarkali (Level 6), Plot 89, Gulshan Avenue, Gulshan-2, Dhaka-1212 | 2023, 2024, 2025 | Multinational Cloud & Enterprise Software / Statutory Audit |

Please see Annexure 2: Organizational Profile for full list of experience.

## 14.3 Experience of Conducting Statutory Audit of NGOs/MFIs

| Sl. | Client’s Name | Registered / Operational Address | Audit Year(s) |
| --- | --- | --- | --- |
| 1 | BRAC (Core & Specialized Programs) | BRAC Centre, 75 Mohakhali, Dhaka-1212 | 2022, 2023 & 2024 |
| 2 | ActionAid Myanmar | Pyapon, Myanmar (Burma) | 2024, 2025 |
| 3 | ActionAid Bangladesh | House SE(C) 5/B (Old 8), Road 136, Gulshan 1, Dhaka 1212, Bangladesh | 2023, 2024 |
| 4 | Friedrich-Ebert-Stiftung (FES) Bangladesh | Gulshan 2, Dhaka | 2024, 2025 |
| 5 | Marie Stopes | House # 6/2, Kazi Nazrul Islam Rd, Block F, Lalmatia, Dhaka 1207 | 2024, 2025 |
| 6 | Handicap International | House 3/A, Road 36, Gulshan-2, Dhaka-1212, Bangladesh | 2025 |
| 7 | Community Development Association (CDA) | CDA Bhaban, New Town, Upashahar, Dinajpur-5200 | 2023, 2024 |
| 8 | Palli Daridro Bimochon Foundation (PDBF) | PDBF Bhaban, 5 Kawran Bazar C/A, Dhaka-1215 | 2023-24 |
| 9 | Social Development Foundation (SDF) | SDF Bhaban, 22/22 Khilji Road, Mohammadpur, Dhaka | 2024-25 |
| 10 | Credit and Development Forum (CDF) | House-13, Road-1, Block-B, Mirpur-12, Dhaka-1216 | 2024-25 |
| 11 | International Development Enterprises (iDE BD) | House-27, Road-44, Gulshan-2, Dhaka-1212 | 2024, 2025, 2026 |
| 12 | Plan International Bangladesh | House-14, Road-35, Sector-7, Uttara, Dhaka-1230 | 2024-26 |
| 13 | Helen Keller International - Bangladesh | House-10E, Road-82, Gulshan-2, Dhaka-1212 | 2025-26 |
| 14 | Social Marketing Company (SMC) | SMC Tower, 33 Banani C/A, Road-17, Dhaka-1213 | 2024-26 |
| 15 | Grameen Telecom Trust | Grameen Bank Bhaban, Mirpur-2, Dhaka-1216 | 2024-25 |
| 16 | UCEP Bangladesh | Plot-2 & 3, Mirpur-2, Dhaka-1216 | 2024-25 |
| 17 | Infolady Social Enterprise Limited (iSocial) | House-10, Road-11, Dhanmondi, Dhaka-1209 | 2023-24 |
| 18 | Association for Land Reform & Development (ALRD) | 1/11, Humayun Road, Block-B, Mohammadpur, Dhaka | 2024-25 |
| 19 | OBHIZATRIK Foundation | House-24, Road-4, Block-F, Banani, Dhaka-1213 | 2023-24 |
| 20 | Bangladesh Youth Leadership Center (BYLC) | Medona Tower (Level-12), 28 Mohakhali, Dhaka-1212 | 2023-24 |
| 21 | Dhrubotara Youth Development Foundation (DYDF) | House-10, Road-6, Block-A, Section-11, Mirpur, Dhaka | 2023-24 |
| 22 | Compassion International Bangladesh | House-33, Road-11, Block-G, Banani, Dhaka-1213 | 2023-24 |

Please see Annexure 2: Organizational Profile for full list of experience.

## 14.4 Experience in Information System (IS) / IT Audit & Software Reviews

| Sl. | Client’s Name | Registered / Head Office Address | Period | Nature of Assignment & System Scope |
| --- | --- | --- | --- | --- |
| 1 | National Credit & Commerce Bank PLC (NCC Bank) | NCC Bank Bhaban, 13/1-2 Toyenbee Circular Road, Motijheel, Dhaka | 2024-2025 | IS Audit as per Bangladesh Bank ICT Security Guideline (Core Banking, DRP, Logs) |
| 2 | MIDAS Financing PLC | MIDAS Centre (10th & 11th Floor), House-05, Road-16 (New), Dhanmondi, Dhaka | 2025-2026 | System Audit since Inception (Lending software logic, automated interest, security) |
| 3 | Walton Hi-Tech Industries PLC | Plot-1088, Block-I, Sabrina Sobhan Road, Bashundhara R/A, Dhaka-1229, | 2023-2026 | Oracle System Review (EBS-12.2.5) (Configuration controls, SOD, consolidation) |

## 14.5 Relevance to the PKSF Assignment

The experience outlined above demonstrates ACNABIN’s practical capability to address the key technical requirements and operational expectations set out in the PKSF Terms of Reference (ToR):

- Microfinance and MRA Regulatory Compliance: Experience with organizations such as the Community Development Association (CDA) and apex sector bodies enables ACNABIN to assess microfinance operations, verify compulsory and voluntary savings mobilization, independently review loan ageing against applicable MRA classification bands, and recompute Loan Loss Provisions (LLP).

- Fund Accountability and Project Implementation: Assignments with development financiers and international development partners, including UNDP, IDCOL, and Swisscontact, have strengthened ACNABIN’s capacity to trace fund flows through designated bank accounts, verify the utilization of project funds, assess counterpart contributions, and examine field-level disbursements.

- Banking and Financial Ratio Analysis: Through statutory and specialized audit assignments involving commercial banks and Grameen Bank, ACNABIN has developed relevant expertise in reviewing and recalculating key financial and prudential ratios, including Portfolio at Risk (PAR), On-Time Realization Rate (OTR), Capital Adequacy Ratio (CAR), and Debt Service Coverage Ratio (DSCR).

- Automation and IT Controls Assurance: With CISA-qualified professionals and experience in information systems audits, including assignments involving NCC Bank and MIDAS Financing, ACNABIN is equipped to assess automated microfinance MIS/ AIS environments, including audit trails, user access and privilege controls, backup and disaster recovery arrangements, and system-based loan and overdue management.

- Three-Tier Field Verification: ACNABIN’s audit approach covers Head Office, Branch Office, and Field/Samity levels, enabling reported financial and operational information to be validated through physical verification of passbooks and assets, as well as independent borrower confirmations.

This multidisciplinary experience positions ACNABIN to undertake a risk-based external audit addressing the requirements of the PKSF ToR and to deliver the prescribed reporting package, including the Independent Auditor’s Report, Audited Financial Statements (Annexures A-J), Observations (Annexure K), and Compliance Issues (Annexure L), together with actionable and risk-prioritized Management Reports for each Partner Organization.

# 15. About ACNABIN

ACNABIN, Chartered Accountants is an independent member firm of Baker Tilly International, based at BDBL Bhaban (Level-13 & 15), 12 Kawran Bazar Commercial Area, Dhaka-1215, Bangladesh. As a chartered accountancy partnership, ACNABIN provides audit, advisory, and consultancy services, including institutional, governance, financial, risk and process advisory support, to clients across Bangladesh's public, private, development and civil-society sectors.

## 15.1 Firm Overview

ACNABIN was formed in February 1985, with a mission to continually add value by helping clients succeed, and has been in public practice for more than 41 years. Founded with a vision to build an institution that fosters leadership, continuous growth, learning and collaboration, ACNABIN has developed into one of the leading and reputable chartered accountancy firms in Bangladesh with global affiliations.

The Firm has eight partners whose expertise spans audit, accounting, review, business consulting, business process outsourcing, technology solutions and taxation, supported by a multidisciplinary organization. The partners bring extensive professional experience in Bangladesh and abroad, including work with international consultants and organizations operating locally and globally.

## 15.2 Global Affiliation and Standing

- Independent member firm of Baker Tilly International since 2004 - a global network represented by independent member firms across 147 countries, with a presence across the Middle East, Latin America, Asia Pacific, the Caribbean, Africa, North America and Europe.

- Enlisted with the Bangladesh Securities and Exchange Commission and listed as an eligible CA firm for Bank Audit by Bangladesh Bank.

- Member of the Metropolitan Chamber of Commerce and Industries, The Dhaka Chamber of Commerce & Industries, and the American Chamber of Commerce in Bangladesh.

- Registered with the Registrar of Joint Stock Companies and Firms (# PF 27897/86) under Section 58(1) of the Partnership Act, 1932, dated 21 June 1986, and the partners are registered with the Institute of Chartered Accountants of Bangladesh (ICAB) for audit practice.

- As a Baker Tilly International member firm, ACNABIN operates under shared commitments to quality, integrity, ethical conduct, open communication, teamwork, collaboration and professional development.

## 15.3.1 Firm Strengths and Partner Profile

- 490 personnel, including partners, staff and articled students.

- 8 partners, with ACNABIN recognized as one of the leading chartered accountancy firms in Bangladesh over several decades.

- 1 partner is a former President of SAFA (South Asian Federation of Accountants); 2 partners are former Presidents of ICAB.

- 4 partners have chaired the Board of Studies and the International Relations Committee of ICAB.

- 3 partners bring senior corporate-sector working experience; 2 in-house lawyers support the Firm's Legal Department; and 5 CISA-qualified IT specialists support IT advisory work.

- Continuous ACNABIN representation on the ICAB Council since inception, including its Executive Committee, Investigation and Disciplinary Committee, Articled Students Committee, Quality Assurance Board, Board of Studies, Editorial Board, Professional Development Committee, and Taxation and Corporate Laws Committee.

- Partners have worked on international assignments in Afghanistan, Australia, Bhutan, China, Ethiopia, Hong Kong, India, Laos, Nepal, North Korea and Oman.

## 15.3.2 Work Experience of Partners

| Sl. | Name | Educational Qualification | Years of Experience |
| --- | --- | --- | --- |
| 1 | Abu Sayed Mohammed Nayeem | B.Com. (Hons.), M.Com., M.Sc. (UK), FCCA (UK), ACA (ICAEW), FCA | 45+ Years |
| 2 | Iftekhar Hossain | B.Com., FCA | 45+ Years |
| 3 | Abu Taher Mohammed Abdul Bari | B.Com., FCA, FCEA (London) | 45+ Years |
| 4 | Md. Moniruzzaman | B.Com. (Hons.), M.Com., FCA | 30+ Years |
| 5 | Md. Rokonuzzaman | B. Com., M.Com., FCA | 28+ Years |
| 6 | Md. Mominul Karim | B.Com. (Hons.), M.Com., FCA | 25+ Years |
| 7 | Md. Reajul Islam | B.B.M (University of Mysore, India), FCA | 22+ Years |
| 8 | Muhammad Aminul Hoque | BBA, MBA (DU), FCA | 21+ Years |

## 15.4 Service Portfolio

Audit & Assurance: Statutory, internal, special, cost, compliance, forensic, management, performance and interim audit; review engagements; NGOAB audit; and donor audit.

Tax & Legal Advice: Corporate and individual tax planning, personal income tax, indirect tax, tax investigations, assessments and appeals, return preparation, inheritance tax planning, international tax services and tax-effective remuneration planning.

Advisory Services / Consultancy: Formation, incorporation and winding up; company secretarial services; company and business valuation; management accounting; structured financing advisory; business planning and feasibility studies; Standard Operating Procedures (SOP); fixed-asset management; payroll management; process improvement; and cost management services.

IT Advisory: Information systems audit, IT general controls review, application review and pre-/post-implementation review, SSAE 16 (SOC1)/SOC2 facilitation and SOX IT controls testing, regulatory audits, ISO 27001/PCI DSS security compliance and governance services, data migration audit, and vulnerability assessment and penetration testing.

## 15.5 Development-Sector and Institutional Client Experience

Directly relevant to assignments involving development finance, NGO operations, fund accountability and field-level implementation, ACNABIN's client base includes a substantial development-partner and NGO portfolio, among them UNDP, UNICEF, UNHCR, IFAD, the World Bank, the Asian Development Bank, Save the Children, BRAC, Swisscontact, Plan International Bangladesh, icddr,b, Pathfinder, Grameen Bank, Action Aid Bangladesh, iDE Bangladesh and CARE Bangladesh.

This experience is complemented by a broad portfolio of financial-sector clients, including Bangladesh Bank, BRAC Bank, Eastern Bank, City Bank and Agrani Bank; multinational and corporate clients, including Unilever, Grameenphone and Marico; and state-owned/autonomous entities, including Biman Bangladesh Airlines and the Bangladesh Securities and Exchange Commission. The breadth of this client experience reflects ACNABIN's capacity to work across organizations with differing governance structures, regulatory requirements, control environments and operating complexity.

## 15.6 External Quality Assurance

- ACNABIN participates in Baker Tilly International's Quality Assurance Program, involving periodic and extensive quality-control reviews and due diligence in accordance with applicable BTI requirements.

- ACNABIN is subject to periodic Quality Assurance Review by the Quality Assurance Department of ICAB.

## 15.7 Why ACNABIN for the PKSF Assignment

- Multidisciplinary assurance capability: ACNABIN combines statutory and development-sector audit experience with expertise in financial reporting, microfinance operations, internal controls, tax and VAT, legal compliance, governance and information systems.

- Risk-based methodology: The Firm's proposed approach directly responds to the ToR's rationale for moving toward risk-based auditing in an increasingly automated PO environment.

- Field-audit capability: The proposed approach integrates head-office, branch and field/member-level procedures, enabling the audit team to corroborate records with operational and participant-level evidence.

- Strong reporting discipline: Audit evidence, findings and conclusions will be linked to the prescribed Independent Auditor's Report, financial statements, Annexures A-L and Management Report.

- Quality and supervision: Engagement Partner oversight, team-lead supervision, documented working papers, specialist review and final partner-level review will support consistent audit quality.

- Technology and system capability: CISA-qualified IT resources and the Firm's IT advisory practice provide relevant support for assessing automated systems, system configuration, data integrity and IT-related control risks.

## 15.8 Value Addition for PKSF and Partner Organizations

Beyond strict compliance with the ToR, ACNABIN's approach is designed to provide practical value through:

- Risk-based, not purely transactional, audit: consistent with the ToR's own stated rationale for moving away from purely thorough transaction-by-transaction audit toward a risk-based approach suited to automated PO operations.

- System-to-record reconciliation as a standing procedure: designed to surface control weaknesses that a document-only review would miss.

- Structured field verification: designed to strengthen the evidentiary basis for opinions on loan and savings integrity, beyond head-office documentation.

- Early identification of control weaknesses: findings are escalated as they are identified during fieldwork rather than held solely for end-of-engagement reporting, allowing timely management action.

- Practical, prioritized recommendations: recommendations in Annexures K and L are written to be actionable, with impact clearly stated.

- Follow-up orientation: our internal-audit-system review (Section 3.3) explicitly assesses the PO's follow-through on prior audit observations, supporting continuity across audit cycles.

- Enhanced Management Reporting: The prescribed management report will prioritize corrective actions by risk, identify repeat findings, and present a clear status of earlier recommendations. Where PKSF allocates multiple POs, we provide a concise, cross-PO summary of recurring control weaknesses and comparable performance indicators, fully protecting each PO's confidential information.

# 16. Conclusion

PKSF's Partner Organization model places significant responsibility on POs for the stewardship of loan, grant and member funds and for the implementation of programs and projects at field level. The external audit therefore needs to combine financial assurance with disciplined examination of governance, internal controls, automated systems, fund flow, portfolio integrity, savings, compliance and field implementation.

ACNABIN's proposed methodology is designed around this requirement. It retains the original ToR scope and terminology while making the detailed audit response more explicit and traceable. Through a combination of professional audit procedures, risk-based field verification, system and control assessment, analytical review and multi-level quality assurance, ACNABIN intends to provide PKSF with a robust, evidence-based and practical external audit of its Partner Organizations.

# 17. Annexures to This Technical Proposal

The following supporting annexures accompany this Technical Proposal:

- Annexure 1 - Legal Documents

- Annexure 2 - Organizational Profile

- Annexure 3 - CV of Core Team Members

- Annexure 4 - Proof of Enlistment

- Annexure 5 - Foreign Affiliation Certificate