Terms of Reference

Consultancy Services for Net Zero Target Setting and ESG Reporting Enhancement

| Concerned Department/Division | Sustainable Finance Department, Risk Management Division |
| --- | --- |
| Oversight | Tashmeem Muntazir Chowdhury, Head of ESG and Sustainable Finance |
| Duration | 4 months (starting from the contract start date) |

- Introduction

BRAC Bank PLC is seeking to engage a qualified and experienced organization to provide technical consultancy services for developing the Bank's Net Zero strategy and enhancing its Environmental, Social, and Governance (ESG) reporting framework.

The organization, to be appointed by the Bank, shall conduct an independent assessment of the Bank's current sustainability practices, greenhouse gas (GHG) emissions profile, climate-related risks and opportunities, ESG governance structure, and existing disclosures. The consultant shall support the Bank in establishing a credible Net Zero pathway, developing science aligned emissions reduction targets, strengthening ESG data management systems, and enhancing sustainability reporting in line with applicable national and international standards.

The primary objective of this consultancy is to support the Bank in aligning its sustainability strategy with evolving regulatory requirements, stakeholders’ expectations, and global best practices, while ensuring robust and transparent ESG disclosures.

- Objectives of the Consultancy

The objectives of the consultancy is to assist BRAC Bank PLC in:

- Developing a comprehensive Net Zero roadmap and emissions reduction strategy

- Establishing industry appropriate and feasible short, medium, and long term GHG reduction targets aligned with recognized international frameworks; develop a mechanism for establishing GHG related database and periodical data collection method.

- Strengthening ESG governance, policies, and data management processes.

- Enhancing ESG reporting and disclosures in accordance with relevant reporting standards and regulatory expectations.

- Building internal capacity for ongoing implementation, monitoring, and reporting of sustainability initiatives.

- Scope of Services

The scope of work of this consultancy service include two major tasks as follows:

3.1 Net Zero Strategy Development and Target Setting

The Consultant shall support BRAC Bank PLC in developing a credible Net Zero strategy and implementation roadmap aligned with international best practices.

a) Baseline Assessment and Gap Analysis

- Review existing climate strategies, emissions profile, and current practices.

- Identify gaps against relevant frameworks and industry standards.

b) GHG Inventory Assessment, baseline and database

- Review GHG accounting methodologies, emissions calculations, data quality and database

- Recommend improvements to strengthen emissions measurement and reporting.

- Establishing GHG related database and periodical data collection method

c) Net Zero Target Setting

- Develop industry specific short, medium, and long term emissions reduction targets.

- Recommend suitable target-setting methodologies and pathways.

d) Net Zero Strategy and Roadmap

- Develop a comprehensive strategy and transition roadmap (phased approach) outlining key actions, timelines, and implementation requirements.

e) Capacity Building and Awareness Raising

- Conduct training and knowledge-sharing programme on Net Zero implementation and monitoring for the concerned BRAC Bank Staff

- Conduct awareness raising sessions on the strategic priorities and the roadmap  with Senior Leadership of BRAC Bank

3.2  ESG Disclosure and Reporting Enhancement

The Consultant shall support BRAC Bank PLC in strengthening its ESG reporting framework and sustainability disclosures.

a) ESG Gap Assessment

- Review existing ESG disclosures and identify improvement areas.

b) Reporting Framework Enhancement

- Enhance reporting practices, metrics, and disclosures in line with applicable standards and best practices.

- Translate ESG related risks into financial impacts, including implications for the lending portfolio

d) Reporting Roadmap and Capacity Building

- Develop an ESG reporting improvement roadmap and conduct relevant training sessions.

- Deliverables

- Inception Report and Detailed Work Plan.

- ESG and Sustainability Gap Assessment Report.

- Net Zero Strategy and Roadmap along with GHG Inventory Review and Improvement Report; This deliverable will include Net Zero Target Setting Methodology, GHG emission baseline and recommendations.

- Enhanced ESG Reporting Framework and Disclosure Recommendations.

- Capacity building and awareness raising plan, materials and completion report.

- Documents Required from the Consultant

- Company Profile and Portfolio.

- Relevant Work Experience and References for Similar Assignments with Financial Institutions on Net Zero Strategy Development, ESG and Sustainable Finance in national and international domains

- List of Key Consultants and Detailed Credentials.

- Proposed Methodology and Work Plan.

- Sample Deliverables from Similar Engagements.

- Financial Proposal.