TECHNICAL PROPOSAL

Recertification of ISO 18788 for BRAC Bank PLC

| Submitted to | BRAC Bank PLC |
| --- | --- |
| RFP Reference | BRACBANK/Proc/RFQ/Y26/290, 2000003445 |
| Submitted by | ACNABIN Chartered Accountants (Proposed Prime Bidder) in consortium with CipherShield Bangladesh Ltd (PCI QSA Technical Partner) |
| Submission Date | Aug 17, 2026 |
| Project Code | 2026-July-ANCCB-ISO0052 |
| Classification | Commercially Confidential |

Commercial Confidentiality Disclaimer

This document is commercial, confidential and copyrighted by the submitting consortium. It may be used solely for evaluation of this proposal and may not be reproduced, distributed or disclosed without prior written approval.

Confidentiality Statement

This proposal and all information contained herein are commercially confidential and proprietary to the submitting organization. It has been prepared solely for the purpose of evaluation in response to the BRAC Bank PLC RFQ for the recertification of ISO 18788:2015 amendment up to 2024 certification.

The contents of this document, including technical approaches, methodologies, commercial information, project plans, personnel information, and supporting deliverables, shall not be reproduced, copied, distributed, disclosed, or shared with any third party without prior written authorization from the submitting organization, except where such disclosure is required for the evaluation of this proposal by BRAC Bank PLC and its authorized representatives.

By accepting this proposal, the recipient acknowledges the confidential nature of the information contained herein and agrees to use it solely for the purpose for which it has been submitted.

Technical Envelope No commercial prices or financial quotations are included in this document. The commercial response is provided separately in the Financial Proposal package.

# Letter of Submission

The Procurement Department
BRAC Bank PLC
Anik Tower (1st Floor)
220/B, Tejgaon I/A
Tejgaon-Gulshan Link Road
Dhaka-1208, Bangladesh

17 August 2026

Submission of Technical Proposal for Recertification of ISO 18788:2015 amendment up to 2024 certification - Management System for Private Security Operations (SOMS)

RFQ Reference: BRACBANK/Proc/RFQ/Y26/290, 2000003445

Dear Sir/Madam,

We are pleased to submit our Technical Proposal in response to the Request for Quotation (RFQ) issued by BRAC Bank PLC for the recertification of ISO 18788:2015, amendment up to 2024 certification - Management System for Private Security Operations (SOMS).

We confirm that we have carefully reviewed the RFQ, Scope of Work, instructions to bidders, participation requirements, terms and conditions, and related annexures provided by BRAC Bank PLC. We understand the requirements of the assignment and are committed to delivering the required services in accordance with the Bank's specified scope, timelines, quality standards, and applicable requirements.

Our proposal presents our understanding of the requirements, proposed methodology and approach, project implementation plan, deliverables, team composition, relevant experience, and supporting credentials for consideration by BRAC Bank PLC.

We further confirm that the information and documents submitted as part of this proposal are true and accurate to the best of our knowledge. We acknowledge that the proposal will be evaluated in accordance with the evaluation criteria specified in the RFQ and that BRAC Bank PLC reserves the rights stated in the RFQ, including the right to accept, reject, cancel, negotiate, or otherwise deal with the proposal in accordance with its procurement requirements.

We also confirm our commitment to comply with the applicable confidentiality, ethical, professional, and contractual requirements of BRAC Bank PLC throughout the engagement.

We appreciate the opportunity to participate in this important assignment and look forward to the opportunity to support BRAC Bank PLC in strengthening and maintaining its information security and ISO certification framework.

Yours faithfully,

Muhammad Aminul Hoque, FCA
Partner
ACNABIN, Chartered Accountants
Mobile: 01671-024714

Contents

Letter of Submission	3

1. Executive Summary	5

2. What BRAC Bank PLC Will Receive:	6

3. Proposed Bid Structure:	6

4. Understanding of BRAC Bank PLC's Requirements	8

5. Engagement Objectives & Outcomes	9

6.  About the ISO 18788:2015 amendment up to 2024 Standard:	9

7. ISO 18788 Recertification Benefits	10

8. About CipherShield	10

9. Industry Accreditations	11

10. Credentials & Capability Snapshot:	11

11. CipherShield Approach	11

12. Certification path (Stage 1 and Stage 2)	12

13. Governance, reporting, and audit evidence model	13

14. Banking-Specific Delivery Considerations:	13

15. Regulatory and Standards Alignment	14

16. High Level Project Plan	15

17. Project Deliverables	16

18. Project Assumptions	17

19. Critical Success Factors for ISO 18788 Implementation:	18

20. Project Risks	19

21. Project Team	20

22. BRAC Bank PLC Team	21

23. Previous Project Experience:	22

24. Project Management (ISO 18788 Optimized)	22

25. Bidder Eligibility & Supporting Documents Checklist	24

26 Non-Compliance Declaration:	25

27. Authorization and Acceptance:	25

## 1. Executive Summary

BRAC Bank PLC requires a qualified and experienced service provider to support the recertification of its ISO 18788:2015 amendment up to 2024 Security Operations Management System (SOMS) certification, covering the relevant security operations, policies, processes, identification of security-related assets, controls, risk management practices and organizational arrangements.

The requested engagement includes an ISO 18788:2015 amendment up to 2024 gap analysis and consultancy, certification scoping, security-asset identification and classification, risk assessment and management, SOMS implementation support, development and review of policies and procedures, manuals, forms, templates, awareness sessions, compliance monitoring, internal audit, remediation support, certification/recertification assessment coordination with the Top Registered Certification Body (RCB), and two subsequent surveillance audits with annual refresher training.

The proposed engagement model provides BRAC Bank PLC with a structured and risk-based approach covering the complete recertification lifecycle. The methodology emphasizes independent assessment, effective risk management, control effectiveness, evidence-based gap identification, remediation support and sustainable compliance. Particular focus will be placed on understanding the Bank's existing SOMS, identifying gaps against the ISO 18788:2015 amendment up to 2024 requirements, supporting corrective actions and preparing the Bank for the formal recertification assessment.

The proposed approach is designed to provide BRAC Bank PLC with practical and sustainable outcomes beyond recertification readiness, including strengthened security operations governance, clearly defined roles and responsibilities, improved risk visibility, measurable SOMS performance and continued compliance through internal audit, surveillance support and periodic awareness and refresher activities.

Through a structured delivery methodology, experienced resources and close coordination with BRAC Bank PLC stakeholders and the top registered certification bodies (such as Bureau Veritas, Intertek, or Royal CERT), the engagement will provide a comprehensive framework for achieving the Bank's recertification objectives while strengthening its overall security operations management and resilience capabilities.

Our Proposed Position A locally coordinated, ISO 18788-led recertification and compliance engagement for BRAC Bank PLC, delivered through a disciplined and structured operating model covering gap assessment, risk assessment, SOMS implementation support, internal audit, remediation guidance, recertification readiness, certification assessment coordination and ongoing surveillance support. The engagement will maintain clear separation between advisory, implementation support, internal audit and certification assessment activities, while ensuring BRAC Bank PLC retains ownership of risk decisions, remediation, control implementation and ongoing operation of the SOMS.

## 2. What BRAC Bank PLC Will Receive:

- A clearly defined and defensible SOMS scope covering the relevant organizational units, identification of security-related assets, processes, facilities, locations, interfaces, dependencies and third-party security service provider’s other areas applicable to the agreed recertification scope.

- Comprehensive identification and classification of security-related assets, including identification of asset owners, classification requirements and maintenance of appropriate asset registers, ensuring alignment with the Bank's broader enterprise risk and asset management frameworks.

- A risk-based ISO 18788:2015 amendment up to 2024 gap assessment covering the existing SOMS, security controls, policies, processes and risk management practices, and legal/regulatory compliance obligations, together with a structured and prioritized remediation roadmap.

- Comprehensive SOMS risk assessment and management support, including assessment methodology, risk treatment Human Rights Risk Assessment (HRIA), and documented risk management outputs aligned with the Bank's requirements.

- SOMS implementation and enhancement support, including organizational roles and responsibilities, security operations policies (including use of force and grievance mechanisms), incident management procedures, evaluation methods, metrics, KPIs and management dashboards.

- Internal audit and certification-readiness support, including an independent internal audit of the SOMS and its documentation, identification of findings, remediation support and closure of identified gaps prior to the formal recertification assessment.

- Recertification assessment coordination and support, including coordination with the Registered Certification Body, application support, pre-audit/document review, the certification audit and assistance toward obtaining the recertification.

- Ongoing surveillance and compliance support, including support for the two subsequent surveillance audits, surveillance certificates, periodic compliance monitoring and regulatory/update guidance as required under the engagement.

- ISO 18788 awareness and annual refresher training for relevant BRAC Bank stakeholders and critical third-party security vendors, supported by structured knowledge transfer to strengthen internal understanding and sustainable operation of the SOMS.

- Management-level reporting and documented deliverables throughout the engagement, providing BRAC Bank PLC executive leadership and the Board with clear visibility of assessment findings, remediation progress, compliance status and recertification readiness.

## 3. Proposed Bid Structure:

The proposed bid structure comprises ACNABIN Chartered Accountants as the prime bidder and CipherShield Bangladesh Ltd. as the specialist technical partner. The proposed delivery model provides BRAC Bank PLC with a local contractual and coordination interface supported by specialist capabilities in ISO management systems, information security, risk management, internal audit, certification readiness and technical compliance support.

The final submission package will include the applicable authorization, partnership/consortium documentation, company credentials, professional qualifications, relevant project references and other eligibility evidence required under the RFQ.

Delivery Responsibility

The proposed operating model will maintain appropriate separation between consultancy/advisory support, SOMS implementation guidance, internal audit and coordination with the Registered Certification Body, ensuring independence and audit defensibility throughout the engagement.

| Entity | Proposed Role | Primary Responsibilities |
| --- | --- | --- |
| ACNABIN, Chartered Accountants | Prime bidder | Overall contractual and commercial interface, coordination with BRAC Bank PLC, proposal and contractual document submission, project governance and overall engagement management. |
| CipherShield Bangladesh Ltd. | ISO & Security Operations Technical Partner | ISO 18788:2015 amendment up to 2024 gap assessment and SOMS support, security operations risk assessment, control and policy and process review, internal audit support, remediation guidance, recertification readiness, technical assessment and specialist compliance advisory certification readiness coordination and subsequent surveillance audits. |

## 4. Understanding of BRAC Bank PLC's Requirements

4.1 Background and Objective

BRAC Bank PLC seeks a qualified service provider to support the recertification of its ISO 18788:2015 amendment up to 2024 Security Operations Management System (SOMS) certification, covering assessment, SOMS enhancement support, internal audit, certification readiness, coordination with the Registered Certification Body (RCB) for the final/recertification audit, and ongoing surveillance activities.

The engagement goes beyond a point-in-time assessment and includes gap analysis, risk assessment, SOMS implementation and enhancement, remediation support, staff awareness training, certification/recertification coordination and two subsequent surveillance audits supported by annual refresher training.

4.2 Project Overview and SOMS Scope

4.2.1 Project Overview

BRAC Bank PLC intends to strengthen, maintain and recertify its Security Operations Management System (SOMS) in accordance with ISO 18788:2015 amendment up to 2024 – Management System for Private Security Operations – and achieve the required recertification objectives.

The proposed engagement will support BRAC Bank PLC through the key stages of the ISO 18788 recertification lifecycle, including gap analysis against the ISO 18788:2015 amendment up to 2024  standard, SOMS scope confirmation, identification and classification of security-related assets and their ownership, risk assessment methodology definition and comprehensive risk assessment, SOMS implementation and enhancement support, definition of roles and responsibilities, policy and procedure development, evaluation methods and performance metrics/KPIs, staff awareness sessions, internal audit, remediation, coordination with the Registered Certification Body (RCB), the certification/recertification audit, and subsequent surveillance audits with annual refresher training.

The engagement will adopt a structured, risk-based and practical approach that considers the Bank's existing security operations governance, policies, processes, manuals, forms, templates, technologies, assets, organizational responsibilities and applicable regulatory and contractual requirements relevant to ISO 18788.

4.2.2 SOMS Scope

The SOMS scope will be established and validated in consultation with BRAC Bank PLC based on its organizational structure, business processes, security operations functions, identification of assets, technology environment, locations, interfaces, dependencies and applicable regulatory and contractual requirements.

The scope definition will include consideration of:

- Relevant business units, functions and organizational responsibilities related to security operations.

- Information Security-related assets, identification of information assets and their respective owners.

- Operational facilities, physical security infrastructure and supporting technologies relevant to security operations.

- Security operations processes, protective services, response mechanisms and other functions within the agreed scope.

- Security operations policies, procedures, manuals, forms, templates and operational controls.

- Internal and external interfaces and dependencies that may affect security operations.

- Applicable legal, regulatory and contractual obligations, including relevant Bangladesh Bank guidelines and private security regulations.

- Relevant risks management support and interested-party requirements.

A formal SOMS Scope Statement will be developed and agreed with BRAC Bank PLC. Where required, scope boundaries, interfaces and dependencies will be clearly documented to ensure that the recertification scope is appropriate, defensible and aligned with the Bank's business and security operations objectives.

The final SOMS scope will be subject to BRAC Bank PLC's approval and will form the basis for subsequent risk assessment, control implementation, internal audit and certification/recertification assessment activities.

## 5. Engagement Objectives & Outcomes

5.1 Engagement Objectives

The primary objectives of this engagement are to:

- Establish and strengthen a bank-wide SOMS aligned with ISO 18788:2015 amendment up to 2024, proportionate to BRAC Bank PLC's risk profile, operational complexity and regulatory environment.

- Provide executive and management visibility over security operations risks, controls, risk treatment decisions and the overall effectiveness of the SOMS.

- Strengthen the security operations posture of in-scope services, facilities, supporting infrastructure and relevant business functions.

- Prepare BRAC Bank PLC for successful ISO 18788 recertification assessment through structured gap assessment, readiness review, internal audit, remediation support and certification coordination.

- Establish sustainable good governance, ownership and evidence mechanisms to ensure that the SOMS remains effective, measurable and continually improved beyond the recertification.

- Support ongoing compliance and continual improvement through surveillance audit support, awareness and refresher training, compliance monitoring and periodic review of the SOMS.

5.2 Key Outcomes

Upon completion of the engagement, BRAC Bank PLC will have:

- A formally established, documented and approved Security Operations Management System (SOMS) aligned with ISO 18788:2015 amendment up to 2024.

- A documented Risk Assessment and Risk Treatment Plan appropriate to the approved SOMS scope.

- Documented and implemented security controls with appropriate supporting evidence.

- Trained personnel with clearly defined SOMS roles, responsibilities and accountability.

- Completed internal audit, management review and remediation activities required for recertification readiness.

- A structured certification readiness position for the external ISO 18788:2015 amendment up to 2024 recertification assessment.

- A sustainable framework for ongoing compliance, monitoring and continual improvement of the SOMS.

## 6.  About the ISO 18788:2015 amendment up to 2024 Standard:

ISO 18788:2015 amendment up to 2024 is the internationally recognized standard for establishing, implementing, maintaining and continually improving a Security Operations Management System (SOMS) for organizations conducting or overseeing private security operations. For BRAC Bank PLC, the standard provides a structured, risk-based framework to identify security operations risks, implement appropriate controls, establish accountability, measure effectiveness and drive continual improvement.

In the banking environment, ISO 18788:2015 amendment up to 2024 provides a governance-led approach that extends beyond day-to-day security procedures. It integrates management oversight, security operations policies and procedures, risk management, asset management, operational controls, compliance monitoring, security awareness, internal audit and management review into a coherent SOMS framework.

For BRAC Bank PLC, this approach is particularly relevant given the importance of the Bank's premises, cash and valuables in transit, personnel safety and supporting security operations. A well-implemented SOMS enables the Bank to establish clear ownership and accountability for security operations risks, ensure appropriate controls are implemented and maintained, and provide objective evidence of their effectiveness.

The standard also provides a structured framework for coordinating security operations responsibilities across relevant business, operations and support functions. It enables BRAC Bank PLC to manage security operations risks systematically, maintain appropriate documentation and evidence, support internal assurance and certification activities, and establish a foundation for continual improvement and sustainable ISO 18788:2015 amendment up to 2024 compliance.

The proposed engagement will therefore focus not only on achieving recertification, but on strengthening the Bank's overall security operations governance, risk management and SOMS maturity in alignment with the requirements defined in the BRAC Bank PLC Scope of Work.

## 7. ISO 18788 Recertification Benefits

For BRAC Bank PLC, successful recertification to ISO 18788:2015 amendment up to 2024 can deliver the following strategic and operational benefits:

Figure 1: Benefits of ISO 18788

## 8. About CipherShield

CipherShield Bangladesh Ltd. is a specialist cybersecurity and Governance, Risk and Compliance (GRC) organization providing practical capabilities across ISO management-system certifications, security governance, technical assurance, risk management and audit readiness. Its delivery approach is focused on developing practical, defensible and sustainable security management systems suitable for highly regulated and high-accountability environments.

For BRAC Bank PLC, CipherShield's focus will be to support the development and enhancement of a banking-appropriate SOMS aligned with ISO 18788:2015 amendment up to 2024, while considering the operational requirements and complexities of a large financial institution. The engagement will extend beyond documentation and will address SOMS scope, governance, control ownership, risk assessment, risk treatment, evidence management, awareness, internal assurance and recertification readiness as interconnected components of the overall programme.

Our Key Differentiators:

- Audit-Defensible Delivery: Development of traceable documentation, evidence structures and governance practices aligned with ISO 18788:2015 amendment up to 2024 recertification assessment expectations.

- Banking-Sector Pragmatism: Designing and supporting controls and processes that are practical for a large financial institution without creating unnecessary operational complexity.

- Risk-Led Prioritization: Prioritizing security operations risks and controls based on their relevance to critical banking services, assets and organizational objectives.

- Specialist ISO 18788 Capability: Engagement supported by appropriately qualified practitioners with practical experience in management-system implementation, assessment and security operations management.

- End-to-End Support: Providing structured support from SOMS scoping, asset and risk assessment and risk treatment through internal audit, management review, remediation and recertification readiness.

The overall objective is to help BRAC Bank PLC maintain a SOMS that is not only recertification-ready, but also practical, measurable, maintainable and capable of supporting continual improvement beyond this recertification cycle.

## 9. Industry Accreditations

| CipherShield is a PCI DSS Qualified Security Assessor (QSA) Company for the Asia Pacific region. |  |
| --- | --- |
| CREST International Accredited Penetration Testing (VAPT) Services Our CREST International accreditation reflects our commitment to technical excellence, integrity, and proven methodologies based on PTES, NIST SP 800-115, and OWASP. | CREST Company ID: 09971032– 1 |

## 10. Credentials & Capability Snapshot:

For this engagement, CipherShield will bring a multidisciplinary delivery model combining SOMS implementation advisory, risk and control expertise, technical/operational assurance capability, and audit readiness support. This is particularly important for a banking programme of this size, where successful delivery depends on more than one consultant or one documentation work stream.

CipherShield’s capability for this engagement includes:

- ISO 18788 management-system implementation leadership, including SOMS scope definition, gap analysis and assessment, policy and procedure framework development, control documentation, and certification readiness and subsequent surveillance audits support.

- Banking-relevant Information System risk and governance expertise, including the risk assessment workshops, risk treatment planning, ownership alignment, governance reporting, and evidence management.

- Information Security assurance capability, including control testing, verification reviews and site/process validation to assist in confirming control effectiveness and prioritizing remediation.

- Internal audit and assurance support, including internal audit planning, execution support, reporting, mitigation tracking, and readiness activities before the recertification audit.

This blended capability is important because large banking SOMS programme frequently encounter challenges such as distributed ownership, varying levels of control maturity, competing operational priorities, legacy practices, and delays in remediation. A successful implementation partner must therefore be able to support governance, operational validation, coordination, and audit preparation in parallel.

## 11. CipherShield Approach

CipherShield proposes an implementation model that is structured, risk-based, evidence-led, and adapted to the operating complexity of BRAC Bank PLC. The objective is to maintain a SOMS that is not only aligned with ISO 18788:2015 amendment up to 2024, but also workable across the bank's people, processes, technologies, facilities, infrastructure, and assurance functions.

Emphasis is placed on:

- Executive and cross-functional good governance

- Traceable risk treatment decisions

- Practical control implementation

- Ongoing evidence development

- Internal audit and management review preparedness

The engagement will be delivered through the following stages:

| Project Stage | Proposed Location | Rationale for Change / Optimization |
| --- | --- | --- |
| Stage 1: Project Initiation & Planning | On-site | Face-to-face kick-offs build necessary trust and alignment. |
| Stage 2: Gap Assessment & Current State Analysis | On-site | Ideal for physical security walk-throughs, stakeholder interviews, and white boarding. |
| Stage 3: Stage 3: SOMS Framework & Documentation Development. | Off-site/ Hybrid | Policy and procedure drafting is deep-focus work best done remotely. If required then meet with stakeholders. |
| Stage 4: Risk Assessment & Treatment | Off-site/Hybrid | Conduct Risk Identification workshops On-site, but do the heavy lifting of Risk Register calculation and Treatment Plan drafting Off-site. |
| Stage 5: Control Implementation & Support | Off-site/ Hybrid | Most tracking and IT support can be remote, but deploying physical controls or complex internal infrastructure changes often benefits from periodic On-site visits. |
| Stage 5A: Security Control Testing, Verification & Configuration Review. | Hybrid (On-site/Off-site) | External VAPT is strictly Off-site. Internal VAPT/Configuration review may require On-site presence depending on whether the client allows remote VPN access to critical infrastructure. |
| Stage 6: Training & Awareness Programs | Off-site/ Hybrid | Deliver leadership/key stakeholder training On-site for impact, but roll out general employee awareness via a remote LMS (Off-site) for efficiency and tracking. |
| Stage 7A: Internal Audit | On-site | It works as excellent. Auditors must observe processes and physical environments directly. |
| Stage 7B: Internal Audit – Mitigation Efforts. | Off-site | Verifying evidence of corrected non-conformities is easily done remotely. |
| Stage 7C: Management Review (SOMS Performance & Sign-off) | (On-Site/Hybrid) | ISO 18788 strictly follows, Management Review (Clause 9.3) is a mandatory requirement for certification |
| Stage 8A: Pre-Certification Training | On-site | Great for preparing staff on how to answer external auditor questions. |
| Stage 8B: Certification Support – External Audit Defense & NC Resolution | On-Site | For a major financial institution, "Certification Support" needs to be explicitly defined so the Bank understands exactly what value are providing while the external auditors (the Certification Body) are in the building. |

Table 2: Project Stage

This structure is intentionally designed to suit a large banking programme. It creates clear progression from governance and current-state review to design and implementation, to testing and assurance, and finally to recertification readiness. It also allows the bank to manage ownership across multiple stakeholders while maintaining a clear line of sight to milestone outcomes

CipherShield consultants possess a wealth of experience that is crucial in helping our clients achieve ISO management-system certification and recertification. The entire ISO 18788 recertification process is divided into well-defined phases, which will be explained in upcoming sections.

## 12. Certification path (Stage 1 and Stage 2)

ISO 18788:2015 amendment up to 2024 recertification is typically completed in two stages by an accredited certification body. The first stage is a readiness and documentation review intended to confirm that the SOMS framework has been properly established, that scope and context are defined, and that the organization is ready to proceed to the implementation effectiveness review.

The second stage is the certification audit itself, where the certification body evaluates the operation and effectiveness of the SOMS and selected controls across the agreed scope.

CipherShield's role is to prepare BRAC Bank PLC for both stages by helping the bank build the required framework, coordinate evidence, facilitate internal assurance activities, and address issues before the certification audit. The responsibility for certification decision-making remains with the external certification body, consistent with standard ISO practice

ISO 18788:2015 amendment up to 2024 recertification is typically completed in two stages by an accredited certification body:

## 13. Governance, reporting, and audit evidence model

To provide executive visibility and maintain audit defensibility, CipherShield will operate a lightweight governance cadence across the engagement, including:

- Cadence: weekly project working sessions, fortnightly status reporting to the Project Sponsor / Steering Committee; and milestone gate reviews prior to internal audit and external audit.

- Reporting: status report covering progress, upcoming activities, decisions required, risks/issues, and dependencies.

- RAID log: a consolidated register of risks, actions, issues, and decisions to support transparency and timely escalation.

- Document control: controlled templates and review/approval workflow to ensure documented information is current, approved, and traceable.

- Evidence preparation: an evidence index aligned to ISO 18788 clauses/controls to reduce audit friction during Stage 1 and Stage 2. Develop milestone readiness checkpoints before internal audit and certification stages.

This model is particularly important in a banking environment, where implementation delays are often driven not by technical difficulty alone, but by cross-functional dependencies, delayed approvals, fragmented ownership, and competing operational priorities. Strong governance reduces these risks and improves the bank’s ability to maintain momentum toward certification readiness.

## 14. Banking-Specific Delivery Considerations:

CipherShield’s implementation approach for BRAC Bank PLC is tailored to the high-stakes risk environment of the financial sector. Our methodology places particular emphasis on the following critical areas:

- Security Operations Governance & Board Accountability: Alignment of the SOMS with the Bank’s Enterprise Risk Management (ERM) framework, ensuring that security objectives support overall business strategy, provide transparent executive reporting, and comply with Bangladesh Bank regulations.

- Human Rights & Rules of Engagement (RoE): Strict integration of legal and human rights frameworks, a core mandate of ISO 18788. We will assess and formalize policies regarding the Use of Force, apprehension guidelines, and ethical conduct for all internal and outsourced security personnel.

- Access Control and High-Value Asset Security: Rigorous assessment of physical access management, restricted-area controls (e.g., Vaults, Currency Chests, Data Centers), guarding deployments, key/asset custody, and mandatory segregation of duties within the SOMS scope.

- Supplier and Third-Party Risk Management (TPRM): Comprehensive evaluation of security risks originating from third-party dependencies. This includes strict SLA monitoring and compliance vetting for outsourced guarding agencies, Cash-in-Transit (CIT) vendors, and ATM replenishment services.

- Resilience, BCM, and Incident Response: Synchronization of security operations with the Bank's Business Continuity Management (BCM). We will validate emergency response and crisis management protocols across corporate branches, primary operations centers, and supporting facilities.

- Traceable Risk Treatment and Ownership: Ensuring that all risk treatment decisions are formally documented, mapped to the Bank’s defined risk appetite, and signed off by appropriate business, operational, and security risk owners.

- Evidence-Based Implementation & KPIs: Moving beyond mere documentation by establishing verifiable Key Performance Indicators (KPIs). We focus on generating the concrete operational artifacts (e.g., incident logs, drill reports, guard training records) required to prove the effective implementation of controls.

- Internal Audit and Recertification Readiness: Equipping the Bank’s internal teams with the frameworks needed to sustain compliance. We prepare the Bank for a frictionless internal audit and external recertification assessment across the agreed organizational, operational, and facility scope.

## 15. Regulatory and Standards Alignment

As part of the SOMS implementation, CipherShield will develop and tailor security operations policies, procedures, and supporting standards to ensure compliance not only with ISO 18788:2015 amendment up to 2024, but also with applicable Bangladesh regulatory requirements, including relevant directives and guidelines issued by Bangladesh Bank (BB).

Where applicable, policies and controls will also be aligned with other banking-specific security and regulatory obligations relevant to the Bank's security operations, ensuring consistency across regulatory, contractual, and industry requirements.

This integrated approach ensures that the SOMS established for BRAC Bank PLC supports international best practices while remaining compliant with local regulatory expectations and sector-specific control requirements.

ISO 18788 – Implementation Process

CipherShield's methodology for the ISO 18788 recertification is explained below.

Figure 3: ISO 18788 Certification Implementation Workflow

The implementation steps are further explained by representing the various stages of the Plan-Do-Check-Act (PDCA) model, along with the detailed activities described in ISO 18788.

The figure below outlines the complete lifecycle that an organization typically adopts when implementing and maintaining an enterprise-wide Security Operations Management System (SOMS).

Figure 4: ISO 18788 Implementation Mapping with PDCA Model

## 16. High Level Project Plan

The project scope is divided into multiple stages. A High-level plan is shown below:

| Resource Name | Initials |
| --- | --- |
| Md Aktaruzzaman Sarker | AZ |
| Muhammad Asaduzzaman | ASZ |
| Haider Memon | HM |
| Aslam Khan | AK |
| Ruman Sarawer | RS |
| Mohammad Iftekhar Hasan | IH |
| Fahima Khanom | FK |
| Soma Harish | SH |
| Sabah Ali | SA |
| Kanwal Siddiqui | KS |
|  | On-Site Activities |
|  | Off-Site Activities |

## 17. Project Deliverables

This engagement culminates in the production of the deliverables below.

| Phase | High-level deliverables |
| --- | --- |
| 1. Project Initiation & Planning | Project kick-off meeting, stakeholder register, Security Operations Steering Committee (SOSC) established, SOSC charter, project governance model, ISO 18788 recertification project plan, initial security operations policy, SOMS scope confirmation, meeting minutes and action tracker. |
| 2. Gap Assessment & Current State Analysis | Current-state documentation review, legal/regulatory/contractual obligations register, banking regulatory mapping, clause-by-clause ISO 18788 gap assessment, people/physical/process/organizational control maturity assessment, gap assessment report, management presentation, asset register template. |
| 3. SOMS Framework & Documentation Development | Mandatory ISO 18788 documentation set, security operations policy suite, risk management policy and methodology, internal audit and corrective action procedure, document and records control procedures, standard operating procedures for security operations, policy exception template, controls-to-documentation mapping tracker, security operations objectives. |
| 4. Risk Assessment & Treatment | Asset register completion, security-related asset identification and classification, threat and vulnerability analysis, detailed risk analysis and evaluation, bank-specific control review, business impact analysis alignment, risk treatment plan, risk owner assignment, risk workshop outputs, SOSC risk presentation, updated minutes and action tracker. |
| 5A. Control Implementation and Support | Control readiness workshop, controls implementation tracker, control advisory and verification support, evidence collection, KPI/KRI tracking, supplier and third-party security review, vendor due diligence support, contract/SLA security clause review, outsourced-guarding and third-party access review, control implementation status reporting. |
| 5B. Security Control Testing & Verification Review | Physical and operational security control testing, site/process verification review, findings tracker, severity rating and remediation recommendations, validation of high and medium findings, closure evidence for remediation items where applicable. |
| 6. Training & Awareness Programs | Training needs analysis, awareness material set, induction module review, incident-response and emergency-procedure awareness content, on-site SOMS training sessions for in-scope departments, attendance records, post-training feedback summary, incident response tabletop review support. |
| 7A. Internal Audit | Internal audit plan, audit programme, stakeholder schedule, audit working papers, internal audit report, non-conformity register, observation log, internal audit presentation to SOSC, management minutes and action tracker. |
| 7B. Internal Audit Mitigation Efforts | Corrective action tracker, evidence of remediation, corrective action verification, closure status report, residual issue log, pre-certification readiness status update. |
| 8A. Certification Support – Pre-Certification | Certification body selection support, audit readiness review, mock interview support, board/senior management SOMS briefing, audit evidence index, final document review, readiness checklist, audit coordination plan. |
| 8B. Certification Support – On-Site | Stage 1 audit support, Stage 1 findings response support, Stage 2 audit support, real-time evidence coordination, corrective action / observation response support, certification closure support, project sign-off documentation. |

Out of Scope

The following activities are excluded from the scope of this proposal unless specifically agreed otherwise in writing:

- Major Infrastructure Replacement or Technology Procurement: Procurement, replacement or major upgrade of security equipment, surveillance/access-control hardware, guarding technology or other physical security assets required to address identified gaps.

- Direct Technical Deployment: Hands-on installation, configuration, deployment or operational implementation of physical security controls and technologies. CipherShield will, however, provide implementation guidance, technical recommendations and remediation support as required under the agreed scope.

- Large-Scale Facility or Infrastructure Redesign: Development, redevelopment or major architectural redesign of facilities, security infrastructure or business premises arising from identified security operations requirements.

- Third-Party Execution: Remediation activities that require direct execution by external security vendors, guarding companies or other third parties. CipherShield will provide appropriate advisory and remediation guidance within the agreed scope.

- Activities Outside the Approved SOMS Scope: Assessments, implementation activities or advisory services relating to business units, systems, locations, processes or security-related assets that are not included within the formally agreed SOMS scope.

- Material Scope Changes: Additional work arising from material changes to the Bank's organizational structure, certification scope, technology environment, business operations, regulatory requirements or operating model after commencement of the engagement, where such changes require substantial additional effort.

## 18. Project Assumptions

The proposal, implementation approach and delivery schedule are based on the following assumptions:

- BRAC Bank PLC will appoint an appropriate project sponsor and dedicated project focal point to facilitate coordination, communication and timely decision-making throughout the engagement.

- Relevant stakeholders from security operations, facilities, business, risk, compliance, operations and other in-scope functions will be available for workshops, interviews, assessments, reviews and approvals as required.

- BRAC Bank PLC will provide timely access to relevant SOMS documentation, policies, procedures, risk records, asset registers, control evidence, personnel and other information necessary to perform the engagement.

- Required on-site access and logistical arrangements will be made available for activities specified in the Scope of Work, including the internal audit.

- Decisions relating to SOMS scope, security operations risks, risk treatment, policies, procedures and other required approvals will be completed within mutually agreed timelines.

- BRAC Bank PLC will retain ownership of risk treatment decisions, remediation actions and implementation of controls, and will ensure that agreed remediation activities are progressed within the established governance timelines.

- Where evidence, information or validation depends on third-party service providers, vendors or other external stakeholders, BRAC Bank PLC will facilitate the required coordination and access.

- BRAC Bank PLC will provide the necessary support for security-asset identification, ownership and classification, risk assessment, SOMS implementation, internal audit and recertification readiness activities.

- The engagement will commence within the timeline specified in the Scope of Work, with the project start targeted within 15 days of issuance of the Purchase Order, subject to stakeholder and resource availability.

- Recertification assessment scheduling will be coordinated with the Registered Certification Body based on the Bank's readiness, completion of required pre-assessment activities and the Certification Body's availability.

- The internal audit will be conducted independently of the implementation support activities and will be performed prior to the formal recertification assessment, as required by the Scope of Work.

- BRAC Bank PLC will facilitate the participation of relevant management and process owners in awareness sessions, internal audit, management review and certification-readiness activities.

- Any material changes to the agreed SOMS scope, organizational structure, business operations, technology environment, certification requirements or project timeline may require a review of the delivery plan and associated effort.

## 19. Critical Success Factors for ISO 18788 Implementation:

The success of the engagement will depend on several critical factors that are particularly vital within a large, highly regulated banking environment. These factors are not optional; they are the foundational conditions required to support timely delivery, mitigate operational liabilities, and ensure a credible certification outcome.

Where these factors are maintained, the implementation will produce a resilient, legally compliant Security Operations Management System (SOMS), rather than merely a paper-based compliance framework. The key success factors are:

Governance & Leadership

a. Active Board and Executive Accountability: Strong sponsorship from BRAC Bank PLC leadership that moves beyond passive endorsement to enforce true governance, integrating SOMS objectives directly into the bank's corporate risk strategy.

b. Decisive Steering Committee Oversight: Consistent, engaged oversight from the Security Operations Steering Committee (SOSC) to ensure rapid issue escalation and actionable decision-making, avoiding administrative bottlenecks.

Operational Integration

c. Cross-Functional Participation: Active, sustained engagement not only from technology and business units, but crucially from Legal, Human Resources, Compliance, and Physical Security teams.

d. Clear Ownership of Specialized Risks: Unambiguous accountability assigned to specific owners for specialized ISO 18788 deliverables, including Human Rights Impact Assessments, Use of Force protocols, and Grievance Mechanisms.

Execution & Verification

e. Early Attention to High-Impact Gaps: Immediate prioritization of high-risk physical security vulnerabilities, third-party/subcontractor guarding compliance, and critical governance gaps.

f. Timely Documentation & Legal Review: Prompt review and approval of complex documentation, remediation actions, and critical standard operating procedures (SOPs).

g. Verifiable Field Evidence: The availability of reliable, real-world evidence to demonstrate that operational controls (e.g., incident response, code of conduct adherence, and training) are actively functioning on the ground, not just in policy.

h. Rigorous Pre-Certification Validation: Thorough readiness of internal audit and top management review activities, ensuring all non-conformities are aggressively mitigated prior to the external certification audit.

Where these factors are maintained, the implementation is much more likely to progress smoothly and produce a durable SOMS rather than a compliance-only framework.

## 20. Project Risks

Given the scale and cross-functional nature of the BRAC Bank PLC programme, successful delivery will depend on disciplined governance, timely stakeholder participation, and consistent remediation follow-through. The key implementation risks for a banking-sector ISO 18788 programme of this nature include the following:

| Project risk | Potential impact | Proposed mitigation |
| --- | --- | --- |
| Lack of management commitment | Slow decisions, weak governance, low staff buy-in, project delays, possible certification failure. | Secure executive sponsorship, hold regular management reviews, and keep leadership informed. |
| Resources and budgets are not allocated | Insufficient staff/time/budget, incomplete implementation, schedule slippage. | Build a business case, assign owners, define resource needs early, and escalate shortages. |
| Delayed stakeholder decisions or approvals | Slippage in document finalization, risk treatment sign-off, and implementation milestones | Establish an executive sponsor, maintain a clear decision log, and use milestone-based approval deadlines |
| Limited availability of business and technical control owners | Delays in workshops, evidence collection, and validation of operating controls | Nominate departmental focal points early and schedule workshops and review cycles in advance |
| Overreliance on documentation without operational evidence | Weak audit outcomes and nonconformity risk during certification | Build an evidence index throughout the project and test evidence readiness before audit stages |
| Competing operational priorities within the bank | Reduced engagement from key teams and slower delivery momentum | Use agreed governance cadence and sponsor-level escalation for priority conflicts |
| Dependency on third parties or external providers | Delays in obtaining evidence, contracts, configurations, or control confirmations | Identify third-party dependencies early and track them separately as part of RAID management |

Table 7: Project Risks

## 21. Project Team

21.1 CipherShield Team

| Name | Role | Experience and Skills |
| --- | --- | --- |
| Fouzan Shaikh | Project Manager and QA | - CISSP, CISA, CRISC, CISM, CDPSE, CCSK v4, PCI DSS QSA, ISO 27001 Lead Auditor, ISO 42001 Lead Auditor, ISO 27701 Lead Implementer and Lead Auditor, ISO 22301 Lead Auditor, Essential 8, ISA 62443 Risk Assessment Specialist, Risk Management, NIST CSF, NIST AI RMF - Bachelor of Electronics and Telecommunications Engineering |
| Md. Aktaruzzaman Sarker | Project lead and QA | - CISA, ISO27001 Lead Auditor & Lead Implementer, Certified Expert in Risk Management (CERM), CEH, JAIBB. - Bachelor of Science in Engineering - Master of Engineering - MBA |
| Muhammad Asaduzzaman | Documentation and Risk Assessment | - PCI QSA, CISA, CISM, SWIFT CSP CA, ISO 27001 Lead Auditor. - B Sc in CSE. - Master of Engineering in Information Systems Security. |
| Aslam Khan | Training, Internal Audit and External Audit Support | - Lead Auditor ISO 9001, ISO 14001, ISO 20000, ISO 22000, ISO 27001, ISO 30000, ISO 42001, ISO 45001, ISO 50001, HACCP and HALAL. - Trainer ISO 9001, ISO 14001, OHSAS 18001, ISO 22000, ISO 28001, ISO 27001, ISO 30000, ISO 42001, ISO 50001, HACCP, HALAL, FSC, MLC 2006, FSC etc. - Doctor of Management (Enrolled Ph.D.), Master of Business Administration, Major in Management, Master of Cybersecurity, M. Phil, Focus on Environment & Sustainability, AI-Powered Cybersecurity Engineering |
| Ruman Sarawer | On-Site Training, Internal Audit and External Audit Support | - CISSP, CISA, ISO 27001 Lead Auditor, ISO 27701 Lead Implementer and Lead Auditor, ISO 42001 Lead Implementer and Lead Auditor, Certified Essential 8 Implementer, ISA 62443 Expert, CCSK v5, Risk Management, NIST CSF, NIST AI RMF, AI Governance - Bachelor of IT (Major in Cyber Security) |
| Mohammad Iftekhar Hasan | Internal Audit and External Audit Support | - Certified Lead Auditor: Qualified Lead Auditor for ISO 9001, ISO 14001, ISO 27001, CISSP, CC, CCNA, MCP and CPISI, with hands-on delivery of ISO 27001:2022, CISSP and CISA-aligned audits and training. - Governance, Risk & Compliance: ISO 9001, ISO 14001, ISO 27001:2022, CISSP, CISA, IT security audit, risk management, compliance certification and PCI DSS. - CISSP, CISA, CDCP, CCNA, RHCE, MS Azure Administrator, CompTIA Linux+ and ISP Setup - Post Graduate: MSc in Telecommunication Engineering - Graduate: BSc (Hons) in Computer Science & Engineering |
| Fahima Khanom | Technical Documentation, IT/IS Auditor | - CISA, CMMI Level 3 – Dev V2.0, ISMS LA - Post Graduate: MSc in Computer Science; MBA in Finance; M.Sc in Food & Nutrition - Graduate: B.Sc. in Food & Nutrition - Diploma: MIS & IT |
| Kanwal Siddiqui | On Site Internal Audit | - CISM, CISA, AAIA, CSPO, CSM, - Bachelor of Commerce (Hons) - Finance - Master of Commerce – Finance |
| Haidar Memon | Technical Consultant | - CISSP, CCSP, SSCP, ISO 27001 Lead Auditor, Certified Essential 8 Implementer, Microsoft SC 300, AZ 500, CompTIA CySA+ - BS in Computer Information Systems, University of Houston - MS in Management Information Systems, University of Houston |
| Soma Harish | Penetration Tester | - OSCP, CEH, SANS – Cybersecurity Fundamentals, AttackIQ – MITRE ATT&CK, - Master in Cybersecurity from Melbourne Institute of Technology |
| Sabah Ali | ISMS Documentation | - ISO 27001:2022 Lead Auditor, Certificate in Cybersecurity (ISC2), ISO 27701 Lead Implementer and Lead Auditor - Master in computer science |
| Ummay Maimona | ISMS Documentation | - ISO 27001:2022 Lead Auditor, - Bachelor of Engineering |

Table 8:  Project Team

## 22. BRAC Bank PLC Team

The availability and active participation of the following BRAC Bank PLC resources will be essential for the successful and timely delivery of the ISO 18788:2015 amendment up to 2024 recertification engagement:

- Project Sponsor / Senior Management Representative to provide executive direction, facilitate decisions and ensure organizational support.

- Security Operations Representatives responsible for coordinating SOMS-related activities and facilitating engagement with relevant stakeholders.

- Departmental Focal Points / Security Operations Coordinators from relevant in-scope business and support functions, as applicable to the agreed SOMS scope.

- Control Owners / Asset Owners / Risk Owners to support control assessment, security-asset ownership, risk identification, risk treatment and evidence validation.

- Facilities and Security Infrastructure Representatives, including relevant teams responsible for physical infrastructure, access control, guarding operations and supporting facilities.

- Risk, Compliance and Governance Representatives to support regulatory, compliance and risk-management requirements relevant to the SOMS.

- Internal Audit Representatives to facilitate coordination of internal audit activities and support alignment with the Bank's internal assurance framework.

- Human Resources, Procurement, Legal, Operations, Facilities and other relevant business/support functions, where their processes, security-related assets or responsibilities fall within the agreed SOMS scope.

The final stakeholder structure will be confirmed during project initiation based on the approved SOMS scope, organizational structure, security-related assets, processes and responsibilities identified during the engagement.

## 23. Previous Project Experience:

CipherShield has successfully conducted multiple GRC and ISO 27001 deployments for several critical clients, demonstrating proven expertise and practical experience in cybersecurity compliance, risk management, and maturity evaluation.

| Client Name | Project Description |
| --- | --- |
| InSource IT | ISO 27001:2022 Implementation. Also Supporting for their surveillance audit. |
| Illuminance Solutions | ISO 27001:2022 Implementation. Also Supporting for their surveillance audit. |
| Insight Hospitals | Security Policies and Procedures as per ISO 27001:2022, NIST CSF and HIPAA. |
| Road Safety Commission | ISO 27001 Gap Assessment, Essential 8, Third Party Risk Assessment |
| Wilson Parking Australia and Wilson Parking New Zealand | On-site support for PCI DSS Implementation advisory across multiple sites. Developed security policies and procedures as per ISO 27001 and PCI standards. |

Table 9: Previous Project Experience (executed by CipherShield)

## 24. Project Management (ISO 18788 Optimized)

24.1 Project Governance (Aligned with ISO 18788 Clause 5: Leadership):

- Top Management / Project Sponsor: Responsible for overall project success, ensuring the integration of the Security Operations Management System (SOMS) requirements into the bank’s broader business processes, and providing necessary resources. (from BRAC Bank PLC)

- Project Manager (SOMS Implementation Lead): Responsible for day-to-day project execution, cross-functional coordination, and driving the Plan-Do-Check-Act (PDCA) implementation cycles. (from CipherShield)

- Security Operations Steering Committee (SOSC): Composed of key stakeholders (including Legal, Compliance, and HR representatives) to provide strategic oversight, ensure board-level accountability, and enforce adherence to human rights and legal obligations throughout the project. (from BRAC Bank PLC and CipherShield)

24.2 Project Management Methodology (Integrated PDCA & Agile):

- A hybrid approach will be utilized. We will use Agile iterative cycles for document development and process mapping to ensure adaptability, operating within the strict Plan-Do-Check-Act (PDCA) phase gates required for ISO 18788 certification.

- Weekly operational meetings with the project team to review implementation progress, address control gaps, and manage the action tracker.

- Bi-weekly executive status reports to the SOSC and Project Sponsor, focusing on risk mitigation progress and milestone achievement.

24.3 Project Risk Management (Aligned with ISO 18788 Clause 6.1):

- Conduct comprehensive, ongoing risk assessments that specifically include a Human Rights Impact Assessment (HRIA) alongside traditional security and asset risk evaluations.

- Identify threats to internal assets, personnel, and external stakeholders (including local communities) at the project's inception and continuously throughout its lifecycle.

- Develop strict risk treatment and mitigation strategies, establishing formalized contingency and business continuity plans for high-impact operational and legal risks.

24.4 SOMS Assurance & Quality Control (Aligned with ISO 18788 Clause 9):

- Develop a SOMS Performance Evaluation plan that outlines the metrics, Key Performance Indicators (KPIs), and procedures for ensuring all deliverables meet ISO 18788 standard requirements.

- Internally conduct regular reviews, document control checks, and pre-certification audits to verify compliance with established security policies, Rules of Engagement (RoE), and international law.

RACI Matrix (High Level)

The table below clarifies responsibility and accountability for key activities (R=Responsible, A=Accountable, C=Consulted, I=Informed).

| Activity | CipherShield | [Company] |
| --- | --- | --- |
| Define SOMS scope, context, interested parties | R | A/C |
| Risk assessment & treatment methodology; conduct workshops | R | A/C |
| Develop Risk Treatment Plan (RTP) and control implementation plan | R | A/C |
| Develop Policy/procedure drafting and tailoring | R | A/C |
| Implementation of technical/operational controls. Close findings from the Gap Assessment, Risk Assessment and Internal Audit findings. | C | R/A |
| Awareness Training | R | A/R attendance) |
| Internal Audit Planning and Execution | R | A/C |
| Management Review Meetings | R | A |
| Certification body selection support | C | R, A |
| Ensure that project is on track | R, A | C |
| External audit (Stage 1/2) support and evidence coordination | R | A/C |

Table 10: RACI Matrix

Change Management Process

Any work requested outside the agreed scope will be managed through the Change Management Process and priced separately upon written approval.

Initiation

Either party, [Company] or CipherShield, can initiate a change request by documenting the required changes and submitting a Change Request Form (CRF) to the designated project manager.

Evaluation

The project manager shall evaluate the change request to determine its impact on the project's scope, timeline, and cost. This evaluation shall include:

- A detailed description of the change

- An assessment of the impact on the current project plan.

- A revised cost estimate, or revised timeline, if applicable

Approval

Before it is implemented, both parties must review and approve the change request. Approval can be provided via email or a signed document.

Implementation

Once approved, the change will be incorporated into the project plan. The project manager shall ensure that all stakeholders are informed of the approved changes and that the project plan, budget, and schedule are updated accordingly.

Documentation

All approved changes must be documented in an updated version of the SoW and the project plan to ensure a clear record of any alterations to the original agreement.

## 25. Bidder Eligibility & Supporting Documents Checklist

| # | Eligibility / Requirement | Supporting Document to Include | Status |
| --- | --- | --- | --- |
| 1 | Reputed company with relevant banking / financial-sector experience | Company profile + banking client references | ☐ |
| 2 | Minimum 5 similar successfully completed projects within the last 5 years | Project completion certificates / client references / work orders | ☐ |
| 3 | Experience in ISO 18788 design, development, implementation and successful certification assistance | Relevant project list + completion/reference letters | ☐ |
| 4 | Experience conducting full ISO 18788 audits | Audit engagement references / certificates / completion letters | ☐ |
| 5 | Minimum 10 years' IT/IS audit and advisory experience | Company incorporation certificate + company profile + evidence of experience | ☐ |
| 6 | CAB / certification-related organization with minimum 10 years' existence, preferably accredited by recognized British, American, North American or Australian accreditation body | Accreditation certificate + CAB profile + incorporation/establishment evidence | ☐ |
| 7 | Qualified project resources with minimum 10 years' relevant experience | CVs + professional certifications | ☐ |
| 8 | Resources holding relevant certifications such as ISO 27001 LA/LI, CISSP, CISM, CCSP | Copies of professional certificates | ☐ |
| 9 | Resource with similar experience with at least 3 banks during the last 2 years | CV + client/project references | ☐ |
| 10 | Evidence of company history, differentiators and comparable scope, size and complexity | Company profile + case studies + client references | ☐ |
| 11 | Independent and documented ISO 18788 methodology | Proposed methodology / approach document | ☐ |
| 12 | Ability to commence within 15 days of PO | Project mobilization plan / undertaking | ☐ |
| 13 | Ability to complete the engagement within the agreed timeline | Project plan / Gantt chart | ☐ |
| 14 | Professional, objective and impartial advisory approach | Methodology + independence statement | ☐ |
| 15 | Required NDA | Signed NDA | ☐ |
| 16 | Customer references | Reference list with client name, project, scope, period and contact details | ☐ |
| 17 | Training / awareness capability | Training plan + trainer CVs | ☐ |
| 18 | Non-blacklisting declaration | Signed declaration | ☐ |
| 19 | Availability for mandatory presentation within 10 working days, if shortlisted | Signed undertaking / confirmation | ☐ |
| 20 | Regional customer base and satisfactory certifications | Customer list / references / certificates | ☐ |
| 21 | Similar assessment experience | Relevant project credentials | ☐ |
| 22 | Team professional qualifications and profiles | Detailed CVs + certificates | ☐ |
| 23 | Local partner details, if applicable | Partnership/authorization agreement | ☐ |
| 24 | Rankings / industry recognition such as Gartner/Forrester, if any | Supporting evidence, if applicable | ☐ |
| 25 | Relevant case study | 1–3 comparable case studies | ☐ |
| 26 | Sample reports | Sample gap assessment / risk assessment / internal audit / certification-readiness report | ☐ |
| 27 | Supplier Relationship Declaration | Completed and signed Annexure-2 | ☐ |
| 28 | Company legal documents, where applicable | Trade License / Certificate of Incorporation | ☐ |
| 29 | TIN | TIN Certificate | ☐ |
| 30 | BIN | BIN Certificate | ☐ |
| 31 | Financial capability, where requested for participation | Bank Solvency Certificate / Bank Statement | ☐ |
| 32 | Company profile | Updated corporate profile | ☐ |
| 33 | Contact information | Authorized contact person's name, mobile and email | ☐ |

## 26 Non-Compliance Declaration:

Declaration No functional or technical exception is proposed against the RFP scope described in Annexure-II. No commercial information is included in this technical proposal.

## 27. Authorization and Acceptance:

| For and on behalf of | ACNABIN, Chartered Accountants |
| --- | --- |
| Authorized Signatory | Muhammad Aminul Hoque, FCA |
| Designation | Partner |
| Signature |  |
| Date | 17 Augus 2026 |
| Company Seal |  |
| Mobile | 01671-024714 |
| Email | amin@acnabin-bd.com |