TECHNICAL PROPOSAL

for

Appointment of Forensic Auditor for the Provident Fund (PF) Accounts of

FARIDPUR SUGAR MILLS LTD.

Submitted to:

Chief Auditor

Bangladesh Sugar & Food Industries Corporation (BSFIC)

Chinishilpa Bhaban (8th Floor), 3 Dilkusha C/A, Dhaka-1000

EOI Ref: 36.04.0000.022.17.001.26/677 dated 29 July 2026

Submitted by:

ACNABIN, Chartered Accountants

An Independent Member Firm of Baker Tilly International

BDBL Bhaban (Level-13 & 15), 12 Kawran Bazar Commercial Area, Dhaka-1215

| Contact Info: Abdullah-Al-Mamun, FCA Director, Audit & Consultancy ACNABIN, Chartered Accountants Email: mamun.abdullah@acnabin-bd.com Phone: +8801915-561888 | Secondary Contact: Md. Shif All Mostakin Assistant Director, Audit & Consultancy ACNABIN, Chartered Accountants Email: mostakin@acnabin-bd.com Phone: +8801820-584481 |
| --- | --- |

# Letter of Transmittal

01.18/2026/0000 (ii)

Date: [To be finalized on submission]

To

The Chief Auditor

Bangladesh Sugar & Food Industries Corporation (BSFIC)

Chinishilpa Bhaban (8th Floor)

3 Dilkusha C/A, Dhaka-1000.

Dear Sir,

We, the undersigned, offer to provide forensic audit services for the Provident Fund (PF) accounts of Faridpur Sugar Mills Ltd. covering FY 2015-16 to FY 2025-26, in accordance with your Expression of Interest Ref. 36.04.0000.022.17.001.26/677 dated 29 July 2026, and our enclosed Technical Proposal. Our Financial Proposal is submitted separately under sealed cover, as required.

If our Proposal is accepted, we undertake to commence the assignment within the timeframe specified by BSFIC following formal engagement, and our Proposal shall remain binding upon us, subject to any modifications resulting from contract negotiations.

We confirm that the Government of Bangladesh has not declared ACNABIN, or any of its partners or proposed staff, ineligible on charges of engaging in corrupt, fraudulent, collusive, or coercive practices, and we pledge not to indulge in such practices in competing for or executing this assignment.

We understand that BSFIC is not bound to accept any proposal it receives, and we accept BSFIC's right to modify the terms of appointment or cancel this proposal process without assigning any reason.

Yours sincerely,

On behalf of ACNABIN, Chartered Accountants

_________________________________

Muhammad Aminul Hoque, FCA,

Partner

ACNABIN, Chartered Accountants

BDBL Bhaban (Level-13 & 15), 12 Kawran Bazar C/A, Dhaka-1215.

Table of Contents

Letter of Transmittal	2

Response to EOI Eligibility & Information Requirements	4

Executive Summary	5

1. Understanding of the Assignment and the Client	6

2. Objectives and Scope of Services	7

3.  Scope of Services	7

4. Proposed Methodology	8

5. Detailed Work Plan	9

6. Team Composition and Key Experts	10

7. Responsibility Matrix	10

8. Quality Assurance Framework and Risk Assessment	11

9. Deliverables of the Assignment	12

10. Timeline of the Assignment	12

11. Relevant Experience	13

12. About ACNABIN Chartered Accountants	14

13. Conclusion	15

Appendices	16

# Response to EOI Eligibility & Information Requirements

The table below presents the information required in BSFIC's EOI Information Form (Chhok-Ka), cross-referenced with ACNABIN's Organizational Profile.

| EOI Requirement (Chhok-Ka) | ACNABIN's Response |
| --- | --- |
| Firm name, address, phone, fax, email | ACNABIN Chartered Accountants BDBL Bhaban (Level-13 & 15), 12 Kawran Bazar Commercial Area, Dhaka-1215, Bangladesh. Telephone: (+88-02) 41020030-35 Facsimile: (+88-02) 41020036 ISD (+88-02) 410 20037 E-mail: acnabin@bangla.net Web: www.acnabin.com |
| List of partners | Number of Partners: 08. - A.S.M Nayeem FCA - Iftekhar Hossain FCA - ATMA Bari FCA - Md. Moniruzzaman FCA - Md. Rokonuzzaman FCA - Md. Mominul Karim FCA - Md. Reajul Islam FCA - Muhammad Aminul Hoque FCA Profiles have been attached as Annex. |
| Qualified Members currently working at ACNABIN | FCAs: ACAs: Profiles have been attached as Annex. |
| Firm's date of establishment | 15 February 1985 - 41 years of continuous public practice. |
| Number of Course Completed (CC) students currently working at ACNABIN | Since its establishment, more than 2,000 students have completed their Chartered Accountancy Course Completion (CC) at ACNABIN. Currently, 406 articled students (284 registered and 122 probationary) are working at the firm. A detailed list, including their registration numbers, is attached as Annex F. |
| Number of articled students currently working at ACNABIN | 284 Students Detailed list with registration numbers has been attached as Annex. |
| Previous Experience: Government Organization | More Than 10 Government Organization |
| Previous Experience: Autonomous Bodies | More Than 10 Autonomous Bodies. |
| Previous Experience: Multinational Companies | More Than 10 Organizations |

# Executive Summary

ACNABIN, Chartered Accountants, is pleased to submit this Technical Proposal for the appointment of a Forensic Auditor to examine the Provident Fund (PF) accounts of Faridpur Sugar Mills Ltd. for the eleven-year period from FY 2015–16 to FY 2025–26, in accordance with the requirements of the Expression of Interest (EOI) issued by Bangladesh Sugar & Food Industries Corporation (BSFIC).

With over four decades of professional excellence, ACNABIN is Bangladesh's largest chartered accountancy partnership by professional manpower and an independent member firm of Baker Tilly International, the world's ninth-largest accounting network. Our extensive experience in statutory audits, internal audits, governance reviews, and financial compliance engagements across government, financial institutions, corporate entities, and development organizations, together with our established audit relationship with BSFIC and its affiliated enterprises, provides us with a strong understanding of the Corporation's financial reporting environment, governance framework, and operational context.

We understand that this assignment requires a comprehensive forensic examination of eleven years of Provident Fund transactions to assess the accuracy, completeness, and compliance of fund administration while identifying any instances of irregularity, misappropriation, fraud, or control weaknesses. The engagement demands an objective, evidence-based approach founded on independent verification, source-document reconciliation, transaction testing, analytical review, and thorough evaluation of internal controls to produce reliable and defensible findings.

Drawing upon our multidisciplinary team, structured forensic audit methodology, and robust quality assurance processes, ACNABIN is well positioned to deliver this assignment with the highest standards of professional independence, confidentiality, and technical excellence while ensuring full compliance with the requirements of BSFIC and applicable professional standards.

This proposal presents our understanding of the assignment, forensic audit methodology, project management approach, experienced engagement team, quality assurance framework, risk management strategy, and relevant experience. Our Financial Proposal has been submitted separately in accordance with the EOI requirements and the Least Cost Selection (LCS) procurement method.

# 1. Understanding of the Assignment and the Client

1.1 Understanding of the Assignment

ACNABIN understands that the assignment requires a comprehensive forensic audit of the Provident Fund (PF) accounts of Faridpur Sugar Mills Ltd. covering the eleven-year period from FY 2015–16 to FY 2025-26, in accordance with the requirements of Bangladesh Sugar & Food Industries Corporation (BSFIC) and applicable laws, regulations, and professional standards.

The engagement extends beyond a conventional financial audit by requiring an independent forensic examination of the PF's financial transactions, governance, and compliance framework to identify any irregularities, fraud, misappropriation, or control deficiencies. Our methodology has therefore been designed to integrate document verification, transaction testing, source-document reconciliation, forensic data analysis, stakeholder interviews, and evidence-based investigation techniques to produce reliable findings and practical recommendations.

1.2 Understanding of the Client

Faridpur Sugar Mills Ltd. is one of the state-owned sugar mills operating under Bangladesh Sugar & Food Industries Corporation (BSFIC). The mill maintains a recognized Provident Fund for its employees, requiring systematic administration of employee and employer contributions, investment of fund balances, benefit settlements, and compliance with applicable statutory and trust requirements.

Based on our review of the available information, including the mill's published financial statements, ACNABIN understands that this assignment will involve the examination of historical records spanning eleven financial years within an operating environment where financial control and record-management challenges have been identified by the statutory auditors. Accordingly, successful execution of the engagement will require a structured forensic methodology emphasizing independent verification, reconciliation with primary supporting documents, corroboration through external evidence where necessary, and comprehensive documentation to ensure that all findings are objective, evidence-based, and fully defensible.

# 2. Objectives and Scope of Services

- Authenticate the integrity, completeness, and timeliness of employer and employee PF contributions for each fiscal year from 2015-16 to 2025-26, reconciled against payroll records.

- Confirm the PF Trust's registration status and compliance with applicable rules governing recognized provident funds under Bangladesh law.

- Verify the investment of PF funds and the accuracy of interest/profit crediting to member accounts.

- Test withdrawals, loans against PF balances, and final settlements for procedural compliance and irregularities.

- Identify, and where possible quantify, any instances of misappropriation, delayed remittance, unauthorized withdrawal, or diversion of PF funds.

- Assess the adequacy of internal controls governing PF administration and recommend practical improvements.

# 3.  Scope of Services

Our proposed scope covers the following work streams across the 11-year review period:

(a) PF Governance & Compliance Review

- Review of the PF Trust Deed, Trust Rules, and registration status with the relevant tax/regulatory authority.

- Assessment of the PF's governing Board of Trustees composition and decision-making records.

(b) Contribution Reconciliation

- Reconciliation of employer (8.33%) and employee (10%) contributions against payroll registers for all eleven fiscal years, on a sample or full-population basis depending on data availability.

- Identification of any gaps, delays, or shortfalls in contribution remittance.

(c) Investment & Fund Management Testing

- Verification of PF fund investments against applicable recognized-PF investment rules.

- Testing of interest/profit calculation and crediting accuracy to individual member accounts.

(d) Withdrawal, Loan & Settlement Testing

- Testing of PF loan disbursements and repayment tracking against Trust Rules.

- Testing of final settlement calculations for retired, resigned, or deceased members' claims.

(e) Exception Identification & Reporting

- Compilation of a schedule of findings with quantified financial impact where determinable.

- Root-cause analysis and control-improvement recommendations.

# 4. Proposed Methodology

Our methodology is purpose-built for this assignment - a materially different discipline from a physical fixed-asset verification exercise, requiring data reconciliation, sampling, and forensic testing techniques rather than physical inspection. The approach below reflects ACNABIN's audit methodology, informed by International Standards on Auditing and our firm's special-audit/investigation experience.

4.1 Methodology Flow

- Entrance Meeting - Kick-off meeting with BSFIC and Faridpur Sugar Mills management to confirm scope, data-access arrangements, and key contacts.

- Document & Data Request - Formal request for the PF Trust Deed, Trust Rules, registration certificate, payroll registers, PF ledgers/member statements, bank and investment statements, and Board of Trustees minutes for FY 2015-16 to FY 2025-26.

- Data Digitization & Sampling Plan - Where records are paper-based or fragmented, digitization and a risk-based sampling plan will be developed, prioritizing years or categories flagged by preliminary risk indicators (e.g., known record gaps, staff turnover, mill management transitions).

- Contribution Reconciliation Testing - Line-by-line (or statistically sampled) reconciliation of PF contributions against payroll for each fiscal year, using data-analytics tools to accelerate testing across the 11-year population.

- Investment & Compliance Testing - Verification of fund investment activity and interest-crediting accuracy against Trust Rules and recognized-PF regulatory requirements.

- Withdrawal, Loan & Settlement Testing - Detailed testing of a sample (or full population, subject to volume) of withdrawal, loan, and final-settlement transactions.

- Exception Identification & Follow-Up - All exceptions identified are logged, discussed with management for explanation, and corroborated against independent evidence before being carried forward as findings.

- Draft Findings & Management Response - A draft report is issued to BSFIC/Faridpur Sugar Mills management for factual verification and formal response before finalization.

- Final Report - Incorporating management responses, the Final Forensic Audit Report is issued with a quantified schedule of findings and recommendations.

4.2 Data Analytics Approach

Given the eleven-year scope, we propose using structured data-analytics techniques (e.g., full-population reconciliation in spreadsheet/database tools rather than manual sampling alone, wherever underlying data can be obtained in electronic form) to materially increase testing coverage without proportionately increasing timeline or cost - a standard technique in modern forensic engagements that also strengthens the defensibility of our findings.

# 5. Detailed Work Plan

ACNABIN will execute the assignment through a structured forensic audit approach designed to ensure systematic investigation, effective coordination with BSFIC, and timely completion of the assignment. The detailed work plan is summarized below.

| Phase / Activity | Description |
| --- | --- |
| Phase 1 - Planning & Data Collection | Entrance meeting; formal data request; inception report covering confirmed scope, data-access status, and revised timeline if needed. |
| Phase 2 - Fieldwork: Contribution Testing | Reconciliation of PF contributions against payroll for all 11 fiscal years. |
| Phase 3 - Fieldwork: Investment & Settlement Testing | Investment verification, interest-crediting checks, withdrawal/loan/settlement testing. |
| Phase 4 - Exception Analysis | Consolidation of exceptions, management discussion, quantification of impact. |
| Phase 5 - Draft Reporting | Draft Forensic Audit Report issued for management response. |
| Phase 6 - Finalization | Final Forensic Audit Report incorporating management responses, submitted with Schedule of Findings. |

# 6. Team Composition and Key Experts

ACNABIN has assembled a multidisciplinary team of experienced Chartered Accountants and forensic audit professionals with extensive expertise in forensic investigations, fraud risk assessment, financial analysis, and compliance reviews. The proposed team combines strong technical knowledge with practical experience in conducting special audits, forensic examinations, and investigative assignments for public- and private-sector organizations, ensuring the effective execution of this engagement from planning through final reporting.

| Name | Proposed Role | Relevant Background |
| --- | --- | --- |
| Abu Sayed Mohammed Nayeem, FCA, FCCA (UK), ACA (ICAEW) | Team Leader / Engagement Partner | Partner with international qualifications (FCCA, ACA-ICAEW) alongside FCA; oversees engagement quality, client relationship, and final report sign-off. |
| Md. Foij Ahmed, ACGA | Deputy Team Leader - Legal & Investigation Lead | Director with M.Com, MPA, and LLB qualifications; leads the legal/compliance review of PF Trust governance and coordinates exception follow-up with management. |
| Abu Nasar Mohammad Shakawath Hossain, CISA, CEH | IT & Data Forensics Specialist | Director with B.Sc (CIS), CISA, and CEH credentials; leads data digitization, full-population reconciliation analytics, and data-integrity testing across the 11-year record set. |
| Two Senior/Assistant Managers (to be confirmed) | Forensic Audit Associates | Drawn from ACNABIN's Audit & Assurance team; conduct fieldwork testing, sampling, and documentation under Deputy Team Leader supervision. |
| Articled Student(s) (to be confirmed) | Data & Documentation Support | Support data entry, file organization, and working-paper preparation. |

# 7. Responsibility Matrix

The assignment will be executed through a collaborative approach with clearly defined responsibilities for ACNABIN and BSFIC/Faridpur Sugar Mills Ltd., ensuring effective coordination, timely access to records and personnel, robust quality control, and the successful delivery of the forensic audit.

| Activity | ACNABIN | BSFIC / Faridpur Sugar Mills Ltd. |
| --- | --- | --- |
| Entrance meeting and confirmation of assignment scope | ✓ | ✓ |
| Preparation of the audit information request and document checklist | ✓ |  |
| Provision of PF records, payroll data, ledgers, bank statements, and supporting documents |  | ✓ |
| Nomination of liaison personnel and facilitation of access to records and personnel |  | ✓ |
| Mobilization of the forensic audit team | ✓ |  |
| Forensic examination, transaction testing, and evidence collection | ✓ |  |
| Clarification of audit queries and provision of additional information |  | ✓ |
| Discussion of preliminary findings | ✓ | ✓ |
| Engagement Partner review and quality assurance | ✓ |  |
| Review of and response to the Draft Forensic Audit Report |  | ✓ |
| Submission of the Final Forensic Audit Report | ✓ |  |

# 8. Quality Assurance Framework and Risk Assessment

8.1 Quality Assurance

As with all ACNABIN engagements, this assignment will be subject to the firm's standard two-tier quality control: the Engagement Partner (Team Leader) is responsible for day-to-day technical direction and sign-off, while an independent Concurring Partner - not otherwise involved in the engagement - will review the draft findings and report before issuance, consistent with ACNABIN's firm-wide quality assurance policy and ICAB/Baker Tilly International practice standards.

8.2 Risk Assessment and Mitigation

| Risk | Potential Impact | Mitigation |
| --- | --- | --- |
| Incomplete or missing PF/payroll records across the 11-year period | Testing coverage gaps; findings that cannot be fully substantiated | Corroborate via alternate sources - bank statements, tax filings, external correspondence - and clearly disclose any residual scope limitations in the final report |
| Management or custodianship transition during the assignment (given reported privatization discussions) | Disruption to data access and continuity of client liaison | Early, complete data request at inception; formal escalation path agreed with BSFIC head office in case of local access disruption |
| Compressed EOI submission timeline relative to assignment complexity | Risk of underscoping at proposal stage | Phased reporting approach with an early inception report to reconfirm scope and timeline once real data volumes are known |

# 9. Deliverables of the Assignment

- Inception Report (scope confirmation, data-access status, revised work plan if needed)

- Draft Forensic Audit Report with preliminary Schedule of Findings

- Final Forensic Audit Report incorporating management responses

- Schedule of Findings with quantified financial impact, where determinable

# 10. Timeline of the Assignment

The assignment will be implemented through a structured six-phase forensic audit approach over a period of 60 calendar days to ensure systematic investigation, timely completion, and compliance with the requirements of BSFIC and applicable professional standards.

| Activity | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Initiation & Mobilization | █ |  |  |  |  |  |  |  |
| Document Collection & Planning | █ | █ |  |  |  |  |  |  |
| Contribution Verification |  | █ | █ | █ |  |  |  |  |
| Investment & Benefit Verification |  |  | █ | █ | █ |  |  |  |
| Exception Analysis & Investigation |  |  |  | █ | █ | █ |  |  |
| Internal Quality Review |  |  |  |  |  | █ |  |  |
| Draft Forensic Audit Report |  |  |  |  |  | █ |  |  |
| Client Review & Management Response |  |  |  |  |  |  | █ |  |
| Final Forensic Audit Report Submission |  |  |  |  |  |  |  | █ |

# 11. Relevant Experience

ACNABIN possesses extensive experience in conducting forensic investigations, special audits, statutory audits, and governance reviews for government, financial, corporate, and development-sector organizations. Our experience in examining employee benefit funds, financial controls, and regulatory compliance, together with our long-standing audit relationship with BSFIC and its affiliated enterprises, provides a strong foundation for the successful execution of this assignment

Selected Relevant Engagements

- Special Audit – People's Oriented Program Implementation (POPI): Conducted a special audit involving forensic examination, investigation of financial irregularities, and evidence-based reporting.

- Bangladesh Sugar & Food Industries Corporation (BSFIC): Statutory audit engagements for BSFIC and several of its affiliated enterprises, providing extensive familiarity with the Corporation's financial reporting environment and governance framework.

- Banking Sector Audits: Statutory and internal audits for leading financial institutions, including Prime Bank PLC, AB Bank PLC, Trust Bank PLC, Islami Bank Bangladesh PLC, and others, involving verification of provident fund contributions, investments, and benefit settlements as part of routine audit procedures.

- Development Sector and NGO Audits: Audit and advisory assignments for organizations including BRAC, PKSF, and other development partners, covering fund governance, fiduciary controls, regulatory compliance, and financial accountability.

# 12. About ACNABIN Chartered Accountants

12.1 About ACNABIN

ACNABIN Chartered Accountants, established in 1985, is one of Bangladesh's leading professional services firms, providing audit, assurance, advisory, taxation, risk consulting, and business support services to clients across the public and private sectors. With over four decades of professional experience, ACNABIN has built a strong reputation for delivering high-quality, technically sound, and practical solutions to complex corporate and government engagements.

12.2 Why ACNABIN for This Assignment

ACNABIN offers a combination of forensic audit expertise, sector knowledge, and institutional capacity that is well aligned with the requirements of this assignment. Our key strengths include:

- Proven experience in conducting forensic investigations, special audits, statutory audits, and governance reviews for public- and private-sector organizations.

- An established forensic audit methodology integrating document review, transaction testing, data analysis, evidence-based investigation, and rigorous quality assurance.

- Existing audit experience with BSFIC and its affiliated enterprises, providing familiarity with the Corporation's financial reporting environment and operational context.

- Extensive experience in verifying employee provident funds, investments, and benefit settlements through our statutory audit engagements with banks, financial institutions, NGOs, and corporate entities.

- An "A" grade awarded by Bangladesh Bank and inclusion in the Bangladesh Securities and Exchange Commission's panel of approved audit firms for listed companies, reflecting ACNABIN's commitment to quality and professional excellence.

- The professional resources and organizational capacity to execute large-scale forensic assignments while maintaining independence, confidentiality, and timely delivery.

12.3 Value Addition

Beyond the core scope, ACNABIN will provide BSFIC and Faridpur Sugar Mills management with practical, prioritized recommendations for strengthening PF governance and internal controls going forward - recognizing that the value of a forensic review lies not only in identifying past exceptions, but in reducing the likelihood of recurrence.

# 13. Conclusion

ACNABIN appreciates the opportunity to submit this Technical Proposal for the appointment of a Forensic Auditor to examine the Provident Fund (PF) accounts of Faridpur Sugar Mills Ltd. for the period from FY 2015–16 to FY 2025–26.

Drawing on our extensive experience in forensic investigations, special audits, statutory audits, and governance reviews, together with our multidisciplinary team and structured forensic audit methodology, we are confident in our ability to deliver the assignment professionally, independently, and in full compliance with the requirements of BSFIC and applicable professional standards.

We look forward to the opportunity to work with BSFIC and Faridpur Sugar Mills Ltd. and to contribute to strengthening the governance, transparency, and integrity of the Provident Fund through an objective, evidence-based forensic audit.

# Appendices

The following documents form part of this Technical Proposal and are attached as appendices for reference:

- Annex A – Trade License

- Annex B - Tax Registration Certificate

- Annex C - VAT Registration Certificate

- Annex D - Firm Registration ICAB

- Annex E - FRC Enlistment Certificate

- Annex F - ACNABIN Organizational Profile, including Partner Profiles, Professional Manpower, Article Student Information, and Relevant Project Experience

The Financial Proposal has been submitted separately in accordance with the requirements of the Expression of Interest (EOI).