TECHNICAL PROPOSAL

for

Revaluation of Assets and Liabilities and Preparation of a Fixed Assets Register (FAR) with Asset Tagging for

NORTH BENGAL SUGAR MILLS LTD.

Submitted to:

Chief Auditor

Bangladesh Sugar & Food Industries Corporation (BSFIC)

Chinishilpa Bhaban (8th Floor), 3 Dilkusha C/A, Dhaka-1000

EOI Ref: 36.04.0000.022.17.001.26/677 dated 29 July 2026

Submitted by:

ACNABIN, Chartered Accountants

An Independent Member Firm of Baker Tilly International

BDBL Bhaban (Level-13 & 15), 12 Kawran Bazar Commercial Area, Dhaka-1215

| Contact Info: Abdullah-Al-Mamun, FCA Director, Audit & Consultancy ACNABIN, Chartered Accountants Email: mamun.abdullah@acnabin-bd.com Phone: +8801915-561888 | Secondary Contact: Md. Shif All Mostakin Assistant Director, Audit & Consultancy ACNABIN, Chartered Accountants Email: mostakin@acnabin-bd.com Phone: +8801820-584481 |
| --- | --- |

# Letter of Transmittal

Ref: 01.18/2026/0000 (i)

Date: [To be finalized on submission]

To

The Chief Auditor

Bangladesh Sugar & Food Industries Corporation (BSFIC)

Chinishilpa Bhaban (8th Floor)

3 Dilkusha C/A, Dhaka-1000.

Dear Sir,

We, the undersigned, offer to provide consulting services for the Revaluation of Assets and Liabilities and Preparation of a Fixed Assets Register (FAR) with Asset Tagging for North Bengal Sugar Mills Ltd., in accordance with your Expression of Interest Ref. 36.04.0000.022.17.001.26/677 dated 29 July 2026, the Finance Division Monitoring Cell's prescribed format, and our enclosed Technical Proposal. Our Financial Proposal is submitted separately under sealed cover, as required.

If our Proposal is accepted, we undertake to commence the assignment within the timeframe specified by BSFIC following formal engagement, and our Proposal shall remain binding upon us, subject to any modifications resulting from contract negotiations.

We confirm that the Government of Bangladesh has not declared ACNABIN, or any of its partners or proposed staff, ineligible on charges of engaging in corrupt, fraudulent, collusive, or coercive practices, and we pledge not to indulge in such practices in competing for or executing this assignment.

We understand that BSFIC is not bound to accept any proposal it receives, and we accept BSFIC's right to modify the terms of appointment or cancel this proposal process without assigning any reason.

Yours sincerely,

On behalf of ACNABIN, Chartered Accountants

_________________________________

Muhammad Aminul Hoque, FCA

Partner

ACNABIN, Chartered Accountants

BDBL Bhaban (Level-13 & 15), 12 Kawran Bazar C/A, Dhaka-1215

Table of Contents

Letter of Transmittal	2

Executive Summary	4

Response to EOI Eligibility & Information Requirements	5

1. Understanding of the Assignment	6

2. Objectives of the Assignment	7

3. Scope of the Assignment	7

4. Proposed Methodology	8

5. Detailed Work Plan	9

6. Team Composition and Key Experts	10

7. Responsibility Matrix	11

8. Quality Assurance and Risk Assessment	12

9. Deliverables of the Assignment	13

10. Timeline of the Assignment	13

11. Relevant Experience	14

12. About ACNABIN Chartered Accountants	15

13. Conclusion	16

Appendices	17

# Executive Summary

ACNABIN, Chartered Accountants, is pleased to submit this Technical Proposal for the Revaluation of Assets and Liabilities and Preparation of a Fixed Assets Register (FAR) with Asset Tagging for North Bengal Sugar Mills Ltd. (NBSML) in accordance with the requirements of the Finance Division's Monitoring Cell, Ministry of Finance, and the Expression of Interest (EOI) issued by Bangladesh Sugar & Food Industries Corporation (BSFIC).

With over four decades of professional excellence and extensive experience in asset verification, valuation, and fixed asset management, ACNABIN has successfully delivered similar assignments for leading public and private sector organizations across Bangladesh. Our portfolio includes Titas Gas Transmission Company Limited, (Need to add more govt org) Berger Paints Bangladesh Limited, Prime Bank Limited, Urmi Group, Union Group, Partex Star Group, Unique Hotel & Resorts Limited, Shun Shing Edible Oil Limited, Opex & Sinha Textile Group, China-Bangla Ceramics Industries Limited, and Bangladesh-China Power Company (Pvt.) Limited (BCPCL). These engagements demonstrate our capability to execute large-scale assignments requiring comprehensive physical verification, asset tagging, valuation, reconciliation, and preparation of reliable Fixed Assets Registers.

We understand that this assignment presents unique technical and operational challenges. North Bengal Sugar Mills Ltd. possesses a diverse asset portfolio comprising legacy industrial assets dating back to 1933 alongside modern facilities developed under the co-generation and refinery modernization programme. In addition, the assignment encompasses the revaluation of liabilities, requiring an integrated methodology that combines technical expertise, rigorous field verification, sound valuation practices, and robust documentation to produce a complete and compliant asset management framework.

Drawing upon our proven methodology, multidisciplinary team, and established quality assurance processes, ACNABIN is well positioned to deliver the assignment efficiently while ensuring full compliance with the Finance Division's Monitoring Cell guidelines and applicable financial reporting and valuation standards.

This proposal presents our understanding of the assignment, implementation methodology, project management approach, experienced engagement team, quality assurance framework, risk management strategy, and relevant experience. Our Financial Proposal has been submitted separately in accordance with the EOI requirements and the Least Cost Selection (LCS) procurement method.

# Response to EOI Eligibility & Information Requirements

The table below presents the information required in BSFIC's EOI Information Form (Chhok-Ka), cross-referenced with ACNABIN's Organizational Profile.

| EOI Requirement (Chhok-Ka) | ACNABIN's Response |
| --- | --- |
| Firm name, address, phone, fax, email | ACNABIN Chartered Accountants BDBL Bhaban (Level-13 & 15), 12 Kawran Bazar Commercial Area, Dhaka-1215, Bangladesh. Telephone: (+88-02) 41020030-35 Facsimile: (+88-02) 41020036 ISD (+88-02) 410 20037 E-mail: acnabin@bangla.net Web: www.acnabin.com |
| List of partners | Number of Partners: 08. - A.S.M Nayeem FCA - Iftekhar Hossain FCA - ATMA Bari FCA - Md. Moniruzzaman FCA - Md. Rokonuzzaman FCA - Md. Mominul Karim FCA - Md. Reajul Islam FCA - Muhammad Aminul Hoque FCA Profiles have been attached as Annex- F. |
| Qualified Members currently working at ACNABIN | FCAs: ACAs: Profiles have been attached as Annex. |
| Firm's date of establishment | 15 February 1985 |
| Number of Course Completed (CC) and Number of Articled Students Currently Working | Since its establishment, more than 2,000 students have completed their Chartered Accountancy Course Completion (CC) at ACNABIN. Currently, 406 articled students (284 registered and 122 probationary) are working at the firm. A detailed list, including their registration numbers, is attached as Annex F. |
| Number of articled students currently working at ACNABIN | 284 Students |
| Previous Experience: Government Organization | More Than 10 Government Organization |
| Previous Experience: Autonomous Bodies | More Than 10 Autonomous Bodies. |
| Previous Experience: Multinational Companies | More Than 10 Organizations |

# 1. Understanding of the Assignment and the Client

1.1 Understanding of the Assignment

ACNABIN understands that the assignment requires the revaluation of assets and liabilities of North Bengal Sugar Mills Ltd. (NBSML), together with the preparation of a comprehensive Fixed Assets Register (FAR) supported by physical asset tagging. The assignment will be undertaken in accordance with the requirements of BSFIC, the guidelines of the Finance Division's Monitoring Cell, and applicable financial reporting and valuation standards.

Unlike a conventional FAR assignment, this engagement also encompasses the revaluation of liabilities, requiring a coordinated approach that integrates physical verification, valuation, reconciliation, and financial analysis. ACNABIN's methodology has been designed to address these requirements through a systematic and practical implementation approach, ensuring the delivery of accurate, reliable, and fully compliant outputs.

1.2 Understanding of the Client

North Bengal Sugar Mills Ltd. (NBSML), one of the sugar mills operating under Bangladesh Sugar & Food Industries Corporation (BSFIC), has a diverse asset base developed over more than nine decades. The mill comprises legacy production facilities established in 1933 together with assets introduced under the co-generation and refinery modernization programme initiated in 2014. Consequently, the asset portfolio reflects significant variations in age, condition, remaining useful life, and supporting documentation.

Based on our experience in delivering similar assignments for large industrial and public-sector organizations, ACNABIN understands that the successful execution of this engagement requires a structured methodology for physical verification, asset classification, valuation, reconciliation, and tagging. Our approach is therefore designed to accommodate the complexity of the mill's asset portfolio while producing a reliable, auditable, and sustainable Fixed Assets Register that supports effective asset management and financial reporting.

# 2. Objectives of the Assignment

- Identify, physically verify, and classify all fixed assets of North Bengal Sugar Mills Ltd. - land and buildings, plant and machinery, vehicles, office and electrical equipment, and furniture and fixtures.

- Revalue identified fixed assets in accordance with the Monitoring Cell's prescribed methodology and applicable valuation standards (IVS, IFRS, IAS).

- Review and revalue major liability classes as directed by BSFIC, in a workstream run in parallel with the asset verification.

- Physically tag all fixed assets per a standard design agreed with BSFIC / the Monitoring Cell.

- Prepare a Fixed Assets Register in the Monitoring Cell's prescribed format, reconciled against the mill's existing accounting records.

# 3. Scope of the Assignment

Our proposed scope covers the following asset classes and work streams:

(a) Asset Identification, Verification & Classification

- Land & Buildings

- Plant & Machinery (including both legacy equipment and the co-generation/modernization assets, tracked separately given their differing vintage)

- Motor Vehicles

- Office & Electrical Equipment

- Furniture & Fixtures

(b) Valuation

- Assignment of value at historical cost from accounting records, purchase documents, and bills of quantities where available.

- Use of alternate sources - market comparables, replacement cost, online/local marketplace pricing - where original documentation is incomplete.

- Classification, valuation, and depreciation on an asset-class basis, following IVS/IFRS/IAS.

(c) Liabilities Revaluation

- Review of major liability classes (loans, payables, provisions) - precise scope to be confirmed with BSFIC at inception.

(d) Tagging & Register Preparation

- Design and physical application of asset ID tags per a design agreed with BSFIC / the Monitoring Cell.

- Preparation of a unit-wise and consolidated Fixed Assets Register aligned to the Monitoring Cell's prescribed format.

# 4. Proposed Methodology

Our methodology builds upon ACNABIN's proven approach to fixed asset verification, valuation, tagging, and Fixed Assets Register (FAR) preparation. For this assignment, we have expanded the methodology to incorporate a parallel liability review in line with the scope of the EOI. The final FAR will be prepared in accordance with the format prescribed by the BSFIC Monitoring Cell, with our working templates remapped accordingly once the complete format is made available.

4.1 Methodology Flow

- Entrance Meeting - Kick-off meeting with BSFIC and North Bengal Sugar Mills management to confirm scope, site access, and key contacts.

- Team Organization & Briefing - Formation of location-wise data collection teams; briefing on asset classes, tagging conventions, and the vintage-mix considerations specific to this mill.

- Data Collection Sheet & Movement Register Design - Preparation of a standard data collection sheet and asset movement register, sign-off with mill management.

- Physical Counting & Initial Tagging - Physical identification, location capture, and condition assessment of all fixed assets, with initial tagging.

- Verification Against Records - Reconciliation of physically identified assets against the mill's existing asset register and accounting records.

- Value Assignment - Assignment of value at historical cost where documentation permits, supplemented by alternate sources (market comparables, replacement cost) where it does not.

- Liabilities Review - Parallel review of major liability classes against loan agreements, payable schedules, and provisioning records.

- Draft FAR & Verification Report - Preparation of a draft Asset Verification & Classification Report and draft Fixed Assets Register, sent to BSFIC/mill management for feedback.

- Sample Recounting & Final Tagging - Sample-basis recounting before final tagging; final tag design and printing sign-off with BSFIC.

- Final FAR & Report - Incorporation of client feedback; submission of the Final Fixed Assets Register and Report, remapped to the Monitoring Cell format.

4.2 Adapting to the Monitoring Cell Format

Our asset verification templates and Fixed Assets Register (FAR) are developed based on ACNABIN's proven methodology and capture all key information required for effective asset management, including asset classification, tag number, location, physical condition, acquisition details, useful life, depreciation, and carrying value. Upon receipt of the Monitoring Cell's prescribed format, we will map our verified asset database and FAR to the required structure to ensure full compliance with BSFIC's reporting requirements. Any structural or formatting changes required to align with the prescribed format will be incorporated without additional cost as part of our commitment to delivering a fully compliant final deliverable.

# 5. Detailed Work Plan

ACNABIN will execute the assignment through a structured five-phase implementation approach designed to ensure timely completion, effective coordination with BSFIC, and compliance with the Finance Division's Monitoring Cell requirements.

| Phase | Key Activities |
| --- | --- |
| Phase 1 - Project Initiation | Kick-off meeting, confirmation of scope, review of available records, project planning, and team mobilization. |
| Phase 2 - Physical Verification & Tagging | Physical identification, verification, classification, condition assessment, and asset tagging across all asset categories. |
| Phase 3 - Valuation & Reconciliation | Revaluation of assets and liabilities, reconciliation with accounting records, and application of appropriate valuation methodologies. |
| Phase 4 - FAR Preparation & Quality Review | Preparation of the draft Fixed Assets Register, internal quality review, and validation with BSFIC and mill management. |
| Phase 5 - Final Reporting & Handover | Incorporation of client feedback, finalization of the FAR, submission of the final report, and project close-out. |

# 6. Team Composition and Key Experts

The ACNABIN has assembled a multidisciplinary team of experienced Chartered Accountants, engineers, and fixed asset specialists with extensive expertise in asset verification, valuation, asset tagging, and Fixed Assets Register (FAR) preparation. The proposed team combines technical knowledge with practical experience in delivering similar assignments for large industrial and public-sector organizations, ensuring the effective execution of this engagement from planning through final reporting.

| Name | Proposed Role | Relevant Background |
| --- | --- | --- |
| Muhammad Aminul Hoque, FCA | Team Leader / Engagement Partner | Partner with 15+ years' experience; has personally led fixed-asset verification, tagging, and valuation engagements for Urmi Group, Unique Hotel & Resorts, Union Group, Partex Star Group, Berger Paints, Prime Bank, and BCPCL, among others. |
| Mahmudur Rahman, FCA, CIMA (UK) | Deputy Team Leader | Director; forms and instructs data collection teams, reviews draft and final verification/classification reports and the Fixed Assets Register, and oversees the value-assignment process. |
| Bhola Nath Kundu, ACA | Field Supervisor | Associate Director (Head of Quality Assurance); has directly supervised and coordinated multiple fixed-asset counting, tagging, register-preparation, and valuation assignments. |
| Technical Experts (Mechanical, Electrical & Civil Engineers) | Field Technical Support | Engineering staff experienced in classifying and assessing plant, electrical, and civil assets across mixed-vintage industrial sites - directly relevant to North Bengal's legacy-plus-modernization asset mix. |
| Fixed Assets Specialists (2) | Fieldwork & Documentation | Managers with direct fixed-asset counting, tagging, and register-preparation experience across ACNABIN's prior FAR engagements. |
| Articled Student(s) (to be confirmed) | Data & Documentation Support | Support data entry, file organization, and working-paper preparation. |

# 7. Responsibility Matrix

| Activity | ACNABIN | BSFIC / NBSML |
| --- | --- | --- |
| Entrance meeting and confirmation of project scope | ✓ | ✓ |
| Preparation of data collection templates and asset movement register | ✓ |  |
| Review and approval of data collection templates and movement register |  | ✓ |
| Mobilization of field verification and asset tagging teams | ✓ |  |
| Nomination of site personnel to facilitate field activities |  | ✓ |
| Provision of the existing Fixed Assets Register, accounting records, and supporting asset and liability documents |  | ✓ |
| Physical verification, asset classification, valuation, and reconciliation | ✓ |  |
| Finalization of asset identification and tagging methodology | ✓ | ✓ |
| Procurement and printing of approved asset tags |  | ✓ |
| Installation of asset tags and joint verification of completed tagging | ✓ | ✓ |
| Engagement Partner review and quality assurance | ✓ |  |
| Review and feedback on the Draft Fixed Assets Register and Draft Report |  | ✓ |
| Submission of the Final Fixed Assets Register and Final Report | ✓ |  |

The assignment will be executed through a multidisciplinary team with clearly defined roles and responsibilities, ensuring effective coordination between ACNABIN and BSFIC, robust quality control, and the timely delivery of all project outputs.

# 8. Quality Assurance and Risk Assessment

8.1 Quality Assurance

ACNABIN is committed to delivering services that meet the highest standards of professional quality and technical excellence. This assignment will be subject to the Firm's established quality assurance framework, comprising continuous supervision by the Engagement Partner and an independent technical review by a Concurring Partner prior to the issuance of the final deliverables. This review process ensures compliance with applicable professional standards, ACNABIN's quality management policies, and Baker Tilly International's quality assurance framework.

8.2 Risk Assessment and Mitigation

| Risk | Potential Impact | Mitigation Strategy |
| --- | --- | --- |
| Delay in obtaining the prescribed FAR format or project information | Delay in preparation of the final FAR and supporting schedules | Develop the FAR using ACNABIN's standard framework and align it with the prescribed format upon confirmation without affecting the project timeline. |
| Incomplete or outdated asset records and supporting documentation | Challenges in asset identification and valuation | Perform comprehensive physical verification and apply appropriate alternative valuation techniques where supporting documentation is unavailable, with all assumptions appropriately documented. |
| Unclear scope of liability revaluation | Potential scope variations and project delays | Confirm the scope and methodology for liability revaluation during the inception phase and document the agreed approach in the Inception Report. |
| Mixed-vintage asset base with varying conditions and useful lives | Inconsistent valuation and depreciation assumptions | Classify assets by category, age, and condition, and apply appropriate valuation methodologies and useful-life assumptions for each asset class. |
| Limited access to assets or operational constraints during fieldwork | Delays in physical verification and project completion | Coordinate closely with BSFIC and mill management to establish a detailed site access schedule and ensure timely availability of responsible personnel and relevant records. |

# 9. Deliverables of the Assignment

- Inception Report

- Data Collection Sheet & Asset Movement Register

- Draft Asset Verification & Classification Report

- Draft Fixed Assets Register (Monitoring Cell format) with valuation

- Liabilities Revaluation Summary

- Final Fixed Assets Register and Report, plus Tagging Completion Report

# 10. Timeline of the Assignment

The assignment will be implemented through a structured five-phase approach over a period of 45 calendar days to ensure timely delivery and compliance with the requirements of BSFIC and the Finance Division's Monitoring Cell.

| Activity | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Initiation & Mobilization | █ |  |  |  |  |  |  |
| Document Review & Planning | █ |  |  |  |  |  |  |
| Physical Verification |  | █ | █ | █ |  |  |  |
| Asset Tagging |  | █ | █ | █ |  |  |  |
| Asset & Liability Revaluation |  |  |  | █ | █ |  |  |
| FAR Preparation |  |  |  |  | █ | █ |  |
| Internal Quality Review |  |  |  |  |  | █ |  |
| Draft Report Submission |  |  |  |  |  | █ |  |
| Client Review & Finalization |  |  |  |  |  | █ | █ |
| Final Report & FAR Submission |  |  |  |  |  |  | █ |

# 11. Relevant Experience

ACNABIN's relevant experience for this assignment is direct and extensive: fixed-asset identification, verification, tagging, valuation, and Fixed Assets Register preparation is a core, recurring service line for the firm, delivered for organizations spanning manufacturing, hospitality, banking, and - most comparably - the power sector state enterprise BCPCL. A representative selection is summarized below; full assignment case studies and CVs of the proposed team are attached as Annexes.

| Client | Scope | Scale |
| --- | --- | --- |
| Bangladesh-China Power Company (Pvt.) Ltd. (BCPCL) | Identification, verification, classification, tagging & FAR preparation for a large state-affiliated power enterprise | Multi-month engagement; closest comparable to this assignment in public-sector character and scale |
| Urmi Group | Identification, verification, reconciliation & tagging of fixed assets across a diversified manufacturing group | 15 staff-months; Tk. 1,000,000 contract value |
| Unique Hotel & Resorts Limited | Full fixed-asset identification, verification & FAR development, including a standard register built for ongoing SAP-based maintenance | 8 staff-months; Tk. 1,500,000 contract value |
| Berger Paints Bangladesh Limited | Identification, verification, reconciliation & tagging of fixed assets across multiple sites (Dhaka, Gazipur) | 12 staff-months; Tk. 1,000,000 contract value |
| Prime Bank Limited | Identification, verification, reconciliation & tagging of fixed assets for a top-tier commercial bank | 20-person team; Tk. 1,700,000 contract value; multi-year continuous engagement |

# 12. About ACNABIN Chartered Accountants

12.1 About ACNABIN

ACNABIN Chartered Accountants, established in 1985, is one of Bangladesh's leading professional services firms, providing audit, assurance, advisory, taxation, risk consulting, and business support services to clients across the public and private sectors. With over four decades of professional experience, ACNABIN has built a strong reputation for delivering high-quality, technically sound, and practical solutions to complex business and government engagements.

12.2 Why ACNABIN for This Assignment

ACNABIN offers a combination of technical expertise, industry experience, and implementation capability that is well aligned with the requirements of this assignment. Our key strengths include:

- Proven experience in physical asset verification, valuation, asset tagging, and Fixed Assets Register (FAR) preparation for large industrial and public-sector organizations.

- An established methodology that integrates physical verification, engineering assessment, valuation, reconciliation, and quality assurance to ensure accurate and reliable project outcomes.

- A multidisciplinary team comprising Chartered Accountants together with Mechanical, Electrical, and Civil Engineers experienced in evaluating complex industrial assets of varying age and condition.

- Extensive experience working with government organizations, state-owned enterprises, and large corporate entities, enabling efficient stakeholder coordination and effective project delivery.

- An "A" grade awarded by Bangladesh Bank and inclusion in the Bangladesh Securities and Exchange Commission's panel of approved audit firms for listed companies, reflecting ACNABIN's professional standing and commitment to quality.

- The organizational capacity and professional resources to execute large-scale field verification assignments while maintaining rigorous quality control and meeting project timelines.

12.3 Value Addition

In addition to the required deliverables, ACNABIN will provide practical value that supports the long-term management of fixed assets at North Bengal Sugar Mills Ltd., including:

- A structured and user-friendly Fixed Assets Register that can be readily maintained and updated by management.

- Standardized asset identification and tagging practices to strengthen asset traceability and control.

- Practical recommendations for improving fixed asset governance, record management, and internal control practices.

- Identification of discrepancies between physical assets and accounting records, together with recommendations for corrective action where applicable.

- Knowledge sharing with designated client personnel on the maintenance and periodic updating of the Fixed Assets Register to support its long-term sustainability.

# 13. Conclusion

ACNABIN appreciates the opportunity to submit this Technical Proposal for the revaluation of assets and liabilities and the preparation of a Fixed Assets Register (FAR) with asset tagging for North Bengal Sugar Mills Ltd.

Drawing on our extensive experience in asset verification, valuation, and Fixed Assets Register preparation, together with our multidisciplinary team and structured implementation methodology, we are confident in our ability to deliver the assignment efficiently, professionally, and in full compliance with the requirements of BSFIC and the Finance Division.

We look forward to the opportunity to work with BSFIC and North Bengal Sugar Mills Ltd. and to contribute to strengthening the organization's asset management and financial reporting framework.

# Appendices

The following documents form part of this Technical Proposal and are attached as appendices for reference:

- Annex A – Trade License

- Annex B - Tax Registration Certificate

- Annex C - VAT Registration Certificate

- Annex D - Firm Registration ICAB

- Annex E - FRC Enlistment Certificate

- Annex F - ACNABIN Organizational Profile, including Partner Profiles, Professional Manpower, Article Student Information, and Relevant Project Experience.

The Financial Proposal has been submitted separately in accordance with the requirements of the Expression of Interest (EOI).